## Project Overview
BEDAGANG ERP - FULL DEVELOPMENT PROJECT PLAN
Project Name | Bedagang ERP - Modern Retail Management Platform
Version | 1.0.0
Platform | Web (Next.js) + Mobile (React Native)
Backend | Node.js + Sequelize + PostgreSQL
Frontend | Next.js + React + TailwindCSS + shadcn/ui
Mobile | React Native + Expo
Start Date | 2025-04-01
End Date | 2026-03-03
Total Duration | 48 Weeks (~12 Months)
Total Modules | 36 Modules
GOAL | Membangun platform ERP retail terintegrasi yang mencakup POS, Inventory, Finance, HRIS, CRM, SFA, Manufacturing, Fleet, dan modul enterprise lainnya untuk mendukung bisnis multi-cabang dengan arsitektur multi-tenant SaaS.
OBJECTIVES
1. | Menyediakan sistem POS modern dengan dukungan multi-payment dan offline mode
2. | Inventory management real-time dengan multi-warehouse dan stock opname
3. | Sistem keuangan lengkap dari Finance Lite hingga Full Accounting
4. | HRIS komprehensif termasuk payroll, attendance, dan performance management
5. | CRM & SFA untuk pengelolaan pelanggan dan tenaga penjualan lapangan
6. | Modul enterprise: Manufacturing, Fleet, TMS, Asset, Project Management
7. | Integrasi marketplace (Tokopedia, Shopee) dan WhatsApp Business
8. | Mobile app untuk kasir, sales lapangan, driver, dan karyawan (ESS)
9. | Multi-tenant SaaS dengan billing dan subscription management
10. | Website builder untuk toko online sederhana
PHASE TIMELINE
Phase 1 - Foundation | Week 1-8 ¦ Auth, Onboarding, Branch, Settings (4 modules)
Phase 2 - Core Commerce | Week 7-18 ¦ Products, POS, Inventory, Purchase Orders (4 modules)
Phase 3 - Customer & Engagement | Week 15-22 ¦ Customers, Loyalty, Promo, CRM (4 modules)
Phase 4 - Operations | Week 19-30 ¦ Kitchen, Tables, Schedule, HRIS (4 modules)
Phase 5 - Finance & Advanced | Week 27-38 ¦ Finance, SFA, Marketing (4 modules)
Phase 6 - Enterprise | Week 33-48 ¦ Fleet, TMS, MFG, Asset, PJM, EXIM, Integrations, Admin (16 modules)

## Task List (All)
# | Phase | Module | Platform | Task | Subtasks | Story Points | Priority | Start Week | End Week | Start Date | End Date | Duration (weeks) | Status | User Story
1 | Phase 1 - Foundation | M01 - Authentication & Authorization | Backend | Auth API - Register/Login/Logout | POST /api/auth/register POST /api/auth/login POST /api/auth/logout JWT token generation & refresh Password hashing (bcrypt) Email verification flow | 8 | High | 1 | 2 | 2025-04-01 | 2025-04-15 | 2 | To Do | Sebagai sistem, saya ingin auth api - register/login/logout agar dapat mengelola Authentication & Authorization secara efisien.
2 | Phase 1 - Foundation | M01 - Authentication & Authorization | Backend | Role & Permission System | Role model (super_admin, owner, admin, manager, staff, cashier, etc) Permission matrix CRUD Middleware auth guard Middleware role guard Middleware module access guard | 8 | High | 1 | 2 | 2025-04-01 | 2025-04-15 | 2 | To Do | Sebagai sistem, saya ingin role & permission system agar dapat mengelola Authentication & Authorization secara efisien.
3 | Phase 1 - Foundation | M01 - Authentication & Authorization | Backend | Multi-Tenant Isolation | Tenant model & migration Tenant middleware for data isolation Tenant-aware query scoping Tenant settings API | 5 | Medium | 2 | 3 | 2025-04-08 | 2025-04-22 | 2 | To Do | Sebagai sistem, saya ingin multi-tenant isolation agar dapat mengelola Authentication & Authorization secara efisien.
4 | Phase 1 - Foundation | M01 - Authentication & Authorization | Frontend | Login & Register Pages | Login page UI Register page UI Forgot password flow OTP verification UI Auth context/provider | 5 | Medium | 2 | 3 | 2025-04-08 | 2025-04-22 | 2 | To Do | Sebagai pengguna web, saya ingin login & register pages agar dapat mengelola Authentication & Authorization secara efisien.
5 | Phase 1 - Foundation | M01 - Authentication & Authorization | Frontend | Auth Guards & Layout | Protected route wrapper Role-based route guard Layout with sidebar (HQ/Branch/Admin) Sidebar config integration User profile dropdown | 5 | Medium | 3 | 4 | 2025-04-15 | 2025-04-29 | 2 | To Do | Sebagai pengguna web, saya ingin auth guards & layout agar dapat mengelola Authentication & Authorization secara efisien.
6 | Phase 1 - Foundation | M01 - Authentication & Authorization | Mobile | Mobile Auth Flow | Login screen Biometric auth (fingerprint/face) Token storage (secure) Auto-refresh token Push notification token registration | 5 | Medium | 4 | 5 | 2025-04-22 | 2025-05-06 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile auth flow agar dapat mengelola Authentication & Authorization secara efisien.
7 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Backend | Onboarding API | POST /api/onboarding/start Business type selection endpoint KYB document upload Tenant provisioning service Default data seeding (roles, modules) | 8 | High | 3 | 4 | 2025-04-15 | 2025-04-29 | 2 | To Do | Sebagai sistem, saya ingin onboarding api agar dapat mengelola Onboarding & Tenant Setup secara efisien.
8 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Backend | Subscription & Package API | Package model & CRUD Subscription lifecycle Module activation per package Trial period management | 5 | Medium | 4 | 5 | 2025-04-22 | 2025-05-06 | 2 | To Do | Sebagai sistem, saya ingin subscription & package api agar dapat mengelola Onboarding & Tenant Setup secara efisien.
9 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Frontend | Onboarding Wizard UI | Step 1: Business info form Step 2: Business type selection Step 3: KYB document upload Step 4: Branch setup Step 5: Admin user creation Progress indicator | 8 | High | 4 | 5 | 2025-04-22 | 2025-05-06 | 2 | To Do | Sebagai pengguna web, saya ingin onboarding wizard ui agar dapat mengelola Onboarding & Tenant Setup secara efisien.
10 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Mobile | Mobile Onboarding | Onboarding welcome screens Business setup wizard (mobile) Initial sync after setup | 3 | Low | 6 | 6 | 2025-05-06 | 2025-05-13 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile onboarding agar dapat mengelola Onboarding & Tenant Setup secara efisien.
11 | Phase 1 - Foundation | M03 - Branch Management | Backend | Branch CRUD API | GET/POST/PUT/DELETE /api/branches Branch model & migration Branch-module activation Branch user assignment Branch real-time metrics model | 8 | High | 4 | 5 | 2025-04-22 | 2025-05-06 | 2 | To Do | Sebagai sistem, saya ingin branch crud api agar dapat mengelola Branch Management secara efisien.
12 | Phase 1 - Foundation | M03 - Branch Management | Backend | Branch Performance API | Sales aggregation per branch Inventory status per branch Employee count & schedule Comparison analytics endpoint | 5 | Medium | 5 | 6 | 2025-04-29 | 2025-05-13 | 2 | To Do | Sebagai sistem, saya ingin branch performance api agar dapat mengelola Branch Management secara efisien.
13 | Phase 1 - Foundation | M03 - Branch Management | Frontend | Branch List & Detail Pages | Branch list with filters & search Branch detail page Branch creation form Branch settings page Branch performance dashboard | 8 | High | 5 | 6 | 2025-04-29 | 2025-05-13 | 2 | To Do | Sebagai pengguna web, saya ingin branch list & detail pages agar dapat mengelola Branch Management secara efisien.
14 | Phase 1 - Foundation | M03 - Branch Management | Frontend | Branch Performance Charts | Revenue comparison chart Top/bottom branch ranking Branch map view (Leaflet) Real-time metrics cards | 5 | Medium | 6 | 7 | 2025-05-06 | 2025-05-20 | 2 | To Do | Sebagai pengguna web, saya ingin branch performance charts agar dapat mengelola Branch Management secara efisien.
15 | Phase 1 - Foundation | M03 - Branch Management | Mobile | Branch Switcher (Mobile) | Branch selector dropdown Branch dashboard summary Quick branch performance view | 3 | Low | 7 | 7 | 2025-05-13 | 2025-05-20 | 1 | To Do | Sebagai pengguna mobile, saya ingin branch switcher (mobile) agar dapat mengelola Branch Management secara efisien.
16 | Phase 1 - Foundation | M04 - Settings & Configuration | Backend | Settings API | Store settings CRUD Tax & fee configuration Notification settings Module toggle endpoints Integration config endpoints | 5 | Medium | 6 | 7 | 2025-05-06 | 2025-05-20 | 2 | To Do | Sebagai sistem, saya ingin settings api agar dapat mengelola Settings & Configuration secara efisien.
17 | Phase 1 - Foundation | M04 - Settings & Configuration | Frontend | Settings Pages | Global settings page Module management page Tax & fee settings Notification preferences Integration settings page | 5 | Medium | 7 | 8 | 2025-05-13 | 2025-05-27 | 2 | To Do | Sebagai pengguna web, saya ingin settings pages agar dapat mengelola Settings & Configuration secara efisien.
18 | Phase 1 - Foundation | M04 - Settings & Configuration | Mobile | Mobile Settings | App preferences screen Notification toggle Printer/device settings | 3 | Low | 8 | 8 | 2025-05-20 | 2025-05-27 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile settings agar dapat mengelola Settings & Configuration secara efisien.
19 | Phase 2 - Core Commerce | M05 - Product & Category Management | Backend | Product CRUD API | Product model & migration GET/POST/PUT/DELETE /api/products Product variant support Image upload (multer) Barcode generation Bulk import/export CSV | 8 | High | 8 | 9 | 2025-05-20 | 2025-06-03 | 2 | To Do | Sebagai sistem, saya ingin product crud api agar dapat mengelola Product & Category Management secara efisien.
20 | Phase 2 - Core Commerce | M05 - Product & Category Management | Backend | Category & Pricing API | Category hierarchy CRUD Price tier model Multi-branch pricing logic Product cost component tracking HPP (Cost of Goods) calculation | 8 | High | 9 | 10 | 2025-05-27 | 2025-06-10 | 2 | To Do | Sebagai sistem, saya ingin category & pricing api agar dapat mengelola Product & Category Management secara efisien.
21 | Phase 2 - Core Commerce | M05 - Product & Category Management | Frontend | Product Management Pages | Product list with grid/list view Product create/edit form Variant builder UI Image upload with crop Barcode scanner integration Bulk import UI | 8 | High | 9 | 10 | 2025-05-27 | 2025-06-10 | 2 | To Do | Sebagai pengguna web, saya ingin product management pages agar dapat mengelola Product & Category Management secara efisien.
22 | Phase 2 - Core Commerce | M05 - Product & Category Management | Frontend | Category & Pricing Pages | Category tree view Drag-drop category reorder Price tier management Branch-specific pricing UI | 5 | Medium | 10 | 11 | 2025-06-03 | 2025-06-17 | 2 | To Do | Sebagai pengguna web, saya ingin category & pricing pages agar dapat mengelola Product & Category Management secara efisien.
23 | Phase 2 - Core Commerce | M05 - Product & Category Management | Mobile | Mobile Product Catalog | Product list & search Product detail view Barcode scan to find product Quick price check | 5 | Medium | 11 | 12 | 2025-06-10 | 2025-06-24 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile product catalog agar dapat mengelola Product & Category Management secara efisien.
24 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Backend | POS Transaction API | POST /api/pos/transactions Transaction model & items Payment processing (cash, card, QRIS, e-wallet) Split payment logic Void & refund endpoints Transaction search & filter | 13 | Critical | 10 | 12 | 2025-06-03 | 2025-06-24 | 3 | To Do | Sebagai sistem, saya ingin pos transaction api agar dapat mengelola Point of Sale (POS) secara efisien.
25 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Backend | Shift & Cash Management API | Open/close shift endpoints Cash drawer tracking Shift handover report Held transaction CRUD Daily sales summary | 8 | High | 11 | 12 | 2025-06-10 | 2025-06-24 | 2 | To Do | Sebagai sistem, saya ingin shift & cash management api agar dapat mengelola Point of Sale (POS) secara efisien.
26 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Backend | Receipt & Printer API | Receipt template engine Thermal printer config Digital receipt (email/WA) Receipt reprint endpoint | 5 | Medium | 12 | 12 | 2025-06-17 | 2025-06-24 | 1 | To Do | Sebagai sistem, saya ingin receipt & printer api agar dapat mengelola Point of Sale (POS) secara efisien.
27 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Frontend | POS Cashier Interface | POS main screen layout Product grid with categories Cart management Quantity & discount controls Customer selection Barcode scanner input Payment modal (multi-method) Split bill UI Receipt preview & print | 13 | Critical | 11 | 13 | 2025-06-10 | 2025-07-01 | 3 | To Do | Sebagai pengguna web, saya ingin pos cashier interface agar dapat mengelola Point of Sale (POS) secara efisien.
28 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Frontend | Shift & Transaction History | Shift open/close dialogs Cash count form Shift summary report Transaction history list Transaction detail & reprint Held transactions list | 8 | High | 13 | 14 | 2025-06-24 | 2025-07-08 | 2 | To Do | Sebagai pengguna web, saya ingin shift & transaction history agar dapat mengelola Point of Sale (POS) secara efisien.
29 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Mobile | Mobile POS | Mobile POS interface Product search & scan Cart management Payment processing Bluetooth printer integration Offline transaction queue Sync when online | 13 | Critical | 13 | 15 | 2025-06-24 | 2025-07-15 | 3 | To Do | Sebagai pengguna mobile, saya ingin mobile pos agar dapat mengelola Point of Sale (POS) secara efisien.
30 | Phase 2 - Core Commerce | M07 - Inventory Management | Backend | Stock & Warehouse API | Stock model per branch/warehouse Stock movement logging GET /api/inventory/stock Stock adjustment endpoints Warehouse CRUD Stock transfer between branches | 13 | Critical | 11 | 13 | 2025-06-10 | 2025-07-01 | 3 | To Do | Sebagai sistem, saya ingin stock & warehouse api agar dapat mengelola Inventory Management secara efisien.
31 | Phase 2 - Core Commerce | M07 - Inventory Management | Backend | Stock Opname API | Stock opname session CRUD Opname item recording Variance calculation Approval workflow Opname history & reports | 8 | High | 13 | 14 | 2025-06-24 | 2025-07-08 | 2 | To Do | Sebagai sistem, saya ingin stock opname api agar dapat mengelola Inventory Management secara efisien.
32 | Phase 2 - Core Commerce | M07 - Inventory Management | Backend | Alerts & Reorder API | Low stock threshold config Alert generation service Reorder point notification Stock expiry tracking Batch/lot number tracking | 5 | Medium | 14 | 15 | 2025-07-01 | 2025-07-15 | 2 | To Do | Sebagai sistem, saya ingin alerts & reorder api agar dapat mengelola Inventory Management secara efisien.
33 | Phase 2 - Core Commerce | M07 - Inventory Management | Frontend | Inventory Dashboard & Stock Pages | Inventory dashboard with KPIs Stock list with filters Stock detail & movement history Stock adjustment form Transfer request form Multi-warehouse view | 8 | High | 12 | 14 | 2025-06-17 | 2025-07-08 | 3 | To Do | Sebagai pengguna web, saya ingin inventory dashboard & stock pages agar dapat mengelola Inventory Management secara efisien.
34 | Phase 2 - Core Commerce | M07 - Inventory Management | Frontend | Stock Opname UI | Start opname wizard Item count entry (manual + scan) Variance review screen Approval flow UI Opname history page | 8 | High | 14 | 15 | 2025-07-01 | 2025-07-15 | 2 | To Do | Sebagai pengguna web, saya ingin stock opname ui agar dapat mengelola Inventory Management secara efisien.
35 | Phase 2 - Core Commerce | M07 - Inventory Management | Mobile | Mobile Stock Management | Stock check by scan Mobile stock opname Stock transfer request Low stock alert push notification Stock receive confirmation | 8 | High | 15 | 16 | 2025-07-08 | 2025-07-22 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile stock management agar dapat mengelola Inventory Management secara efisien.
36 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Backend | Purchase Order API | PO model & items PO CRUD endpoints PO approval workflow PO status tracking Auto-PO from reorder point | 8 | High | 14 | 15 | 2025-07-01 | 2025-07-15 | 2 | To Do | Sebagai sistem, saya ingin purchase order api agar dapat mengelola Purchase Orders & Suppliers secara efisien.
37 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Backend | Supplier & Goods Receipt API | Supplier CRUD Goods receipt recording Partial receipt handling Receipt-to-stock integration Supplier performance metrics | 5 | Medium | 15 | 16 | 2025-07-08 | 2025-07-22 | 2 | To Do | Sebagai sistem, saya ingin supplier & goods receipt api agar dapat mengelola Purchase Orders & Suppliers secara efisien.
38 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Frontend | Purchase Order Pages | PO list & filter PO creation wizard PO approval screen PO detail & status timeline Supplier list & form Goods receipt form | 8 | High | 15 | 16 | 2025-07-08 | 2025-07-22 | 2 | To Do | Sebagai pengguna web, saya ingin purchase order pages agar dapat mengelola Purchase Orders & Suppliers secara efisien.
39 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Mobile | Mobile Goods Receipt | Scan PO barcode to receive Item count confirmation Photo proof of delivery Receipt signature capture | 5 | Medium | 17 | 17 | 2025-07-22 | 2025-07-29 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile goods receipt agar dapat mengelola Purchase Orders & Suppliers secara efisien.
40 | Phase 3 - Customer & Engagement | M09 - Customer Management | Backend | Customer CRUD API | Customer model & migration GET/POST/PUT/DELETE endpoints Customer search & filter Customer import/export Customer segmentation logic Corporate customer support | 8 | High | 16 | 17 | 2025-07-15 | 2025-07-29 | 2 | To Do | Sebagai sistem, saya ingin customer crud api agar dapat mengelola Customer Management secara efisien.
41 | Phase 3 - Customer & Engagement | M09 - Customer Management | Frontend | Customer Management Pages | Customer list with search Customer detail 360 view Add customer wizard Customer edit form Transaction history per customer Customer segmentation UI Corporate customer form | 8 | High | 16 | 17 | 2025-07-15 | 2025-07-29 | 2 | To Do | Sebagai pengguna web, saya ingin customer management pages agar dapat mengelola Customer Management secara efisien.
42 | Phase 3 - Customer & Engagement | M09 - Customer Management | Mobile | Mobile Customer Lookup | Customer search Quick add customer Customer card view Link customer to POS transaction | 3 | Low | 18 | 18 | 2025-07-29 | 2025-08-05 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile customer lookup agar dapat mengelola Customer Management secara efisien.
43 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Backend | Loyalty Program API | LoyaltyProgram model Point transaction recording Tier calculation engine Reward catalog CRUD Redemption processing Point expiry service | 8 | High | 18 | 19 | 2025-07-29 | 2025-08-12 | 2 | To Do | Sebagai sistem, saya ingin loyalty program api agar dapat mengelola Loyalty Program secara efisien.
44 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Frontend | Loyalty Program Pages | Loyalty dashboard Program configuration Tier management Reward catalog editor Redemption history Member analytics | 8 | High | 18 | 19 | 2025-07-29 | 2025-08-12 | 2 | To Do | Sebagai pengguna web, saya ingin loyalty program pages agar dapat mengelola Loyalty Program secara efisien.
45 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Mobile | Mobile Loyalty | Loyalty card view Point balance & history Available rewards Redeem from mobile Digital membership card | 5 | Medium | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile loyalty agar dapat mengelola Loyalty Program secara efisien.
46 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Backend | Promo & Voucher API | Promo model & rules engine Bundle deal logic Voucher generation (unique codes) Voucher validation & redemption Promo scheduling Category/product-specific promos | 8 | High | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai sistem, saya ingin promo & voucher api agar dapat mengelola Promo & Voucher secara efisien.
47 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Frontend | Promo & Voucher Pages | Promo list & creation wizard Bundle builder UI Voucher generator page Promo analytics dashboard Promo calendar view | 8 | High | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai pengguna web, saya ingin promo & voucher pages agar dapat mengelola Promo & Voucher secara efisien.
48 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Mobile | Mobile Promo Display | Active promo list Voucher scanner at POS Apply promo in cart Push notification for new promos | 3 | Low | 22 | 22 | 2025-08-26 | 2025-09-02 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile promo display agar dapat mengelola Promo & Voucher secara efisien.
49 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Backend | CRM Core API | CrmContact model CrmCommunication model CrmInteraction tracking CrmDocument management CrmCalendarEvent CRUD Customer 360 aggregation endpoint | 8 | High | 19 | 20 | 2025-08-05 | 2025-08-19 | 2 | To Do | Sebagai sistem, saya ingin crm core api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
50 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Backend | CRM Tickets & Automation API | CrmTicket CRUD SLA policy engine Ticket escalation logic CrmAutomationRule engine Trigger-based actions CrmFollowUp scheduler | 8 | High | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai sistem, saya ingin crm tickets & automation api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
51 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Backend | CRM Forecasting API | CrmForecast model Pipeline value calculation Win probability scoring CrmDealScore model Forecast vs actual comparison | 5 | Medium | 21 | 22 | 2025-08-19 | 2025-09-02 | 2 | To Do | Sebagai sistem, saya ingin crm forecasting api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
52 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Frontend | CRM Dashboard & Contact Pages | CRM dashboard with pipeline Contact list & 360 view Communication timeline Calendar & task integration Document management UI | 8 | High | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai pengguna web, saya ingin crm dashboard & contact pages agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
53 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Frontend | CRM Tickets & Automation UI | Ticket list & kanban board Ticket detail & comments SLA configuration page Automation rule builder Follow-up scheduler | 8 | High | 21 | 22 | 2025-08-19 | 2025-09-02 | 2 | To Do | Sebagai pengguna web, saya ingin crm tickets & automation ui agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
54 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Mobile | Mobile CRM | Contact list & search Quick log interaction Ticket view & update Follow-up reminders (push) | 5 | Medium | 22 | 23 | 2025-08-26 | 2025-09-09 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile crm agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
55 | Phase 4 - Operations | M13 - Kitchen Management | Backend | Kitchen Order API | KitchenOrder model Order queue management Order status updates (new/preparing/ready/served) KDS integration endpoint Order priority logic | 8 | High | 20 | 21 | 2025-08-12 | 2025-08-26 | 2 | To Do | Sebagai sistem, saya ingin kitchen order api agar dapat mengelola Kitchen Management secara efisien.
56 | Phase 4 - Operations | M13 - Kitchen Management | Backend | Recipe & Kitchen Inventory API | Recipe CRUD with ingredients Auto-deduct stock on order Kitchen inventory tracking Production waste recording Recipe costing calculation | 8 | High | 21 | 22 | 2025-08-19 | 2025-09-02 | 2 | To Do | Sebagai sistem, saya ingin recipe & kitchen inventory api agar dapat mengelola Kitchen Management secara efisien.
57 | Phase 4 - Operations | M13 - Kitchen Management | Frontend | Kitchen Display System (KDS) | KDS board layout Order cards with timers Status update buttons Sound/visual alerts Multi-station view | 8 | High | 21 | 22 | 2025-08-19 | 2025-09-02 | 2 | To Do | Sebagai pengguna web, saya ingin kitchen display system (kds) agar dapat mengelola Kitchen Management secara efisien.
58 | Phase 4 - Operations | M13 - Kitchen Management | Frontend | Recipe & Kitchen Settings | Recipe editor Ingredient mapping Kitchen inventory page Kitchen staff assignment Kitchen settings | 5 | Medium | 22 | 23 | 2025-08-26 | 2025-09-09 | 2 | To Do | Sebagai pengguna web, saya ingin recipe & kitchen settings agar dapat mengelola Kitchen Management secara efisien.
59 | Phase 4 - Operations | M13 - Kitchen Management | Mobile | Mobile KDS | Mobile kitchen display Order status quick update Alert on new orders | 3 | Low | 23 | 23 | 2025-09-02 | 2025-09-09 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile kds agar dapat mengelola Kitchen Management secara efisien.
60 | Phase 4 - Operations | M14 - Table & Reservation Management | Backend | Table & Session API | Table model CRUD Table session management Table status tracking Merge/split table Table-POS transaction linking | 5 | Medium | 22 | 23 | 2025-08-26 | 2025-09-09 | 2 | To Do | Sebagai sistem, saya ingin table & session api agar dapat mengelola Table & Reservation Management secara efisien.
61 | Phase 4 - Operations | M14 - Table & Reservation Management | Backend | Reservation API | Reservation CRUD Availability check Confirmation & reminder Walk-in vs reserved Cancellation policy | 5 | Medium | 23 | 24 | 2025-09-02 | 2025-09-16 | 2 | To Do | Sebagai sistem, saya ingin reservation api agar dapat mengelola Table & Reservation Management secara efisien.
62 | Phase 4 - Operations | M14 - Table & Reservation Management | Frontend | Table Layout & Reservation UI | Drag-drop table layout editor Real-time table status map Table session view Reservation calendar Reservation create/edit form Waitlist management | 8 | High | 23 | 24 | 2025-09-02 | 2025-09-16 | 2 | To Do | Sebagai pengguna web, saya ingin table layout & reservation ui agar dapat mengelola Table & Reservation Management secara efisien.
63 | Phase 4 - Operations | M14 - Table & Reservation Management | Mobile | Mobile Table/Reservation | Table status overview Quick seat assignment Reservation lookup | 3 | Low | 25 | 25 | 2025-09-16 | 2025-09-23 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile table/reservation agar dapat mengelola Table & Reservation Management secara efisien.
64 | Phase 4 - Operations | M15 - Employee & Schedule Management | Backend | Schedule & Shift API | Shift model & templates Schedule CRUD Shift assignment engine Shift handover recording Schedule conflict detection | 5 | Medium | 23 | 24 | 2025-09-02 | 2025-09-16 | 2 | To Do | Sebagai sistem, saya ingin schedule & shift api agar dapat mengelola Employee & Schedule Management secara efisien.
65 | Phase 4 - Operations | M15 - Employee & Schedule Management | Frontend | Schedule & Shift Pages | Schedule calendar view (FullCalendar) Shift template builder Drag-drop shift assignment Shift handover form Schedule print/export | 8 | High | 23 | 24 | 2025-09-02 | 2025-09-16 | 2 | To Do | Sebagai pengguna web, saya ingin schedule & shift pages agar dapat mengelola Employee & Schedule Management secara efisien.
66 | Phase 4 - Operations | M15 - Employee & Schedule Management | Mobile | Mobile Schedule View | My schedule view Shift swap request Clock in/out Handover checklist | 5 | Medium | 25 | 26 | 2025-09-16 | 2025-09-30 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile schedule view agar dapat mengelola Employee & Schedule Management secara efisien.
67 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Backend | Employee Database API | Employee model (comprehensive) Employee documents Employee family data Employee education & skills Employee work experience Organization structure Job grade system | 8 | High | 24 | 25 | 2025-09-09 | 2025-09-23 | 2 | To Do | Sebagai sistem, saya ingin employee database api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
68 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Backend | Attendance & Devices API | AttendanceDevice model Device log ingestion Attendance calculation Overtime calculation AttendanceSettings per branch Fingerprint/face device integration | 8 | High | 25 | 26 | 2025-09-16 | 2025-09-30 | 2 | To Do | Sebagai sistem, saya ingin attendance & devices api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
69 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Backend | Payroll API | PayrollComponent model Salary structure Payroll run processing Tax calculation (PPh21) Payslip generation Bank file export | 13 | Critical | 26 | 28 | 2025-09-23 | 2025-10-14 | 3 | To Do | Sebagai sistem, saya ingin payroll api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
70 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Backend | Leave & Performance API | LeaveType & balance model Leave request workflow Leave approval chain PerformanceReview model KPI template & scoring 360 feedback system | 8 | High | 27 | 28 | 2025-09-30 | 2025-10-14 | 2 | To Do | Sebagai sistem, saya ingin leave & performance api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
71 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Backend | Recruitment & Training API | Job posting CRUD Candidate tracking Interview scheduling Training program model Certification tracking Employee mutation/transfer | 5 | Medium | 28 | 29 | 2025-10-07 | 2025-10-21 | 2 | To Do | Sebagai sistem, saya ingin recruitment & training api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
72 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Frontend | HRIS Dashboard & Employee Pages | HRIS dashboard Employee list & detail Employee create/edit wizard Organization chart Document management Employee lifecycle timeline | 8 | High | 25 | 26 | 2025-09-16 | 2025-09-30 | 2 | To Do | Sebagai pengguna web, saya ingin hris dashboard & employee pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
73 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Frontend | Attendance & Payroll Pages | Attendance dashboard Daily attendance log Device management page Payroll run wizard Payslip viewer Salary structure editor | 8 | High | 27 | 28 | 2025-09-30 | 2025-10-14 | 2 | To Do | Sebagai pengguna web, saya ingin attendance & payroll pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
74 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Frontend | Leave, KPI & Recruitment Pages | Leave calendar & balance Leave request form Leave approval list KPI dashboard KPI scoring form Performance review form Recruitment pipeline board Training catalog | 8 | High | 28 | 29 | 2025-10-07 | 2025-10-21 | 2 | To Do | Sebagai pengguna web, saya ingin leave, kpi & recruitment pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
75 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Mobile | Mobile HRIS (ESS) | My profile view Clock in/out with GPS Leave request from mobile Payslip viewer KPI & goals view Training schedule Claim submission Travel request | 8 | High | 29 | 30 | 2025-10-14 | 2025-10-28 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile hris (ess) agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
76 | Phase 5 - Finance & Advanced | M17 - Finance Lite | Backend | Finance Lite API | FinanceTransaction model Daily income aggregation Basic expense recording Daily/weekly/monthly summary Export to Excel/PDF | 5 | Medium | 28 | 29 | 2025-10-07 | 2025-10-21 | 2 | To Do | Sebagai sistem, saya ingin finance lite api agar dapat mengelola Finance Lite secara efisien.
77 | Phase 5 - Finance & Advanced | M17 - Finance Lite | Frontend | Finance Lite Pages | Transaction list Daily summary dashboard Simple income/expense chart Export buttons | 5 | Medium | 28 | 29 | 2025-10-07 | 2025-10-21 | 2 | To Do | Sebagai pengguna web, saya ingin finance lite pages agar dapat mengelola Finance Lite secara efisien.
78 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Backend | Chart of Accounts & GL API | FinanceAccount model (CoA) Journal entry recording General ledger queries Trial balance calculation Balance sheet generation Income statement (P&L) | 13 | Critical | 29 | 31 | 2025-10-14 | 2025-11-04 | 3 | To Do | Sebagai sistem, saya ingin chart of accounts & gl api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
79 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Backend | Invoice & AP/AR API | Invoice model & items Invoice generation from POS AR tracking & aging AP tracking & aging Payment recording Invoice email sending | 8 | High | 31 | 32 | 2025-10-28 | 2025-11-11 | 2 | To Do | Sebagai sistem, saya ingin invoice & ap/ar api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
80 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Backend | Budget & Cash Flow API | Budget model per department Budget vs actual tracking Cash flow projection Cash flow report Tax calculation service Tax report generation | 8 | High | 32 | 33 | 2025-11-04 | 2025-11-18 | 2 | To Do | Sebagai sistem, saya ingin budget & cash flow api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
81 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Frontend | Finance Dashboard & GL Pages | Finance dashboard with KPIs Chart of Accounts page Journal entry form General ledger view Trial balance report P&L report Balance sheet report | 13 | Critical | 30 | 32 | 2025-10-21 | 2025-11-11 | 3 | To Do | Sebagai pengguna web, saya ingin finance dashboard & gl pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
82 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Frontend | Invoice & AP/AR Pages | Invoice list & detail Invoice creation form AR aging report AP aging report Payment recording form Invoice PDF preview | 8 | High | 32 | 33 | 2025-11-04 | 2025-11-18 | 2 | To Do | Sebagai pengguna web, saya ingin invoice & ap/ar pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
83 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Frontend | Budget & Tax Pages | Budget planning page Budget vs actual chart Cash flow report Tax summary page Financial ratio analysis | 5 | Medium | 33 | 34 | 2025-11-11 | 2025-11-25 | 2 | To Do | Sebagai pengguna web, saya ingin budget & tax pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
84 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Mobile | Mobile Finance | Daily revenue summary Expense quick entry Invoice approval Cash flow overview | 3 | Low | 34 | 34 | 2025-11-18 | 2025-11-25 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile finance agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
85 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | Backend | SFA Core API | SfaTeam & territory model SfaVisit with GPS check-in SfaLead & opportunity pipeline SfaFieldOrder CRUD SfaQuotation CRUD Coverage plan & assignment | 13 | Critical | 31 | 33 | 2025-10-28 | 2025-11-18 | 3 | To Do | Sebagai sistem, saya ingin sfa core api agar dapat mengelola SFA (Sales Force Automation) secara efisien.
86 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | Backend | SFA Target & Incentive API | SfaTarget & assignment model Achievement tracking Incentive scheme engine Commission calculation SfaPlafon (credit limit) Approval workflow | 8 | High | 33 | 34 | 2025-11-11 | 2025-11-25 | 2 | To Do | Sebagai sistem, saya ingin sfa target & incentive api agar dapat mengelola SFA (Sales Force Automation) secara efisien.
87 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | Frontend | SFA Dashboard & Pages | SFA dashboard Visit map & list Lead/opportunity pipeline (kanban) Field order management Quotation builder Team & territory management Target setting & tracking Incentive calculation view Survey & competitor activity | 13 | Critical | 32 | 34 | 2025-11-04 | 2025-11-25 | 3 | To Do | Sebagai pengguna web, saya ingin sfa dashboard & pages agar dapat mengelola SFA (Sales Force Automation) secara efisien.
88 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | Mobile | Mobile SFA | GPS check-in for visits Photo proof upload Quick field order entry Route plan view Target & achievement dashboard Customer visit history Offline mode with sync | 13 | Critical | 34 | 36 | 2025-11-18 | 2025-12-09 | 3 | To Do | Sebagai pengguna mobile, saya ingin mobile sfa agar dapat mengelola SFA (Sales Force Automation) secara efisien.
89 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Backend | Marketing API | MktCampaign CRUD MktCampaignChannel tracking MktSegment & rules engine MktPromotion model MktBudget tracking Campaign performance analytics | 8 | High | 34 | 35 | 2025-11-18 | 2025-12-02 | 2 | To Do | Sebagai sistem, saya ingin marketing api agar dapat mengelola Marketing & Campaigns secara efisien.
90 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Frontend | Marketing Pages | Marketing dashboard Campaign builder wizard Segment builder (rules-based) Promotion management Budget allocation & tracking Campaign analytics charts | 8 | High | 34 | 35 | 2025-11-18 | 2025-12-02 | 2 | To Do | Sebagai pengguna web, saya ingin marketing pages agar dapat mengelola Marketing & Campaigns secara efisien.
91 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Mobile | Mobile Marketing | Campaign overview Quick promotion setup Push notification to customers | 3 | Low | 36 | 36 | 2025-12-02 | 2025-12-09 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile marketing agar dapat mengelola Marketing & Campaigns secara efisien.
92 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Backend | Fleet Core API | FleetVehicle CRUD FleetDriver CRUD GPS location ingestion Geofence model & check Maintenance schedule engine Fuel transaction recording Inspection & incident models | 13 | Critical | 34 | 36 | 2025-11-18 | 2025-12-09 | 3 | To Do | Sebagai sistem, saya ingin fleet core api agar dapat mengelola Fleet Management (FMS) secara efisien.
93 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Frontend | Fleet Dashboard & Pages | Fleet dashboard Vehicle list & detail Driver list & assignment GPS live map (Leaflet) Geofence editor Maintenance calendar Fuel log & analytics Inspection forms Incident reports Cost analytics | 13 | Critical | 35 | 37 | 2025-11-25 | 2025-12-16 | 3 | To Do | Sebagai pengguna web, saya ingin fleet dashboard & pages agar dapat mengelola Fleet Management (FMS) secara efisien.
94 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Mobile | Mobile Fleet (Driver App) | Driver check-in/out GPS tracking background service Fuel entry form Vehicle inspection checklist Incident report with photos Route navigation | 8 | High | 37 | 38 | 2025-12-09 | 2025-12-23 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile fleet (driver app) agar dapat mengelola Fleet Management (FMS) secara efisien.
95 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | Backend | TMS API | Shipment CRUD Dispatch & assignment Tracking status updates Carrier model & scoring Route optimization Rate card management Zone & warehouse mapping Billing integration SLA monitoring | 13 | Critical | 36 | 38 | 2025-12-02 | 2025-12-23 | 3 | To Do | Sebagai sistem, saya ingin tms api agar dapat mengelola Transportation Management (TMS) secara efisien.
96 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | Frontend | TMS Dashboard & Pages | TMS dashboard Shipment list & tracking Dispatch board Carrier management Route planner Rate card editor Zone management SLA dashboard Logistics KPI analytics | 13 | Critical | 37 | 39 | 2025-12-09 | 2025-12-30 | 3 | To Do | Sebagai pengguna web, saya ingin tms dashboard & pages agar dapat mengelola Transportation Management (TMS) secara efisien.
97 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | Mobile | Mobile TMS (Driver) | Delivery task list GPS tracking & proof of delivery Signature capture Photo upload Status updates | 5 | Medium | 39 | 40 | 2025-12-23 | 2026-01-06 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile tms (driver) agar dapat mengelola Transportation Management (TMS) secara efisien.
98 | Phase 6 - Enterprise | M23 - Manufacturing | Backend | Manufacturing API | MfgWorkOrder CRUD MfgBom & BomItem MfgRouting & operations MfgWorkCenter & Machine MfgQcTemplate & inspection MfgProductionPlan MfgProductionCost MfgWasteRecord MfgShiftProduction Subcontracting model COGM calculation | 13 | Critical | 37 | 39 | 2025-12-09 | 2025-12-30 | 3 | To Do | Sebagai sistem, saya ingin manufacturing api agar dapat mengelola Manufacturing secara efisien.
99 | Phase 6 - Enterprise | M23 - Manufacturing | Frontend | Manufacturing Pages | Manufacturing dashboard Work order list & detail BOM builder Routing editor Work center management Machine registry & maintenance QC inspection forms Production planning calendar OEE analytics dashboard Cost analysis Waste tracking PLM (Product Lifecycle) | 13 | Critical | 38 | 40 | 2025-12-16 | 2026-01-06 | 3 | To Do | Sebagai pengguna web, saya ingin manufacturing pages agar dapat mengelola Manufacturing secara efisien.
100 | Phase 6 - Enterprise | M23 - Manufacturing | Mobile | Mobile Manufacturing | Work order task view QC inspection mobile form Production count entry Machine status update Waste recording | 5 | Medium | 40 | 41 | 2025-12-30 | 2026-01-13 | 2 | To Do | Sebagai pengguna mobile, saya ingin mobile manufacturing agar dapat mengelola Manufacturing secara efisien.
101 | Phase 6 - Enterprise | M24 - Asset Management | Backend | Asset Management API | Asset CRUD AssetCategory model Depreciation calculation (SL/DB/SYD) AssetMovement tracking AssetMaintenanceSchedule AssetWorkOrder AssetLicense tracking AssetTenancy (rental) Alert generation | 8 | High | 39 | 40 | 2025-12-23 | 2026-01-06 | 2 | To Do | Sebagai sistem, saya ingin asset management api agar dapat mengelola Asset Management secara efisien.
102 | Phase 6 - Enterprise | M24 - Asset Management | Frontend | Asset Management Pages | Asset dashboard Asset registry list Asset detail & history Depreciation report Maintenance calendar Work order management License tracking page Asset movement log Settings & categories | 8 | High | 40 | 41 | 2025-12-30 | 2026-01-13 | 2 | To Do | Sebagai pengguna web, saya ingin asset management pages agar dapat mengelola Asset Management secara efisien.
103 | Phase 6 - Enterprise | M24 - Asset Management | Mobile | Mobile Asset | Asset scan (barcode/QR) Asset inspection form Maintenance request Asset transfer request | 3 | Low | 41 | 41 | 2026-01-06 | 2026-01-13 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile asset agar dapat mengelola Asset Management secara efisien.
104 | Phase 6 - Enterprise | M25 - Project Management | Backend | Project Management API | PjmProject CRUD PjmTask CRUD PjmMilestone model PjmTimesheet recording PjmResource allocation PjmRisk model PjmBudget tracking PjmDocument management | 8 | High | 40 | 41 | 2025-12-30 | 2026-01-13 | 2 | To Do | Sebagai sistem, saya ingin project management api agar dapat mengelola Project Management secara efisien.
105 | Phase 6 - Enterprise | M25 - Project Management | Frontend | Project Management Pages | Project dashboard Project list & detail Task kanban board Gantt chart view Milestone timeline Timesheet entry & report Resource allocation view Risk register Budget tracking Document repository | 8 | High | 41 | 42 | 2026-01-06 | 2026-01-20 | 2 | To Do | Sebagai pengguna web, saya ingin project management pages agar dapat mengelola Project Management secara efisien.
106 | Phase 6 - Enterprise | M25 - Project Management | Mobile | Mobile Project | Task list & update Time logging Milestone notifications Document viewer | 3 | Low | 42 | 42 | 2026-01-13 | 2026-01-20 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile project agar dapat mengelola Project Management secara efisien.
107 | Phase 6 - Enterprise | M26 - E-Procurement | Backend | E-Procurement API | EprVendor CRUD EprProcurementRequest EprRfq & responses EprTender & bids EprContract lifecycle EprEvaluation scoring Approval workflows Analytics endpoints | 8 | High | 41 | 42 | 2026-01-06 | 2026-01-20 | 2 | To Do | Sebagai sistem, saya ingin e-procurement api agar dapat mengelola E-Procurement secara efisien.
108 | Phase 6 - Enterprise | M26 - E-Procurement | Frontend | E-Procurement Pages | E-Procurement dashboard Vendor registry Procurement request form RFQ builder & comparison Tender management Contract management Vendor evaluation scorecards Analytics & reports | 8 | High | 42 | 43 | 2026-01-13 | 2026-01-27 | 2 | To Do | Sebagai pengguna web, saya ingin e-procurement pages agar dapat mengelola E-Procurement secara efisien.
109 | Phase 6 - Enterprise | M26 - E-Procurement | Mobile | Mobile E-Procurement | Approval from mobile Vendor lookup RFQ review & compare | 3 | Low | 43 | 43 | 2026-01-20 | 2026-01-27 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile e-procurement agar dapat mengelola E-Procurement secara efisien.
110 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | Backend | EXIM API | EximShipment CRUD EximCustoms model EximLC (Letter of Credit) EximContainer tracking EximDocument management EximPartner CRUD EximCost recording EximHsCode reference Analytics endpoints | 8 | High | 42 | 43 | 2026-01-13 | 2026-01-27 | 2 | To Do | Sebagai sistem, saya ingin exim api agar dapat mengelola Export/Import (EXIM) secara efisien.
111 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | Frontend | EXIM Pages | EXIM dashboard Shipment list & detail Customs management L/C tracking Container tracking Document management Partner registry Cost analysis HS code search Analytics charts | 8 | High | 43 | 44 | 2026-01-20 | 2026-02-03 | 2 | To Do | Sebagai pengguna web, saya ingin exim pages agar dapat mengelola Export/Import (EXIM) secara efisien.
112 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | Mobile | Mobile EXIM | Shipment status tracker Document viewer Cost entry | 3 | Low | 44 | 44 | 2026-01-27 | 2026-02-03 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile exim agar dapat mengelola Export/Import (EXIM) secara efisien.
113 | Phase 6 - Enterprise | M28 - Reports & Analytics | Backend | Report Engine API | Report query builder Sales report aggregation Inventory report aggregation Finance report aggregation HR report aggregation Consolidated multi-branch report Export to Excel/PDF/CSV Scheduled report (cron) | 13 | Critical | 36 | 38 | 2025-12-02 | 2025-12-23 | 3 | To Do | Sebagai sistem, saya ingin report engine api agar dapat mengelola Reports & Analytics secara efisien.
114 | Phase 6 - Enterprise | M28 - Reports & Analytics | Frontend | Report Hub & Pages | Report hub dashboard Sales report page Inventory report page Finance report page Customer report page HR report page Procurement report page Custom data analysis tool Chart & pivot table builder Export & schedule UI | 13 | Critical | 37 | 39 | 2025-12-09 | 2025-12-30 | 3 | To Do | Sebagai pengguna web, saya ingin report hub & pages agar dapat mengelola Reports & Analytics secara efisien.
115 | Phase 6 - Enterprise | M28 - Reports & Analytics | Mobile | Mobile Reports | Key metric dashboard Quick report viewer Share report via mobile | 3 | Low | 39 | 39 | 2025-12-23 | 2025-12-30 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile reports agar dapat mengelola Reports & Analytics secara efisien.
116 | Phase 6 - Enterprise | M29 - WhatsApp Business Integration | Backend | WhatsApp API Integration | WA Business API connection Message template CRUD Broadcast service Auto-reply webhook handler Message log & analytics Rate limiting | 8 | High | 43 | 44 | 2026-01-20 | 2026-02-03 | 2 | To Do | Sebagai sistem, saya ingin whatsapp api integration agar dapat mengelola WhatsApp Business Integration secara efisien.
117 | Phase 6 - Enterprise | M29 - WhatsApp Business Integration | Frontend | WhatsApp Management Pages | WA dashboard Template editor Broadcast builder & scheduler Message analytics Settings & connection | 5 | Medium | 44 | 45 | 2026-01-27 | 2026-02-10 | 2 | To Do | Sebagai pengguna web, saya ingin whatsapp management pages agar dapat mengelola WhatsApp Business Integration secara efisien.
118 | Phase 6 - Enterprise | M30 - Marketplace Integration | Backend | Marketplace API Integration | Marketplace adapter pattern Tokopedia API integration Shopee API integration Product sync service Order sync service Stock sync service Webhook handlers Error retry queue | 13 | Critical | 44 | 46 | 2026-01-27 | 2026-02-17 | 3 | To Do | Sebagai sistem, saya ingin marketplace api integration agar dapat mengelola Marketplace Integration secara efisien.
119 | Phase 6 - Enterprise | M30 - Marketplace Integration | Frontend | Marketplace Pages | Marketplace dashboard Channel connection wizard Product mapping UI Order list (multi-channel) Stock sync status Settings & configuration | 8 | High | 45 | 46 | 2026-02-03 | 2026-02-17 | 2 | To Do | Sebagai pengguna web, saya ingin marketplace pages agar dapat mengelola Marketplace Integration secara efisien.
120 | Phase 6 - Enterprise | M31 - Website Builder | Backend | Website Builder API | Page model CRUD Component/section storage Theme configuration Publish/unpublish endpoint Custom domain mapping SEO metadata | 5 | Medium | 45 | 46 | 2026-02-03 | 2026-02-17 | 2 | To Do | Sebagai sistem, saya ingin website builder api agar dapat mengelola Website Builder secara efisien.
121 | Phase 6 - Enterprise | M31 - Website Builder | Frontend | Website Builder Editor | Drag-drop page editor Component palette Theme customizer Preview mode Publish flow Page list management | 8 | High | 45 | 47 | 2026-02-03 | 2026-02-24 | 3 | To Do | Sebagai pengguna web, saya ingin website builder editor agar dapat mengelola Website Builder secara efisien.
122 | Phase 6 - Enterprise | M32 - Knowledge Base | Backend | Knowledge Base API | Article model CRUD Category organization Full-text search Article versioning Access control | 3 | Low | 46 | 46 | 2026-02-10 | 2026-02-17 | 1 | To Do | Sebagai sistem, saya ingin knowledge base api agar dapat mengelola Knowledge Base secara efisien.
123 | Phase 6 - Enterprise | M32 - Knowledge Base | Frontend | Knowledge Base Pages | Article list & search Article editor (rich text) Category navigation Version history | 3 | Low | 46 | 46 | 2026-02-10 | 2026-02-17 | 1 | To Do | Sebagai pengguna web, saya ingin knowledge base pages agar dapat mengelola Knowledge Base secara efisien.
124 | Phase 6 - Enterprise | M33 - Billing & Subscription (SaaS) | Backend | Billing API | SubscriptionPackage CRUD Subscription model & lifecycle BillingCycle tracking Invoice auto-generation Payment gateway integration (Stripe/Midtrans) Webhook payment confirmation Usage-based billing Downgrade/upgrade logic | 8 | High | 45 | 46 | 2026-02-03 | 2026-02-17 | 2 | To Do | Sebagai sistem, saya ingin billing api agar dapat mengelola Billing & Subscription (SaaS) secara efisien.
125 | Phase 6 - Enterprise | M33 - Billing & Subscription (SaaS) | Frontend | Billing Pages | Pricing page Subscription management Invoice list & detail Payment history Upgrade/downgrade flow Usage analytics | 5 | Medium | 46 | 47 | 2026-02-10 | 2026-02-24 | 2 | To Do | Sebagai pengguna web, saya ingin billing pages agar dapat mengelola Billing & Subscription (SaaS) secara efisien.
126 | Phase 6 - Enterprise | M34 - Admin Panel (Super Admin) | Backend | Admin API | Tenant list & management Module activation/deactivation System user management Audit log queries Business type CRUD System health endpoints Backup management | 8 | High | 46 | 47 | 2026-02-10 | 2026-02-24 | 2 | To Do | Sebagai sistem, saya ingin admin api agar dapat mengelola Admin Panel (Super Admin) secara efisien.
127 | Phase 6 - Enterprise | M34 - Admin Panel (Super Admin) | Frontend | Admin Panel Pages | Admin dashboard Tenant list & detail Module management User management System log viewer Business type config System settings | 8 | High | 47 | 48 | 2026-02-17 | 2026-03-03 | 2 | To Do | Sebagai pengguna web, saya ingin admin panel pages agar dapat mengelola Admin Panel (Super Admin) secara efisien.
128 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Backend | Notification Service | Notification model WebSocket/SSE real-time delivery Push notification (FCM) Email notification (Nodemailer) Alert subscription model Alert trigger engine Notification preferences | 8 | High | 47 | 48 | 2026-02-17 | 2026-03-03 | 2 | To Do | Sebagai sistem, saya ingin notification service agar dapat mengelola Notifications & Alerts secara efisien.
129 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Frontend | Notification UI | Notification bell & dropdown Notification center page Alert subscription settings Real-time toast notifications | 3 | Low | 48 | 48 | 2026-02-24 | 2026-03-03 | 1 | To Do | Sebagai pengguna web, saya ingin notification ui agar dapat mengelola Notifications & Alerts secara efisien.
130 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Mobile | Mobile Notifications | Push notification handler Notification list screen Deep linking from notification Badge count management | 3 | Low | 48 | 48 | 2026-02-24 | 2026-03-03 | 1 | To Do | Sebagai pengguna mobile, saya ingin mobile notifications agar dapat mengelola Notifications & Alerts secara efisien.
131 | Phase 6 - Enterprise | M36 - Audit & Security | Backend | Audit & Security Services | AuditLog model Audit middleware (auto-log all mutations) IP tracking Rate limiting middleware CORS configuration Security headers (helmet) Data encryption at rest API key management | 5 | Medium | 47 | 48 | 2026-02-17 | 2026-03-03 | 2 | To Do | Sebagai sistem, saya ingin audit & security services agar dapat mengelola Audit & Security secara efisien.
132 | Phase 6 - Enterprise | M36 - Audit & Security | Frontend | Audit Log Page | Audit log viewer with filters User activity timeline Export audit data | 3 | Low | 48 | 48 | 2026-02-24 | 2026-03-03 | 1 | To Do | Sebagai pengguna web, saya ingin audit log page agar dapat mengelola Audit & Security secara efisien.

## Backend Tasks
# | Phase | Module | Task | Subtasks | Story Points | Priority | Start Date | End Date | Duration | User Story
1 | Phase 1 - Foundation | M01 - Authentication & Authorization | Auth API - Register/Login/Logout | POST /api/auth/register POST /api/auth/login POST /api/auth/logout JWT token generation & refresh Password hashing (bcrypt) Email verification flow | 8 | High | 2025-04-01 | 2025-04-15 | 2w | Sebagai sistem, saya ingin auth api - register/login/logout agar dapat mengelola Authentication & Authorization secara efisien.
2 | Phase 1 - Foundation | M01 - Authentication & Authorization | Role & Permission System | Role model (super_admin, owner, admin, manager, staff, cashier, etc) Permission matrix CRUD Middleware auth guard Middleware role guard Middleware module access guard | 8 | High | 2025-04-01 | 2025-04-15 | 2w | Sebagai sistem, saya ingin role & permission system agar dapat mengelola Authentication & Authorization secara efisien.
3 | Phase 1 - Foundation | M01 - Authentication & Authorization | Multi-Tenant Isolation | Tenant model & migration Tenant middleware for data isolation Tenant-aware query scoping Tenant settings API | 5 | Medium | 2025-04-08 | 2025-04-22 | 2w | Sebagai sistem, saya ingin multi-tenant isolation agar dapat mengelola Authentication & Authorization secara efisien.
4 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Onboarding API | POST /api/onboarding/start Business type selection endpoint KYB document upload Tenant provisioning service Default data seeding (roles, modules) | 8 | High | 2025-04-15 | 2025-04-29 | 2w | Sebagai sistem, saya ingin onboarding api agar dapat mengelola Onboarding & Tenant Setup secara efisien.
5 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Subscription & Package API | Package model & CRUD Subscription lifecycle Module activation per package Trial period management | 5 | Medium | 2025-04-22 | 2025-05-06 | 2w | Sebagai sistem, saya ingin subscription & package api agar dapat mengelola Onboarding & Tenant Setup secara efisien.
6 | Phase 1 - Foundation | M03 - Branch Management | Branch CRUD API | GET/POST/PUT/DELETE /api/branches Branch model & migration Branch-module activation Branch user assignment Branch real-time metrics model | 8 | High | 2025-04-22 | 2025-05-06 | 2w | Sebagai sistem, saya ingin branch crud api agar dapat mengelola Branch Management secara efisien.
7 | Phase 1 - Foundation | M03 - Branch Management | Branch Performance API | Sales aggregation per branch Inventory status per branch Employee count & schedule Comparison analytics endpoint | 5 | Medium | 2025-04-29 | 2025-05-13 | 2w | Sebagai sistem, saya ingin branch performance api agar dapat mengelola Branch Management secara efisien.
8 | Phase 1 - Foundation | M04 - Settings & Configuration | Settings API | Store settings CRUD Tax & fee configuration Notification settings Module toggle endpoints Integration config endpoints | 5 | Medium | 2025-05-06 | 2025-05-20 | 2w | Sebagai sistem, saya ingin settings api agar dapat mengelola Settings & Configuration secara efisien.
9 | Phase 2 - Core Commerce | M05 - Product & Category Management | Product CRUD API | Product model & migration GET/POST/PUT/DELETE /api/products Product variant support Image upload (multer) Barcode generation Bulk import/export CSV | 8 | High | 2025-05-20 | 2025-06-03 | 2w | Sebagai sistem, saya ingin product crud api agar dapat mengelola Product & Category Management secara efisien.
10 | Phase 2 - Core Commerce | M05 - Product & Category Management | Category & Pricing API | Category hierarchy CRUD Price tier model Multi-branch pricing logic Product cost component tracking HPP (Cost of Goods) calculation | 8 | High | 2025-05-27 | 2025-06-10 | 2w | Sebagai sistem, saya ingin category & pricing api agar dapat mengelola Product & Category Management secara efisien.
11 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | POS Transaction API | POST /api/pos/transactions Transaction model & items Payment processing (cash, card, QRIS, e-wallet) Split payment logic Void & refund endpoints Transaction search & filter | 13 | Critical | 2025-06-03 | 2025-06-24 | 3w | Sebagai sistem, saya ingin pos transaction api agar dapat mengelola Point of Sale (POS) secara efisien.
12 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Shift & Cash Management API | Open/close shift endpoints Cash drawer tracking Shift handover report Held transaction CRUD Daily sales summary | 8 | High | 2025-06-10 | 2025-06-24 | 2w | Sebagai sistem, saya ingin shift & cash management api agar dapat mengelola Point of Sale (POS) secara efisien.
13 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Receipt & Printer API | Receipt template engine Thermal printer config Digital receipt (email/WA) Receipt reprint endpoint | 5 | Medium | 2025-06-17 | 2025-06-24 | 1w | Sebagai sistem, saya ingin receipt & printer api agar dapat mengelola Point of Sale (POS) secara efisien.
14 | Phase 2 - Core Commerce | M07 - Inventory Management | Stock & Warehouse API | Stock model per branch/warehouse Stock movement logging GET /api/inventory/stock Stock adjustment endpoints Warehouse CRUD Stock transfer between branches | 13 | Critical | 2025-06-10 | 2025-07-01 | 3w | Sebagai sistem, saya ingin stock & warehouse api agar dapat mengelola Inventory Management secara efisien.
15 | Phase 2 - Core Commerce | M07 - Inventory Management | Stock Opname API | Stock opname session CRUD Opname item recording Variance calculation Approval workflow Opname history & reports | 8 | High | 2025-06-24 | 2025-07-08 | 2w | Sebagai sistem, saya ingin stock opname api agar dapat mengelola Inventory Management secara efisien.
16 | Phase 2 - Core Commerce | M07 - Inventory Management | Alerts & Reorder API | Low stock threshold config Alert generation service Reorder point notification Stock expiry tracking Batch/lot number tracking | 5 | Medium | 2025-07-01 | 2025-07-15 | 2w | Sebagai sistem, saya ingin alerts & reorder api agar dapat mengelola Inventory Management secara efisien.
17 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Purchase Order API | PO model & items PO CRUD endpoints PO approval workflow PO status tracking Auto-PO from reorder point | 8 | High | 2025-07-01 | 2025-07-15 | 2w | Sebagai sistem, saya ingin purchase order api agar dapat mengelola Purchase Orders & Suppliers secara efisien.
18 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Supplier & Goods Receipt API | Supplier CRUD Goods receipt recording Partial receipt handling Receipt-to-stock integration Supplier performance metrics | 5 | Medium | 2025-07-08 | 2025-07-22 | 2w | Sebagai sistem, saya ingin supplier & goods receipt api agar dapat mengelola Purchase Orders & Suppliers secara efisien.
19 | Phase 3 - Customer & Engagement | M09 - Customer Management | Customer CRUD API | Customer model & migration GET/POST/PUT/DELETE endpoints Customer search & filter Customer import/export Customer segmentation logic Corporate customer support | 8 | High | 2025-07-15 | 2025-07-29 | 2w | Sebagai sistem, saya ingin customer crud api agar dapat mengelola Customer Management secara efisien.
20 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Loyalty Program API | LoyaltyProgram model Point transaction recording Tier calculation engine Reward catalog CRUD Redemption processing Point expiry service | 8 | High | 2025-07-29 | 2025-08-12 | 2w | Sebagai sistem, saya ingin loyalty program api agar dapat mengelola Loyalty Program secara efisien.
21 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Promo & Voucher API | Promo model & rules engine Bundle deal logic Voucher generation (unique codes) Voucher validation & redemption Promo scheduling Category/product-specific promos | 8 | High | 2025-08-12 | 2025-08-26 | 2w | Sebagai sistem, saya ingin promo & voucher api agar dapat mengelola Promo & Voucher secara efisien.
22 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | CRM Core API | CrmContact model CrmCommunication model CrmInteraction tracking CrmDocument management CrmCalendarEvent CRUD Customer 360 aggregation endpoint | 8 | High | 2025-08-05 | 2025-08-19 | 2w | Sebagai sistem, saya ingin crm core api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
23 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | CRM Tickets & Automation API | CrmTicket CRUD SLA policy engine Ticket escalation logic CrmAutomationRule engine Trigger-based actions CrmFollowUp scheduler | 8 | High | 2025-08-12 | 2025-08-26 | 2w | Sebagai sistem, saya ingin crm tickets & automation api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
24 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | CRM Forecasting API | CrmForecast model Pipeline value calculation Win probability scoring CrmDealScore model Forecast vs actual comparison | 5 | Medium | 2025-08-19 | 2025-09-02 | 2w | Sebagai sistem, saya ingin crm forecasting api agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
25 | Phase 4 - Operations | M13 - Kitchen Management | Kitchen Order API | KitchenOrder model Order queue management Order status updates (new/preparing/ready/served) KDS integration endpoint Order priority logic | 8 | High | 2025-08-12 | 2025-08-26 | 2w | Sebagai sistem, saya ingin kitchen order api agar dapat mengelola Kitchen Management secara efisien.
26 | Phase 4 - Operations | M13 - Kitchen Management | Recipe & Kitchen Inventory API | Recipe CRUD with ingredients Auto-deduct stock on order Kitchen inventory tracking Production waste recording Recipe costing calculation | 8 | High | 2025-08-19 | 2025-09-02 | 2w | Sebagai sistem, saya ingin recipe & kitchen inventory api agar dapat mengelola Kitchen Management secara efisien.
27 | Phase 4 - Operations | M14 - Table & Reservation Management | Table & Session API | Table model CRUD Table session management Table status tracking Merge/split table Table-POS transaction linking | 5 | Medium | 2025-08-26 | 2025-09-09 | 2w | Sebagai sistem, saya ingin table & session api agar dapat mengelola Table & Reservation Management secara efisien.
28 | Phase 4 - Operations | M14 - Table & Reservation Management | Reservation API | Reservation CRUD Availability check Confirmation & reminder Walk-in vs reserved Cancellation policy | 5 | Medium | 2025-09-02 | 2025-09-16 | 2w | Sebagai sistem, saya ingin reservation api agar dapat mengelola Table & Reservation Management secara efisien.
29 | Phase 4 - Operations | M15 - Employee & Schedule Management | Schedule & Shift API | Shift model & templates Schedule CRUD Shift assignment engine Shift handover recording Schedule conflict detection | 5 | Medium | 2025-09-02 | 2025-09-16 | 2w | Sebagai sistem, saya ingin schedule & shift api agar dapat mengelola Employee & Schedule Management secara efisien.
30 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Employee Database API | Employee model (comprehensive) Employee documents Employee family data Employee education & skills Employee work experience Organization structure Job grade system | 8 | High | 2025-09-09 | 2025-09-23 | 2w | Sebagai sistem, saya ingin employee database api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
31 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Attendance & Devices API | AttendanceDevice model Device log ingestion Attendance calculation Overtime calculation AttendanceSettings per branch Fingerprint/face device integration | 8 | High | 2025-09-16 | 2025-09-30 | 2w | Sebagai sistem, saya ingin attendance & devices api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
32 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Payroll API | PayrollComponent model Salary structure Payroll run processing Tax calculation (PPh21) Payslip generation Bank file export | 13 | Critical | 2025-09-23 | 2025-10-14 | 3w | Sebagai sistem, saya ingin payroll api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
33 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Leave & Performance API | LeaveType & balance model Leave request workflow Leave approval chain PerformanceReview model KPI template & scoring 360 feedback system | 8 | High | 2025-09-30 | 2025-10-14 | 2w | Sebagai sistem, saya ingin leave & performance api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
34 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Recruitment & Training API | Job posting CRUD Candidate tracking Interview scheduling Training program model Certification tracking Employee mutation/transfer | 5 | Medium | 2025-10-07 | 2025-10-21 | 2w | Sebagai sistem, saya ingin recruitment & training api agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
35 | Phase 5 - Finance & Advanced | M17 - Finance Lite | Finance Lite API | FinanceTransaction model Daily income aggregation Basic expense recording Daily/weekly/monthly summary Export to Excel/PDF | 5 | Medium | 2025-10-07 | 2025-10-21 | 2w | Sebagai sistem, saya ingin finance lite api agar dapat mengelola Finance Lite secara efisien.
36 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Chart of Accounts & GL API | FinanceAccount model (CoA) Journal entry recording General ledger queries Trial balance calculation Balance sheet generation Income statement (P&L) | 13 | Critical | 2025-10-14 | 2025-11-04 | 3w | Sebagai sistem, saya ingin chart of accounts & gl api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
37 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Invoice & AP/AR API | Invoice model & items Invoice generation from POS AR tracking & aging AP tracking & aging Payment recording Invoice email sending | 8 | High | 2025-10-28 | 2025-11-11 | 2w | Sebagai sistem, saya ingin invoice & ap/ar api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
38 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Budget & Cash Flow API | Budget model per department Budget vs actual tracking Cash flow projection Cash flow report Tax calculation service Tax report generation | 8 | High | 2025-11-04 | 2025-11-18 | 2w | Sebagai sistem, saya ingin budget & cash flow api agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
39 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | SFA Core API | SfaTeam & territory model SfaVisit with GPS check-in SfaLead & opportunity pipeline SfaFieldOrder CRUD SfaQuotation CRUD Coverage plan & assignment | 13 | Critical | 2025-10-28 | 2025-11-18 | 3w | Sebagai sistem, saya ingin sfa core api agar dapat mengelola SFA (Sales Force Automation) secara efisien.
40 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | SFA Target & Incentive API | SfaTarget & assignment model Achievement tracking Incentive scheme engine Commission calculation SfaPlafon (credit limit) Approval workflow | 8 | High | 2025-11-11 | 2025-11-25 | 2w | Sebagai sistem, saya ingin sfa target & incentive api agar dapat mengelola SFA (Sales Force Automation) secara efisien.
41 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Marketing API | MktCampaign CRUD MktCampaignChannel tracking MktSegment & rules engine MktPromotion model MktBudget tracking Campaign performance analytics | 8 | High | 2025-11-18 | 2025-12-02 | 2w | Sebagai sistem, saya ingin marketing api agar dapat mengelola Marketing & Campaigns secara efisien.
42 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Fleet Core API | FleetVehicle CRUD FleetDriver CRUD GPS location ingestion Geofence model & check Maintenance schedule engine Fuel transaction recording Inspection & incident models | 13 | Critical | 2025-11-18 | 2025-12-09 | 3w | Sebagai sistem, saya ingin fleet core api agar dapat mengelola Fleet Management (FMS) secara efisien.
43 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | TMS API | Shipment CRUD Dispatch & assignment Tracking status updates Carrier model & scoring Route optimization Rate card management Zone & warehouse mapping Billing integration SLA monitoring | 13 | Critical | 2025-12-02 | 2025-12-23 | 3w | Sebagai sistem, saya ingin tms api agar dapat mengelola Transportation Management (TMS) secara efisien.
44 | Phase 6 - Enterprise | M23 - Manufacturing | Manufacturing API | MfgWorkOrder CRUD MfgBom & BomItem MfgRouting & operations MfgWorkCenter & Machine MfgQcTemplate & inspection MfgProductionPlan MfgProductionCost MfgWasteRecord MfgShiftProduction Subcontracting model COGM calculation | 13 | Critical | 2025-12-09 | 2025-12-30 | 3w | Sebagai sistem, saya ingin manufacturing api agar dapat mengelola Manufacturing secara efisien.
45 | Phase 6 - Enterprise | M24 - Asset Management | Asset Management API | Asset CRUD AssetCategory model Depreciation calculation (SL/DB/SYD) AssetMovement tracking AssetMaintenanceSchedule AssetWorkOrder AssetLicense tracking AssetTenancy (rental) Alert generation | 8 | High | 2025-12-23 | 2026-01-06 | 2w | Sebagai sistem, saya ingin asset management api agar dapat mengelola Asset Management secara efisien.
46 | Phase 6 - Enterprise | M25 - Project Management | Project Management API | PjmProject CRUD PjmTask CRUD PjmMilestone model PjmTimesheet recording PjmResource allocation PjmRisk model PjmBudget tracking PjmDocument management | 8 | High | 2025-12-30 | 2026-01-13 | 2w | Sebagai sistem, saya ingin project management api agar dapat mengelola Project Management secara efisien.
47 | Phase 6 - Enterprise | M26 - E-Procurement | E-Procurement API | EprVendor CRUD EprProcurementRequest EprRfq & responses EprTender & bids EprContract lifecycle EprEvaluation scoring Approval workflows Analytics endpoints | 8 | High | 2026-01-06 | 2026-01-20 | 2w | Sebagai sistem, saya ingin e-procurement api agar dapat mengelola E-Procurement secara efisien.
48 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | EXIM API | EximShipment CRUD EximCustoms model EximLC (Letter of Credit) EximContainer tracking EximDocument management EximPartner CRUD EximCost recording EximHsCode reference Analytics endpoints | 8 | High | 2026-01-13 | 2026-01-27 | 2w | Sebagai sistem, saya ingin exim api agar dapat mengelola Export/Import (EXIM) secara efisien.
49 | Phase 6 - Enterprise | M28 - Reports & Analytics | Report Engine API | Report query builder Sales report aggregation Inventory report aggregation Finance report aggregation HR report aggregation Consolidated multi-branch report Export to Excel/PDF/CSV Scheduled report (cron) | 13 | Critical | 2025-12-02 | 2025-12-23 | 3w | Sebagai sistem, saya ingin report engine api agar dapat mengelola Reports & Analytics secara efisien.
50 | Phase 6 - Enterprise | M29 - WhatsApp Business Integration | WhatsApp API Integration | WA Business API connection Message template CRUD Broadcast service Auto-reply webhook handler Message log & analytics Rate limiting | 8 | High | 2026-01-20 | 2026-02-03 | 2w | Sebagai sistem, saya ingin whatsapp api integration agar dapat mengelola WhatsApp Business Integration secara efisien.
51 | Phase 6 - Enterprise | M30 - Marketplace Integration | Marketplace API Integration | Marketplace adapter pattern Tokopedia API integration Shopee API integration Product sync service Order sync service Stock sync service Webhook handlers Error retry queue | 13 | Critical | 2026-01-27 | 2026-02-17 | 3w | Sebagai sistem, saya ingin marketplace api integration agar dapat mengelola Marketplace Integration secara efisien.
52 | Phase 6 - Enterprise | M31 - Website Builder | Website Builder API | Page model CRUD Component/section storage Theme configuration Publish/unpublish endpoint Custom domain mapping SEO metadata | 5 | Medium | 2026-02-03 | 2026-02-17 | 2w | Sebagai sistem, saya ingin website builder api agar dapat mengelola Website Builder secara efisien.
53 | Phase 6 - Enterprise | M32 - Knowledge Base | Knowledge Base API | Article model CRUD Category organization Full-text search Article versioning Access control | 3 | Low | 2026-02-10 | 2026-02-17 | 1w | Sebagai sistem, saya ingin knowledge base api agar dapat mengelola Knowledge Base secara efisien.
54 | Phase 6 - Enterprise | M33 - Billing & Subscription (SaaS) | Billing API | SubscriptionPackage CRUD Subscription model & lifecycle BillingCycle tracking Invoice auto-generation Payment gateway integration (Stripe/Midtrans) Webhook payment confirmation Usage-based billing Downgrade/upgrade logic | 8 | High | 2026-02-03 | 2026-02-17 | 2w | Sebagai sistem, saya ingin billing api agar dapat mengelola Billing & Subscription (SaaS) secara efisien.
55 | Phase 6 - Enterprise | M34 - Admin Panel (Super Admin) | Admin API | Tenant list & management Module activation/deactivation System user management Audit log queries Business type CRUD System health endpoints Backup management | 8 | High | 2026-02-10 | 2026-02-24 | 2w | Sebagai sistem, saya ingin admin api agar dapat mengelola Admin Panel (Super Admin) secara efisien.
56 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Notification Service | Notification model WebSocket/SSE real-time delivery Push notification (FCM) Email notification (Nodemailer) Alert subscription model Alert trigger engine Notification preferences | 8 | High | 2026-02-17 | 2026-03-03 | 2w | Sebagai sistem, saya ingin notification service agar dapat mengelola Notifications & Alerts secara efisien.
57 | Phase 6 - Enterprise | M36 - Audit & Security | Audit & Security Services | AuditLog model Audit middleware (auto-log all mutations) IP tracking Rate limiting middleware CORS configuration Security headers (helmet) Data encryption at rest API key management | 5 | Medium | 2026-02-17 | 2026-03-03 | 2w | Sebagai sistem, saya ingin audit & security services agar dapat mengelola Audit & Security secara efisien.

## Frontend Tasks
# | Phase | Module | Task | Subtasks | Story Points | Priority | Start Date | End Date | Duration | User Story
1 | Phase 1 - Foundation | M01 - Authentication & Authorization | Login & Register Pages | Login page UI Register page UI Forgot password flow OTP verification UI Auth context/provider | 5 | Medium | 2025-04-08 | 2025-04-22 | 2w | Sebagai pengguna web, saya ingin login & register pages agar dapat mengelola Authentication & Authorization secara efisien.
2 | Phase 1 - Foundation | M01 - Authentication & Authorization | Auth Guards & Layout | Protected route wrapper Role-based route guard Layout with sidebar (HQ/Branch/Admin) Sidebar config integration User profile dropdown | 5 | Medium | 2025-04-15 | 2025-04-29 | 2w | Sebagai pengguna web, saya ingin auth guards & layout agar dapat mengelola Authentication & Authorization secara efisien.
3 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Onboarding Wizard UI | Step 1: Business info form Step 2: Business type selection Step 3: KYB document upload Step 4: Branch setup Step 5: Admin user creation Progress indicator | 8 | High | 2025-04-22 | 2025-05-06 | 2w | Sebagai pengguna web, saya ingin onboarding wizard ui agar dapat mengelola Onboarding & Tenant Setup secara efisien.
4 | Phase 1 - Foundation | M03 - Branch Management | Branch List & Detail Pages | Branch list with filters & search Branch detail page Branch creation form Branch settings page Branch performance dashboard | 8 | High | 2025-04-29 | 2025-05-13 | 2w | Sebagai pengguna web, saya ingin branch list & detail pages agar dapat mengelola Branch Management secara efisien.
5 | Phase 1 - Foundation | M03 - Branch Management | Branch Performance Charts | Revenue comparison chart Top/bottom branch ranking Branch map view (Leaflet) Real-time metrics cards | 5 | Medium | 2025-05-06 | 2025-05-20 | 2w | Sebagai pengguna web, saya ingin branch performance charts agar dapat mengelola Branch Management secara efisien.
6 | Phase 1 - Foundation | M04 - Settings & Configuration | Settings Pages | Global settings page Module management page Tax & fee settings Notification preferences Integration settings page | 5 | Medium | 2025-05-13 | 2025-05-27 | 2w | Sebagai pengguna web, saya ingin settings pages agar dapat mengelola Settings & Configuration secara efisien.
7 | Phase 2 - Core Commerce | M05 - Product & Category Management | Product Management Pages | Product list with grid/list view Product create/edit form Variant builder UI Image upload with crop Barcode scanner integration Bulk import UI | 8 | High | 2025-05-27 | 2025-06-10 | 2w | Sebagai pengguna web, saya ingin product management pages agar dapat mengelola Product & Category Management secara efisien.
8 | Phase 2 - Core Commerce | M05 - Product & Category Management | Category & Pricing Pages | Category tree view Drag-drop category reorder Price tier management Branch-specific pricing UI | 5 | Medium | 2025-06-03 | 2025-06-17 | 2w | Sebagai pengguna web, saya ingin category & pricing pages agar dapat mengelola Product & Category Management secara efisien.
9 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | POS Cashier Interface | POS main screen layout Product grid with categories Cart management Quantity & discount controls Customer selection Barcode scanner input Payment modal (multi-method) Split bill UI Receipt preview & print | 13 | Critical | 2025-06-10 | 2025-07-01 | 3w | Sebagai pengguna web, saya ingin pos cashier interface agar dapat mengelola Point of Sale (POS) secara efisien.
10 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Shift & Transaction History | Shift open/close dialogs Cash count form Shift summary report Transaction history list Transaction detail & reprint Held transactions list | 8 | High | 2025-06-24 | 2025-07-08 | 2w | Sebagai pengguna web, saya ingin shift & transaction history agar dapat mengelola Point of Sale (POS) secara efisien.
11 | Phase 2 - Core Commerce | M07 - Inventory Management | Inventory Dashboard & Stock Pages | Inventory dashboard with KPIs Stock list with filters Stock detail & movement history Stock adjustment form Transfer request form Multi-warehouse view | 8 | High | 2025-06-17 | 2025-07-08 | 3w | Sebagai pengguna web, saya ingin inventory dashboard & stock pages agar dapat mengelola Inventory Management secara efisien.
12 | Phase 2 - Core Commerce | M07 - Inventory Management | Stock Opname UI | Start opname wizard Item count entry (manual + scan) Variance review screen Approval flow UI Opname history page | 8 | High | 2025-07-01 | 2025-07-15 | 2w | Sebagai pengguna web, saya ingin stock opname ui agar dapat mengelola Inventory Management secara efisien.
13 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Purchase Order Pages | PO list & filter PO creation wizard PO approval screen PO detail & status timeline Supplier list & form Goods receipt form | 8 | High | 2025-07-08 | 2025-07-22 | 2w | Sebagai pengguna web, saya ingin purchase order pages agar dapat mengelola Purchase Orders & Suppliers secara efisien.
14 | Phase 3 - Customer & Engagement | M09 - Customer Management | Customer Management Pages | Customer list with search Customer detail 360 view Add customer wizard Customer edit form Transaction history per customer Customer segmentation UI Corporate customer form | 8 | High | 2025-07-15 | 2025-07-29 | 2w | Sebagai pengguna web, saya ingin customer management pages agar dapat mengelola Customer Management secara efisien.
15 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Loyalty Program Pages | Loyalty dashboard Program configuration Tier management Reward catalog editor Redemption history Member analytics | 8 | High | 2025-07-29 | 2025-08-12 | 2w | Sebagai pengguna web, saya ingin loyalty program pages agar dapat mengelola Loyalty Program secara efisien.
16 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Promo & Voucher Pages | Promo list & creation wizard Bundle builder UI Voucher generator page Promo analytics dashboard Promo calendar view | 8 | High | 2025-08-12 | 2025-08-26 | 2w | Sebagai pengguna web, saya ingin promo & voucher pages agar dapat mengelola Promo & Voucher secara efisien.
17 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | CRM Dashboard & Contact Pages | CRM dashboard with pipeline Contact list & 360 view Communication timeline Calendar & task integration Document management UI | 8 | High | 2025-08-12 | 2025-08-26 | 2w | Sebagai pengguna web, saya ingin crm dashboard & contact pages agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
18 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | CRM Tickets & Automation UI | Ticket list & kanban board Ticket detail & comments SLA configuration page Automation rule builder Follow-up scheduler | 8 | High | 2025-08-19 | 2025-09-02 | 2w | Sebagai pengguna web, saya ingin crm tickets & automation ui agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
19 | Phase 4 - Operations | M13 - Kitchen Management | Kitchen Display System (KDS) | KDS board layout Order cards with timers Status update buttons Sound/visual alerts Multi-station view | 8 | High | 2025-08-19 | 2025-09-02 | 2w | Sebagai pengguna web, saya ingin kitchen display system (kds) agar dapat mengelola Kitchen Management secara efisien.
20 | Phase 4 - Operations | M13 - Kitchen Management | Recipe & Kitchen Settings | Recipe editor Ingredient mapping Kitchen inventory page Kitchen staff assignment Kitchen settings | 5 | Medium | 2025-08-26 | 2025-09-09 | 2w | Sebagai pengguna web, saya ingin recipe & kitchen settings agar dapat mengelola Kitchen Management secara efisien.
21 | Phase 4 - Operations | M14 - Table & Reservation Management | Table Layout & Reservation UI | Drag-drop table layout editor Real-time table status map Table session view Reservation calendar Reservation create/edit form Waitlist management | 8 | High | 2025-09-02 | 2025-09-16 | 2w | Sebagai pengguna web, saya ingin table layout & reservation ui agar dapat mengelola Table & Reservation Management secara efisien.
22 | Phase 4 - Operations | M15 - Employee & Schedule Management | Schedule & Shift Pages | Schedule calendar view (FullCalendar) Shift template builder Drag-drop shift assignment Shift handover form Schedule print/export | 8 | High | 2025-09-02 | 2025-09-16 | 2w | Sebagai pengguna web, saya ingin schedule & shift pages agar dapat mengelola Employee & Schedule Management secara efisien.
23 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | HRIS Dashboard & Employee Pages | HRIS dashboard Employee list & detail Employee create/edit wizard Organization chart Document management Employee lifecycle timeline | 8 | High | 2025-09-16 | 2025-09-30 | 2w | Sebagai pengguna web, saya ingin hris dashboard & employee pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
24 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Attendance & Payroll Pages | Attendance dashboard Daily attendance log Device management page Payroll run wizard Payslip viewer Salary structure editor | 8 | High | 2025-09-30 | 2025-10-14 | 2w | Sebagai pengguna web, saya ingin attendance & payroll pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
25 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Leave, KPI & Recruitment Pages | Leave calendar & balance Leave request form Leave approval list KPI dashboard KPI scoring form Performance review form Recruitment pipeline board Training catalog | 8 | High | 2025-10-07 | 2025-10-21 | 2w | Sebagai pengguna web, saya ingin leave, kpi & recruitment pages agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
26 | Phase 5 - Finance & Advanced | M17 - Finance Lite | Finance Lite Pages | Transaction list Daily summary dashboard Simple income/expense chart Export buttons | 5 | Medium | 2025-10-07 | 2025-10-21 | 2w | Sebagai pengguna web, saya ingin finance lite pages agar dapat mengelola Finance Lite secara efisien.
27 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Finance Dashboard & GL Pages | Finance dashboard with KPIs Chart of Accounts page Journal entry form General ledger view Trial balance report P&L report Balance sheet report | 13 | Critical | 2025-10-21 | 2025-11-11 | 3w | Sebagai pengguna web, saya ingin finance dashboard & gl pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
28 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Invoice & AP/AR Pages | Invoice list & detail Invoice creation form AR aging report AP aging report Payment recording form Invoice PDF preview | 8 | High | 2025-11-04 | 2025-11-18 | 2w | Sebagai pengguna web, saya ingin invoice & ap/ar pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
29 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Budget & Tax Pages | Budget planning page Budget vs actual chart Cash flow report Tax summary page Financial ratio analysis | 5 | Medium | 2025-11-11 | 2025-11-25 | 2w | Sebagai pengguna web, saya ingin budget & tax pages agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
30 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | SFA Dashboard & Pages | SFA dashboard Visit map & list Lead/opportunity pipeline (kanban) Field order management Quotation builder Team & territory management Target setting & tracking Incentive calculation view Survey & competitor activity | 13 | Critical | 2025-11-04 | 2025-11-25 | 3w | Sebagai pengguna web, saya ingin sfa dashboard & pages agar dapat mengelola SFA (Sales Force Automation) secara efisien.
31 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Marketing Pages | Marketing dashboard Campaign builder wizard Segment builder (rules-based) Promotion management Budget allocation & tracking Campaign analytics charts | 8 | High | 2025-11-18 | 2025-12-02 | 2w | Sebagai pengguna web, saya ingin marketing pages agar dapat mengelola Marketing & Campaigns secara efisien.
32 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Fleet Dashboard & Pages | Fleet dashboard Vehicle list & detail Driver list & assignment GPS live map (Leaflet) Geofence editor Maintenance calendar Fuel log & analytics Inspection forms Incident reports Cost analytics | 13 | Critical | 2025-11-25 | 2025-12-16 | 3w | Sebagai pengguna web, saya ingin fleet dashboard & pages agar dapat mengelola Fleet Management (FMS) secara efisien.
33 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | TMS Dashboard & Pages | TMS dashboard Shipment list & tracking Dispatch board Carrier management Route planner Rate card editor Zone management SLA dashboard Logistics KPI analytics | 13 | Critical | 2025-12-09 | 2025-12-30 | 3w | Sebagai pengguna web, saya ingin tms dashboard & pages agar dapat mengelola Transportation Management (TMS) secara efisien.
34 | Phase 6 - Enterprise | M23 - Manufacturing | Manufacturing Pages | Manufacturing dashboard Work order list & detail BOM builder Routing editor Work center management Machine registry & maintenance QC inspection forms Production planning calendar OEE analytics dashboard Cost analysis Waste tracking PLM (Product Lifecycle) | 13 | Critical | 2025-12-16 | 2026-01-06 | 3w | Sebagai pengguna web, saya ingin manufacturing pages agar dapat mengelola Manufacturing secara efisien.
35 | Phase 6 - Enterprise | M24 - Asset Management | Asset Management Pages | Asset dashboard Asset registry list Asset detail & history Depreciation report Maintenance calendar Work order management License tracking page Asset movement log Settings & categories | 8 | High | 2025-12-30 | 2026-01-13 | 2w | Sebagai pengguna web, saya ingin asset management pages agar dapat mengelola Asset Management secara efisien.
36 | Phase 6 - Enterprise | M25 - Project Management | Project Management Pages | Project dashboard Project list & detail Task kanban board Gantt chart view Milestone timeline Timesheet entry & report Resource allocation view Risk register Budget tracking Document repository | 8 | High | 2026-01-06 | 2026-01-20 | 2w | Sebagai pengguna web, saya ingin project management pages agar dapat mengelola Project Management secara efisien.
37 | Phase 6 - Enterprise | M26 - E-Procurement | E-Procurement Pages | E-Procurement dashboard Vendor registry Procurement request form RFQ builder & comparison Tender management Contract management Vendor evaluation scorecards Analytics & reports | 8 | High | 2026-01-13 | 2026-01-27 | 2w | Sebagai pengguna web, saya ingin e-procurement pages agar dapat mengelola E-Procurement secara efisien.
38 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | EXIM Pages | EXIM dashboard Shipment list & detail Customs management L/C tracking Container tracking Document management Partner registry Cost analysis HS code search Analytics charts | 8 | High | 2026-01-20 | 2026-02-03 | 2w | Sebagai pengguna web, saya ingin exim pages agar dapat mengelola Export/Import (EXIM) secara efisien.
39 | Phase 6 - Enterprise | M28 - Reports & Analytics | Report Hub & Pages | Report hub dashboard Sales report page Inventory report page Finance report page Customer report page HR report page Procurement report page Custom data analysis tool Chart & pivot table builder Export & schedule UI | 13 | Critical | 2025-12-09 | 2025-12-30 | 3w | Sebagai pengguna web, saya ingin report hub & pages agar dapat mengelola Reports & Analytics secara efisien.
40 | Phase 6 - Enterprise | M29 - WhatsApp Business Integration | WhatsApp Management Pages | WA dashboard Template editor Broadcast builder & scheduler Message analytics Settings & connection | 5 | Medium | 2026-01-27 | 2026-02-10 | 2w | Sebagai pengguna web, saya ingin whatsapp management pages agar dapat mengelola WhatsApp Business Integration secara efisien.
41 | Phase 6 - Enterprise | M30 - Marketplace Integration | Marketplace Pages | Marketplace dashboard Channel connection wizard Product mapping UI Order list (multi-channel) Stock sync status Settings & configuration | 8 | High | 2026-02-03 | 2026-02-17 | 2w | Sebagai pengguna web, saya ingin marketplace pages agar dapat mengelola Marketplace Integration secara efisien.
42 | Phase 6 - Enterprise | M31 - Website Builder | Website Builder Editor | Drag-drop page editor Component palette Theme customizer Preview mode Publish flow Page list management | 8 | High | 2026-02-03 | 2026-02-24 | 3w | Sebagai pengguna web, saya ingin website builder editor agar dapat mengelola Website Builder secara efisien.
43 | Phase 6 - Enterprise | M32 - Knowledge Base | Knowledge Base Pages | Article list & search Article editor (rich text) Category navigation Version history | 3 | Low | 2026-02-10 | 2026-02-17 | 1w | Sebagai pengguna web, saya ingin knowledge base pages agar dapat mengelola Knowledge Base secara efisien.
44 | Phase 6 - Enterprise | M33 - Billing & Subscription (SaaS) | Billing Pages | Pricing page Subscription management Invoice list & detail Payment history Upgrade/downgrade flow Usage analytics | 5 | Medium | 2026-02-10 | 2026-02-24 | 2w | Sebagai pengguna web, saya ingin billing pages agar dapat mengelola Billing & Subscription (SaaS) secara efisien.
45 | Phase 6 - Enterprise | M34 - Admin Panel (Super Admin) | Admin Panel Pages | Admin dashboard Tenant list & detail Module management User management System log viewer Business type config System settings | 8 | High | 2026-02-17 | 2026-03-03 | 2w | Sebagai pengguna web, saya ingin admin panel pages agar dapat mengelola Admin Panel (Super Admin) secara efisien.
46 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Notification UI | Notification bell & dropdown Notification center page Alert subscription settings Real-time toast notifications | 3 | Low | 2026-02-24 | 2026-03-03 | 1w | Sebagai pengguna web, saya ingin notification ui agar dapat mengelola Notifications & Alerts secara efisien.
47 | Phase 6 - Enterprise | M36 - Audit & Security | Audit Log Page | Audit log viewer with filters User activity timeline Export audit data | 3 | Low | 2026-02-24 | 2026-03-03 | 1w | Sebagai pengguna web, saya ingin audit log page agar dapat mengelola Audit & Security secara efisien.

## Mobile Tasks
# | Phase | Module | Task | Subtasks | Story Points | Priority | Start Date | End Date | Duration | User Story
1 | Phase 1 - Foundation | M01 - Authentication & Authorization | Mobile Auth Flow | Login screen Biometric auth (fingerprint/face) Token storage (secure) Auto-refresh token Push notification token registration | 5 | Medium | 2025-04-22 | 2025-05-06 | 2w | Sebagai pengguna mobile, saya ingin mobile auth flow agar dapat mengelola Authentication & Authorization secara efisien.
2 | Phase 1 - Foundation | M02 - Onboarding & Tenant Setup | Mobile Onboarding | Onboarding welcome screens Business setup wizard (mobile) Initial sync after setup | 3 | Low | 2025-05-06 | 2025-05-13 | 1w | Sebagai pengguna mobile, saya ingin mobile onboarding agar dapat mengelola Onboarding & Tenant Setup secara efisien.
3 | Phase 1 - Foundation | M03 - Branch Management | Branch Switcher (Mobile) | Branch selector dropdown Branch dashboard summary Quick branch performance view | 3 | Low | 2025-05-13 | 2025-05-20 | 1w | Sebagai pengguna mobile, saya ingin branch switcher (mobile) agar dapat mengelola Branch Management secara efisien.
4 | Phase 1 - Foundation | M04 - Settings & Configuration | Mobile Settings | App preferences screen Notification toggle Printer/device settings | 3 | Low | 2025-05-20 | 2025-05-27 | 1w | Sebagai pengguna mobile, saya ingin mobile settings agar dapat mengelola Settings & Configuration secara efisien.
5 | Phase 2 - Core Commerce | M05 - Product & Category Management | Mobile Product Catalog | Product list & search Product detail view Barcode scan to find product Quick price check | 5 | Medium | 2025-06-10 | 2025-06-24 | 2w | Sebagai pengguna mobile, saya ingin mobile product catalog agar dapat mengelola Product & Category Management secara efisien.
6 | Phase 2 - Core Commerce | M06 - Point of Sale (POS) | Mobile POS | Mobile POS interface Product search & scan Cart management Payment processing Bluetooth printer integration Offline transaction queue Sync when online | 13 | Critical | 2025-06-24 | 2025-07-15 | 3w | Sebagai pengguna mobile, saya ingin mobile pos agar dapat mengelola Point of Sale (POS) secara efisien.
7 | Phase 2 - Core Commerce | M07 - Inventory Management | Mobile Stock Management | Stock check by scan Mobile stock opname Stock transfer request Low stock alert push notification Stock receive confirmation | 8 | High | 2025-07-08 | 2025-07-22 | 2w | Sebagai pengguna mobile, saya ingin mobile stock management agar dapat mengelola Inventory Management secara efisien.
8 | Phase 2 - Core Commerce | M08 - Purchase Orders & Suppliers | Mobile Goods Receipt | Scan PO barcode to receive Item count confirmation Photo proof of delivery Receipt signature capture | 5 | Medium | 2025-07-22 | 2025-07-29 | 1w | Sebagai pengguna mobile, saya ingin mobile goods receipt agar dapat mengelola Purchase Orders & Suppliers secara efisien.
9 | Phase 3 - Customer & Engagement | M09 - Customer Management | Mobile Customer Lookup | Customer search Quick add customer Customer card view Link customer to POS transaction | 3 | Low | 2025-07-29 | 2025-08-05 | 1w | Sebagai pengguna mobile, saya ingin mobile customer lookup agar dapat mengelola Customer Management secara efisien.
10 | Phase 3 - Customer & Engagement | M10 - Loyalty Program | Mobile Loyalty | Loyalty card view Point balance & history Available rewards Redeem from mobile Digital membership card | 5 | Medium | 2025-08-12 | 2025-08-26 | 2w | Sebagai pengguna mobile, saya ingin mobile loyalty agar dapat mengelola Loyalty Program secara efisien.
11 | Phase 3 - Customer & Engagement | M11 - Promo & Voucher | Mobile Promo Display | Active promo list Voucher scanner at POS Apply promo in cart Push notification for new promos | 3 | Low | 2025-08-26 | 2025-09-02 | 1w | Sebagai pengguna mobile, saya ingin mobile promo display agar dapat mengelola Promo & Voucher secara efisien.
12 | Phase 3 - Customer & Engagement | M12 - CRM (Customer Relationship Management) | Mobile CRM | Contact list & search Quick log interaction Ticket view & update Follow-up reminders (push) | 5 | Medium | 2025-08-26 | 2025-09-09 | 2w | Sebagai pengguna mobile, saya ingin mobile crm agar dapat mengelola CRM (Customer Relationship Management) secara efisien.
13 | Phase 4 - Operations | M13 - Kitchen Management | Mobile KDS | Mobile kitchen display Order status quick update Alert on new orders | 3 | Low | 2025-09-02 | 2025-09-09 | 1w | Sebagai pengguna mobile, saya ingin mobile kds agar dapat mengelola Kitchen Management secara efisien.
14 | Phase 4 - Operations | M14 - Table & Reservation Management | Mobile Table/Reservation | Table status overview Quick seat assignment Reservation lookup | 3 | Low | 2025-09-16 | 2025-09-23 | 1w | Sebagai pengguna mobile, saya ingin mobile table/reservation agar dapat mengelola Table & Reservation Management secara efisien.
15 | Phase 4 - Operations | M15 - Employee & Schedule Management | Mobile Schedule View | My schedule view Shift swap request Clock in/out Handover checklist | 5 | Medium | 2025-09-16 | 2025-09-30 | 2w | Sebagai pengguna mobile, saya ingin mobile schedule view agar dapat mengelola Employee & Schedule Management secara efisien.
16 | Phase 4 - Operations | M16 - HRIS (Human Resource Information System) | Mobile HRIS (ESS) | My profile view Clock in/out with GPS Leave request from mobile Payslip viewer KPI & goals view Training schedule Claim submission Travel request | 8 | High | 2025-10-14 | 2025-10-28 | 2w | Sebagai pengguna mobile, saya ingin mobile hris (ess) agar dapat mengelola HRIS (Human Resource Information System) secara efisien.
17 | Phase 5 - Finance & Advanced | M18 - Finance Pro (Full Accounting) | Mobile Finance | Daily revenue summary Expense quick entry Invoice approval Cash flow overview | 3 | Low | 2025-11-18 | 2025-11-25 | 1w | Sebagai pengguna mobile, saya ingin mobile finance agar dapat mengelola Finance Pro (Full Accounting) secara efisien.
18 | Phase 5 - Finance & Advanced | M19 - SFA (Sales Force Automation) | Mobile SFA | GPS check-in for visits Photo proof upload Quick field order entry Route plan view Target & achievement dashboard Customer visit history Offline mode with sync | 13 | Critical | 2025-11-18 | 2025-12-09 | 3w | Sebagai pengguna mobile, saya ingin mobile sfa agar dapat mengelola SFA (Sales Force Automation) secara efisien.
19 | Phase 5 - Finance & Advanced | M20 - Marketing & Campaigns | Mobile Marketing | Campaign overview Quick promotion setup Push notification to customers | 3 | Low | 2025-12-02 | 2025-12-09 | 1w | Sebagai pengguna mobile, saya ingin mobile marketing agar dapat mengelola Marketing & Campaigns secara efisien.
20 | Phase 6 - Enterprise | M21 - Fleet Management (FMS) | Mobile Fleet (Driver App) | Driver check-in/out GPS tracking background service Fuel entry form Vehicle inspection checklist Incident report with photos Route navigation | 8 | High | 2025-12-09 | 2025-12-23 | 2w | Sebagai pengguna mobile, saya ingin mobile fleet (driver app) agar dapat mengelola Fleet Management (FMS) secara efisien.
21 | Phase 6 - Enterprise | M22 - Transportation Management (TMS) | Mobile TMS (Driver) | Delivery task list GPS tracking & proof of delivery Signature capture Photo upload Status updates | 5 | Medium | 2025-12-23 | 2026-01-06 | 2w | Sebagai pengguna mobile, saya ingin mobile tms (driver) agar dapat mengelola Transportation Management (TMS) secara efisien.
22 | Phase 6 - Enterprise | M23 - Manufacturing | Mobile Manufacturing | Work order task view QC inspection mobile form Production count entry Machine status update Waste recording | 5 | Medium | 2025-12-30 | 2026-01-13 | 2w | Sebagai pengguna mobile, saya ingin mobile manufacturing agar dapat mengelola Manufacturing secara efisien.
23 | Phase 6 - Enterprise | M24 - Asset Management | Mobile Asset | Asset scan (barcode/QR) Asset inspection form Maintenance request Asset transfer request | 3 | Low | 2026-01-06 | 2026-01-13 | 1w | Sebagai pengguna mobile, saya ingin mobile asset agar dapat mengelola Asset Management secara efisien.
24 | Phase 6 - Enterprise | M25 - Project Management | Mobile Project | Task list & update Time logging Milestone notifications Document viewer | 3 | Low | 2026-01-13 | 2026-01-20 | 1w | Sebagai pengguna mobile, saya ingin mobile project agar dapat mengelola Project Management secara efisien.
25 | Phase 6 - Enterprise | M26 - E-Procurement | Mobile E-Procurement | Approval from mobile Vendor lookup RFQ review & compare | 3 | Low | 2026-01-20 | 2026-01-27 | 1w | Sebagai pengguna mobile, saya ingin mobile e-procurement agar dapat mengelola E-Procurement secara efisien.
26 | Phase 6 - Enterprise | M27 - Export/Import (EXIM) | Mobile EXIM | Shipment status tracker Document viewer Cost entry | 3 | Low | 2026-01-27 | 2026-02-03 | 1w | Sebagai pengguna mobile, saya ingin mobile exim agar dapat mengelola Export/Import (EXIM) secara efisien.
27 | Phase 6 - Enterprise | M28 - Reports & Analytics | Mobile Reports | Key metric dashboard Quick report viewer Share report via mobile | 3 | Low | 2025-12-23 | 2025-12-30 | 1w | Sebagai pengguna mobile, saya ingin mobile reports agar dapat mengelola Reports & Analytics secara efisien.
28 | Phase 6 - Enterprise | M35 - Notifications & Alerts | Mobile Notifications | Push notification handler Notification list screen Deep linking from notification Badge count management | 3 | Low | 2026-02-24 | 2026-03-03 | 1w | Sebagai pengguna mobile, saya ingin mobile notifications agar dapat mengelola Notifications & Alerts secara efisien.

## Gantt Chart
# | Module | Task | Platform | SP | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48
[7 empty] | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb
1 | Authentication & Authorization | Auth API - Register/Login/Logout | Backend | 8 | 2025-04-01 | 2025-04-15 | bar: Apr to Apr
2 | Authentication & Authorization | Role & Permission System | Backend | 8 | 2025-04-01 | 2025-04-15 | bar: Apr to Apr
3 | Authentication & Authorization | Multi-Tenant Isolation | Backend | 5 | 2025-04-08 | 2025-04-22 | bar: Apr to Apr
4 | Authentication & Authorization | Login & Register Pages | Frontend | 5 | 2025-04-08 | 2025-04-22 | bar: Apr to Apr
5 | Authentication & Authorization | Auth Guards & Layout | Frontend | 5 | 2025-04-15 | 2025-04-29 | bar: Apr to Apr
6 | Authentication & Authorization | Mobile Auth Flow | Mobile | 5 | 2025-04-22 | 2025-05-06 | bar: Apr to Apr
7 | Onboarding & Tenant Setup | Onboarding API | Backend | 8 | 2025-04-15 | 2025-04-29 | bar: Apr to Apr
8 | Onboarding & Tenant Setup | Subscription & Package API | Backend | 5 | 2025-04-22 | 2025-05-06 | bar: Apr to Apr
9 | Onboarding & Tenant Setup | Onboarding Wizard UI | Frontend | 8 | 2025-04-22 | 2025-05-06 | bar: Apr to Apr
10 | Onboarding & Tenant Setup | Mobile Onboarding | Mobile | 3 | 2025-05-06 | 2025-05-13 | bar: May
11 | Branch Management | Branch CRUD API | Backend | 8 | 2025-04-22 | 2025-05-06 | bar: Apr to Apr
12 | Branch Management | Branch Performance API | Backend | 5 | 2025-04-29 | 2025-05-13 | bar: Apr to May
13 | Branch Management | Branch List & Detail Pages | Frontend | 8 | 2025-04-29 | 2025-05-13 | bar: Apr to May
14 | Branch Management | Branch Performance Charts | Frontend | 5 | 2025-05-06 | 2025-05-20 | bar: May to May
15 | Branch Management | Branch Switcher (Mobile) | Mobile | 3 | 2025-05-13 | 2025-05-20 | bar: May
16 | Settings & Configuration | Settings API | Backend | 5 | 2025-05-06 | 2025-05-20 | bar: May to May
17 | Settings & Configuration | Settings Pages | Frontend | 5 | 2025-05-13 | 2025-05-27 | bar: May to May
18 | Settings & Configuration | Mobile Settings | Mobile | 3 | 2025-05-20 | 2025-05-27 | bar: May
19 | Product & Category Management | Product CRUD API | Backend | 8 | 2025-05-20 | 2025-06-03 | bar: May to May
20 | Product & Category Management | Category & Pricing API | Backend | 8 | 2025-05-27 | 2025-06-10 | bar: May to Jun
21 | Product & Category Management | Product Management Pages | Frontend | 8 | 2025-05-27 | 2025-06-10 | bar: May to Jun
22 | Product & Category Management | Category & Pricing Pages | Frontend | 5 | 2025-06-03 | 2025-06-17 | bar: Jun to Jun
23 | Product & Category Management | Mobile Product Catalog | Mobile | 5 | 2025-06-10 | 2025-06-24 | bar: Jun to Jun
24 | Point of Sale (POS) | POS Transaction API | Backend | 13 | 2025-06-03 | 2025-06-24 | bar: Jun to Jun
25 | Point of Sale (POS) | Shift & Cash Management API | Backend | 8 | 2025-06-10 | 2025-06-24 | bar: Jun to Jun
26 | Point of Sale (POS) | Receipt & Printer API | Backend | 5 | 2025-06-17 | 2025-06-24 | bar: Jun
27 | Point of Sale (POS) | POS Cashier Interface | Frontend | 13 | 2025-06-10 | 2025-07-01 | bar: Jun to Jun
28 | Point of Sale (POS) | Shift & Transaction History | Frontend | 8 | 2025-06-24 | 2025-07-08 | bar: Jun to Jul
29 | Point of Sale (POS) | Mobile POS | Mobile | 13 | 2025-06-24 | 2025-07-15 | bar: Jun to Jul
30 | Inventory Management | Stock & Warehouse API | Backend | 13 | 2025-06-10 | 2025-07-01 | bar: Jun to Jun
31 | Inventory Management | Stock Opname API | Backend | 8 | 2025-06-24 | 2025-07-08 | bar: Jun to Jul
32 | Inventory Management | Alerts & Reorder API | Backend | 5 | 2025-07-01 | 2025-07-15 | bar: Jul to Jul
33 | Inventory Management | Inventory Dashboard & Stock Pages | Frontend | 8 | 2025-06-17 | 2025-07-08 | bar: Jun to Jul
34 | Inventory Management | Stock Opname UI | Frontend | 8 | 2025-07-01 | 2025-07-15 | bar: Jul to Jul
35 | Inventory Management | Mobile Stock Management | Mobile | 8 | 2025-07-08 | 2025-07-22 | bar: Jul to Jul
36 | Purchase Orders & Suppliers | Purchase Order API | Backend | 8 | 2025-07-01 | 2025-07-15 | bar: Jul to Jul
37 | Purchase Orders & Suppliers | Supplier & Goods Receipt API | Backend | 5 | 2025-07-08 | 2025-07-22 | bar: Jul to Jul
38 | Purchase Orders & Suppliers | Purchase Order Pages | Frontend | 8 | 2025-07-08 | 2025-07-22 | bar: Jul to Jul
39 | Purchase Orders & Suppliers | Mobile Goods Receipt | Mobile | 5 | 2025-07-22 | 2025-07-29 | bar: Jul
40 | Customer Management | Customer CRUD API | Backend | 8 | 2025-07-15 | 2025-07-29 | bar: Jul to Jul
41 | Customer Management | Customer Management Pages | Frontend | 8 | 2025-07-15 | 2025-07-29 | bar: Jul to Jul
42 | Customer Management | Mobile Customer Lookup | Mobile | 3 | 2025-07-29 | 2025-08-05 | bar: Jul
43 | Loyalty Program | Loyalty Program API | Backend | 8 | 2025-07-29 | 2025-08-12 | bar: Jul to Aug
44 | Loyalty Program | Loyalty Program Pages | Frontend | 8 | 2025-07-29 | 2025-08-12 | bar: Jul to Aug
45 | Loyalty Program | Mobile Loyalty | Mobile | 5 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
46 | Promo & Voucher | Promo & Voucher API | Backend | 8 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
47 | Promo & Voucher | Promo & Voucher Pages | Frontend | 8 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
48 | Promo & Voucher | Mobile Promo Display | Mobile | 3 | 2025-08-26 | 2025-09-02 | bar: Aug
49 | CRM (Customer Relationship Management) | CRM Core API | Backend | 8 | 2025-08-05 | 2025-08-19 | bar: Aug to Aug
50 | CRM (Customer Relationship Management) | CRM Tickets & Automation API | Backend | 8 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
51 | CRM (Customer Relationship Management) | CRM Forecasting API | Backend | 5 | 2025-08-19 | 2025-09-02 | bar: Aug to Aug
52 | CRM (Customer Relationship Management) | CRM Dashboard & Contact Pages | Frontend | 8 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
53 | CRM (Customer Relationship Management) | CRM Tickets & Automation UI | Frontend | 8 | 2025-08-19 | 2025-09-02 | bar: Aug to Aug
54 | CRM (Customer Relationship Management) | Mobile CRM | Mobile | 5 | 2025-08-26 | 2025-09-09 | bar: Aug to Sep
55 | Kitchen Management | Kitchen Order API | Backend | 8 | 2025-08-12 | 2025-08-26 | bar: Aug to Aug
56 | Kitchen Management | Recipe & Kitchen Inventory API | Backend | 8 | 2025-08-19 | 2025-09-02 | bar: Aug to Aug
57 | Kitchen Management | Kitchen Display System (KDS) | Frontend | 8 | 2025-08-19 | 2025-09-02 | bar: Aug to Aug
58 | Kitchen Management | Recipe & Kitchen Settings | Frontend | 5 | 2025-08-26 | 2025-09-09 | bar: Aug to Sep
59 | Kitchen Management | Mobile KDS | Mobile | 3 | 2025-09-02 | 2025-09-09 | bar: Sep
60 | Table & Reservation Management | Table & Session API | Backend | 5 | 2025-08-26 | 2025-09-09 | bar: Aug to Sep
61 | Table & Reservation Management | Reservation API | Backend | 5 | 2025-09-02 | 2025-09-16 | bar: Sep to Sep
62 | Table & Reservation Management | Table Layout & Reservation UI | Frontend | 8 | 2025-09-02 | 2025-09-16 | bar: Sep to Sep
63 | Table & Reservation Management | Mobile Table/Reservation | Mobile | 3 | 2025-09-16 | 2025-09-23 | bar: Sep
64 | Employee & Schedule Management | Schedule & Shift API | Backend | 5 | 2025-09-02 | 2025-09-16 | bar: Sep to Sep
65 | Employee & Schedule Management | Schedule & Shift Pages | Frontend | 8 | 2025-09-02 | 2025-09-16 | bar: Sep to Sep
66 | Employee & Schedule Management | Mobile Schedule View | Mobile | 5 | 2025-09-16 | 2025-09-30 | bar: Sep to Sep
67 | HRIS (Human Resource Information System) | Employee Database API | Backend | 8 | 2025-09-09 | 2025-09-23 | bar: Sep to Sep
68 | HRIS (Human Resource Information System) | Attendance & Devices API | Backend | 8 | 2025-09-16 | 2025-09-30 | bar: Sep to Sep
69 | HRIS (Human Resource Information System) | Payroll API | Backend | 13 | 2025-09-23 | 2025-10-14 | bar: Sep to Oct
70 | HRIS (Human Resource Information System) | Leave & Performance API | Backend | 8 | 2025-09-30 | 2025-10-14 | bar: Sep to Oct
71 | HRIS (Human Resource Information System) | Recruitment & Training API | Backend | 5 | 2025-10-07 | 2025-10-21 | bar: Oct to Oct
72 | HRIS (Human Resource Information System) | HRIS Dashboard & Employee Pages | Frontend | 8 | 2025-09-16 | 2025-09-30 | bar: Sep to Sep
73 | HRIS (Human Resource Information System) | Attendance & Payroll Pages | Frontend | 8 | 2025-09-30 | 2025-10-14 | bar: Sep to Oct
74 | HRIS (Human Resource Information System) | Leave, KPI & Recruitment Pages | Frontend | 8 | 2025-10-07 | 2025-10-21 | bar: Oct to Oct
75 | HRIS (Human Resource Information System) | Mobile HRIS (ESS) | Mobile | 8 | 2025-10-14 | 2025-10-28 | bar: Oct to Oct
76 | Finance Lite | Finance Lite API | Backend | 5 | 2025-10-07 | 2025-10-21 | bar: Oct to Oct
77 | Finance Lite | Finance Lite Pages | Frontend | 5 | 2025-10-07 | 2025-10-21 | bar: Oct to Oct
78 | Finance Pro (Full Accounting) | Chart of Accounts & GL API | Backend | 13 | 2025-10-14 | 2025-11-04 | bar: Oct to Oct
79 | Finance Pro (Full Accounting) | Invoice & AP/AR API | Backend | 8 | 2025-10-28 | 2025-11-11 | bar: Oct to Nov
80 | Finance Pro (Full Accounting) | Budget & Cash Flow API | Backend | 8 | 2025-11-04 | 2025-11-18 | bar: Nov to Nov
81 | Finance Pro (Full Accounting) | Finance Dashboard & GL Pages | Frontend | 13 | 2025-10-21 | 2025-11-11 | bar: Oct to Nov
82 | Finance Pro (Full Accounting) | Invoice & AP/AR Pages | Frontend | 8 | 2025-11-04 | 2025-11-18 | bar: Nov to Nov
83 | Finance Pro (Full Accounting) | Budget & Tax Pages | Frontend | 5 | 2025-11-11 | 2025-11-25 | bar: Nov to Nov
84 | Finance Pro (Full Accounting) | Mobile Finance | Mobile | 3 | 2025-11-18 | 2025-11-25 | bar: Nov
85 | SFA (Sales Force Automation) | SFA Core API | Backend | 13 | 2025-10-28 | 2025-11-18 | bar: Oct to Nov
86 | SFA (Sales Force Automation) | SFA Target & Incentive API | Backend | 8 | 2025-11-11 | 2025-11-25 | bar: Nov to Nov
87 | SFA (Sales Force Automation) | SFA Dashboard & Pages | Frontend | 13 | 2025-11-04 | 2025-11-25 | bar: Nov to Nov
88 | SFA (Sales Force Automation) | Mobile SFA | Mobile | 13 | 2025-11-18 | 2025-12-09 | bar: Nov to Dec
89 | Marketing & Campaigns | Marketing API | Backend | 8 | 2025-11-18 | 2025-12-02 | bar: Nov to Nov
90 | Marketing & Campaigns | Marketing Pages | Frontend | 8 | 2025-11-18 | 2025-12-02 | bar: Nov to Nov
91 | Marketing & Campaigns | Mobile Marketing | Mobile | 3 | 2025-12-02 | 2025-12-09 | bar: Dec
92 | Fleet Management (FMS) | Fleet Core API | Backend | 13 | 2025-11-18 | 2025-12-09 | bar: Nov to Dec
93 | Fleet Management (FMS) | Fleet Dashboard & Pages | Frontend | 13 | 2025-11-25 | 2025-12-16 | bar: Nov to Dec
94 | Fleet Management (FMS) | Mobile Fleet (Driver App) | Mobile | 8 | 2025-12-09 | 2025-12-23 | bar: Dec to Dec
95 | Transportation Management (TMS) | TMS API | Backend | 13 | 2025-12-02 | 2025-12-23 | bar: Dec to Dec
96 | Transportation Management (TMS) | TMS Dashboard & Pages | Frontend | 13 | 2025-12-09 | 2025-12-30 | bar: Dec to Dec
97 | Transportation Management (TMS) | Mobile TMS (Driver) | Mobile | 5 | 2025-12-23 | 2026-01-06 | bar: Dec to Dec
98 | Manufacturing | Manufacturing API | Backend | 13 | 2025-12-09 | 2025-12-30 | bar: Dec to Dec
99 | Manufacturing | Manufacturing Pages | Frontend | 13 | 2025-12-16 | 2026-01-06 | bar: Dec to Dec
100 | Manufacturing | Mobile Manufacturing | Mobile | 5 | 2025-12-30 | 2026-01-13 | bar: Dec to Jan
101 | Asset Management | Asset Management API | Backend | 8 | 2025-12-23 | 2026-01-06 | bar: Dec to Dec
102 | Asset Management | Asset Management Pages | Frontend | 8 | 2025-12-30 | 2026-01-13 | bar: Dec to Jan
103 | Asset Management | Mobile Asset | Mobile | 3 | 2026-01-06 | 2026-01-13 | bar: Jan
104 | Project Management | Project Management API | Backend | 8 | 2025-12-30 | 2026-01-13 | bar: Dec to Jan
105 | Project Management | Project Management Pages | Frontend | 8 | 2026-01-06 | 2026-01-20 | bar: Jan to Jan
106 | Project Management | Mobile Project | Mobile | 3 | 2026-01-13 | 2026-01-20 | bar: Jan
107 | E-Procurement | E-Procurement API | Backend | 8 | 2026-01-06 | 2026-01-20 | bar: Jan to Jan
108 | E-Procurement | E-Procurement Pages | Frontend | 8 | 2026-01-13 | 2026-01-27 | bar: Jan to Jan
109 | E-Procurement | Mobile E-Procurement | Mobile | 3 | 2026-01-20 | 2026-01-27 | bar: Jan
110 | Export/Import (EXIM) | EXIM API | Backend | 8 | 2026-01-13 | 2026-01-27 | bar: Jan to Jan
111 | Export/Import (EXIM) | EXIM Pages | Frontend | 8 | 2026-01-20 | 2026-02-03 | bar: Jan to Jan
112 | Export/Import (EXIM) | Mobile EXIM | Mobile | 3 | 2026-01-27 | 2026-02-03 | bar: Jan
113 | Reports & Analytics | Report Engine API | Backend | 13 | 2025-12-02 | 2025-12-23 | bar: Dec to Dec
114 | Reports & Analytics | Report Hub & Pages | Frontend | 13 | 2025-12-09 | 2025-12-30 | bar: Dec to Dec
115 | Reports & Analytics | Mobile Reports | Mobile | 3 | 2025-12-23 | 2025-12-30 | bar: Dec
116 | WhatsApp Business Integration | WhatsApp API Integration | Backend | 8 | 2026-01-20 | 2026-02-03 | bar: Jan to Jan
117 | WhatsApp Business Integration | WhatsApp Management Pages | Frontend | 5 | 2026-01-27 | 2026-02-10 | bar: Jan to Feb
118 | Marketplace Integration | Marketplace API Integration | Backend | 13 | 2026-01-27 | 2026-02-17 | bar: Jan to Feb
119 | Marketplace Integration | Marketplace Pages | Frontend | 8 | 2026-02-03 | 2026-02-17 | bar: Feb to Feb
120 | Website Builder | Website Builder API | Backend | 5 | 2026-02-03 | 2026-02-17 | bar: Feb to Feb
121 | Website Builder | Website Builder Editor | Frontend | 8 | 2026-02-03 | 2026-02-24 | bar: Feb to Feb
122 | Knowledge Base | Knowledge Base API | Backend | 3 | 2026-02-10 | 2026-02-17 | bar: Feb
123 | Knowledge Base | Knowledge Base Pages | Frontend | 3 | 2026-02-10 | 2026-02-17 | bar: Feb
124 | Billing & Subscription (SaaS) | Billing API | Backend | 8 | 2026-02-03 | 2026-02-17 | bar: Feb to Feb
125 | Billing & Subscription (SaaS) | Billing Pages | Frontend | 5 | 2026-02-10 | 2026-02-24 | bar: Feb to Feb
126 | Admin Panel (Super Admin) | Admin API | Backend | 8 | 2026-02-10 | 2026-02-24 | bar: Feb to Feb
127 | Admin Panel (Super Admin) | Admin Panel Pages | Frontend | 8 | 2026-02-17 | 2026-03-03 | bar: Feb to Feb
128 | Notifications & Alerts | Notification Service | Backend | 8 | 2026-02-17 | 2026-03-03 | bar: Feb to Feb
129 | Notifications & Alerts | Notification UI | Frontend | 3 | 2026-02-24 | 2026-03-03 | bar: Feb
130 | Notifications & Alerts | Mobile Notifications | Mobile | 3 | 2026-02-24 | 2026-03-03 | bar: Feb
131 | Audit & Security | Audit & Security Services | Backend | 5 | 2026-02-17 | 2026-03-03 | bar: Feb to Feb
132 | Audit & Security | Audit Log Page | Frontend | 3 | 2026-02-24 | 2026-03-03 | bar: Feb

## Summary
PROJECT SUMMARY & STATISTICS
Category | Tasks | Story Points | % SP | Est. Man-days
Backend | 57 | 456 | 47.6% | 684
Frontend | 47 | 366 | 38.2% | 549
Mobile | 28 | 135 | 14.1% | 203
TOTAL | 132 | 957 | 100.0% | 1436
MODULE BREAKDOWN
Module | BE Tasks | FE Tasks | MB Tasks | Total SP
M01 - Authentication & Authorization | 3 | 2 | 1 | 36
M02 - Onboarding & Tenant Setup | 2 | 1 | 1 | 24
M03 - Branch Management | 2 | 2 | 1 | 29
M04 - Settings & Configuration | 1 | 1 | 1 | 13
M05 - Product & Category Management | 2 | 2 | 1 | 34
M06 - Point of Sale (POS) | 3 | 2 | 1 | 60
M07 - Inventory Management | 3 | 2 | 1 | 50
M08 - Purchase Orders & Suppliers | 2 | 1 | 1 | 26
M09 - Customer Management | 1 | 1 | 1 | 19
M10 - Loyalty Program | 1 | 1 | 1 | 21
M11 - Promo & Voucher | 1 | 1 | 1 | 19
M12 - CRM (Customer Relationship Management) | 3 | 2 | 1 | 42
M13 - Kitchen Management | 2 | 2 | 1 | 32
M14 - Table & Reservation Management | 2 | 1 | 1 | 21
M15 - Employee & Schedule Management | 1 | 1 | 1 | 18
M16 - HRIS (Human Resource Information System) | 5 | 3 | 1 | 74
M17 - Finance Lite | 1 | 1 | 0 | 10
M18 - Finance Pro (Full Accounting) | 3 | 3 | 1 | 58
M19 - SFA (Sales Force Automation) | 2 | 1 | 1 | 47
M20 - Marketing & Campaigns | 1 | 1 | 1 | 19
M21 - Fleet Management (FMS) | 1 | 1 | 1 | 34
M22 - Transportation Management (TMS) | 1 | 1 | 1 | 31
M23 - Manufacturing | 1 | 1 | 1 | 31
M24 - Asset Management | 1 | 1 | 1 | 19
M25 - Project Management | 1 | 1 | 1 | 19
M26 - E-Procurement | 1 | 1 | 1 | 19
M27 - Export/Import (EXIM) | 1 | 1 | 1 | 19
M28 - Reports & Analytics | 1 | 1 | 1 | 29
M29 - WhatsApp Business Integration | 1 | 1 | 0 | 13
M30 - Marketplace Integration | 1 | 1 | 0 | 21
M31 - Website Builder | 1 | 1 | 0 | 13
M32 - Knowledge Base | 1 | 1 | 0 | 6
M33 - Billing & Subscription (SaaS) | 1 | 1 | 0 | 13
M34 - Admin Panel (Super Admin) | 1 | 1 | 0 | 16
M35 - Notifications & Alerts | 1 | 1 | 1 | 14
M36 - Audit & Security | 1 | 1 | 0 | 8
TEAM RECOMMENDATION
Backend Developer (Senior) | 2 | Node.js, PostgreSQL, Sequelize, REST API
Backend Developer (Mid) | 2 | Node.js, Database, API Development
Frontend Developer (Senior) | 2 | Next.js, React, TailwindCSS
Frontend Developer (Mid) | 2 | React, UI/UX Implementation
Mobile Developer (Senior) | 1 | React Native, Expo
Mobile Developer (Mid) | 1 | React Native, Mobile UI
UI/UX Designer | 1 | Figma, User Research, Design System
QA Engineer | 2 | Jest, Cypress, API Testing
DevOps Engineer | 1 | CI/CD, Docker, AWS/GCP
Project Manager | 1 | Agile, Scrum, Stakeholder Management
Product Owner | 1 | Business Analysis, Requirements
TOTAL TEAM | 16

## Sprint Planning
SPRINT PLANNING (2-Week Sprints)
# | Sprint | Start Date | End Date | Key Deliverables | Phase | Sprint SP
1 | Sprint 1 | 2025-04-01 | 2025-04-15 | Authentication & Authorization | Phase 1 - Foundation | 26
2 | Sprint 2 | 2025-04-15 | 2025-04-29 | Authentication & Authorization, Onboarding & Tenant Setup, Branch Management | Phase 1 - Foundation | 39
3 | Sprint 3 | 2025-04-29 | 2025-05-13 | Onboarding & Tenant Setup, Branch Management, Settings & Configuration | Phase 1 - Foundation | 26
4 | Sprint 4 | 2025-05-13 | 2025-05-27 | Branch Management, Settings & Configuration, Product & Category Management | Phase 1 - Foundation | 19
5 | Sprint 5 | 2025-05-27 | 2025-06-10 | Product & Category Management, Point of Sale (POS) | Phase 2 - Core Commerce | 34
6 | Sprint 6 | 2025-06-10 | 2025-06-24 | Product & Category Management, Point of Sale (POS), Inventory Management | Phase 2 - Core Commerce | 52
7 | Sprint 7 | 2025-06-24 | 2025-07-08 | Point of Sale (POS), Inventory Management, Purchase Orders & Suppliers | Phase 2 - Core Commerce | 50
8 | Sprint 8 | 2025-07-08 | 2025-07-22 | Inventory Management, Purchase Orders & Suppliers, Customer Management | Phase 2 - Core Commerce | 37
9 | Sprint 9 | 2025-07-22 | 2025-08-05 | Purchase Orders & Suppliers, Customer Management, Loyalty Program | Phase 2 - Core Commerce | 24
10 | Sprint 10 | 2025-08-05 | 2025-08-19 | Loyalty Program, Promo & Voucher, CRM (Customer Relationship Management), Kitchen Management | Phase 3 - Customer & Engagement | 53
11 | Sprint 11 | 2025-08-19 | 2025-09-02 | Promo & Voucher, CRM (Customer Relationship Management), Kitchen Management, Table & Reservation Management | Phase 3 - Customer & Engagement | 47
12 | Sprint 12 | 2025-09-02 | 2025-09-16 | Kitchen Management, Table & Reservation Management, Employee & Schedule Management, HRIS (Human Resource Information System) | Phase 4 - Operations | 37
13 | Sprint 13 | 2025-09-16 | 2025-09-30 | Table & Reservation Management, Employee & Schedule Management, HRIS (Human Resource Information System) | Phase 4 - Operations | 37
14 | Sprint 14 | 2025-09-30 | 2025-10-14 | HRIS (Human Resource Information System), Finance Lite | Phase 4 - Operations | 39
15 | Sprint 15 | 2025-10-14 | 2025-10-28 | HRIS (Human Resource Information System), Finance Pro (Full Accounting) | Phase 4 - Operations | 34
16 | Sprint 16 | 2025-10-28 | 2025-11-11 | Finance Pro (Full Accounting), SFA (Sales Force Automation) | Phase 5 - Finance & Advanced | 50
17 | Sprint 17 | 2025-11-11 | 2025-11-25 | Finance Pro (Full Accounting), SFA (Sales Force Automation), Marketing & Campaigns, Fleet Management (FMS) | Phase 5 - Finance & Advanced | 58
18 | Sprint 18 | 2025-11-25 | 2025-12-09 | Marketing & Campaigns, Fleet Management (FMS), Transportation Management (TMS), Reports & Analytics | Phase 5 - Finance & Advanced | 42
19 | Sprint 19 | 2025-12-09 | 2025-12-23 | Fleet Management (FMS), Transportation Management (TMS), Manufacturing, Reports & Analytics | Phase 6 - Enterprise | 60
20 | Sprint 20 | 2025-12-23 | 2026-01-06 | Transportation Management (TMS), Manufacturing, Asset Management, Project Management, Reports & Analytics | Phase 6 - Enterprise | 37
21 | Sprint 21 | 2026-01-06 | 2026-01-20 | Asset Management, Project Management, E-Procurement, Export/Import (EXIM) | Phase 6 - Enterprise | 38
22 | Sprint 22 | 2026-01-20 | 2026-02-03 | E-Procurement, Export/Import (EXIM), WhatsApp Business Integration, Marketplace Integration | Phase 6 - Enterprise | 40
23 | Sprint 23 | 2026-02-03 | 2026-02-17 | Marketplace Integration, Website Builder, Knowledge Base, Billing & Subscription (SaaS), Admin Panel (Super Admin) | Phase 6 - Enterprise | 48
24 | Sprint 24 | 2026-02-17 | 2026-03-03 | Admin Panel (Super Admin), Notifications & Alerts, Audit & Security | Phase 6 - Enterprise | 30