## Project Overview
BEDAGANG ERP - 3-MONTH PROJECT PLAN
Project Name | Bedagang ERP - Full Development
Timeline | 13 Minggu (3 Bulan) - AGGRESSIVE
Start Date | 2026-03-26
End Date | 2026-06-25
Total Sprints | 7 sprints (2 minggu/sprint, sprint terakhir 1 minggu)
Total Tasks | 132 tasks
Total Story Points | 962 SP
Backend Tasks | 57 tasks (459 SP)
Frontend Tasks | 47 tasks (368 SP)
Mobile Tasks | 28 tasks (135 SP)
Est. Man-days | 1443 hari
GOAL | Membangun platform ERP multi-tenant SaaS lengkap dengan 36 modul dalam 3 bulan
APPROACH | Agile Sprint dengan paralelisasi maksimum, tim besar, dan modul overlap
Phase 1 | Foundation (W1-3): Auth, Onboarding, Branch, Settings
Phase 2 | Core Commerce (W3-6): Products, POS, Inventory, Purchase Orders
Phase 3 | Customer & Engagement (W5-7): Customers, Loyalty, Promo, CRM
Phase 4 | Operations (W6-9): Kitchen, Tables, Schedule, HRIS
Phase 5 | Finance & Advanced (W8-11): Finance Lite/Pro, SFA, Marketing
Phase 6 | Enterprise (W9-13): Fleet, TMS, Manufacturing, Asset, Project, EXIM, Reports, Integrations, Admin, Billing, Notifications, Audit
TEAM RECOMMENDATION | 24-30 developers (8 BE, 8 FE, 4 Mobile, 2 DevOps, 1 QA Lead, 2 QA, 1 PM, 1 Tech Lead)
NOTE | ⚠️ Timeline agresif - memerlukan tim besar dan paralelisasi penuh. Overlap antar phase untuk efisiensi.

## Task List (All)
ID | Phase | Module | Platform | Task | Subtasks | Goal | Objectives | Story Points | Priority | Start Date | End Date | Duration (Weeks) | User Story
1 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Auth API - Register/Login/Logout | POST /api/auth/register POST /api/auth/login POST /api/auth/logout JWT token generation & refresh Password hashing (bcrypt) Email verification flow | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 8 | High | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin auth api - register/login/logout agar sistem login multi-tenant dengan role-based access control
2 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Role & Permission System | Role model (super_admin, owner, admin, manager, staff, cashier) Permission matrix CRUD Middleware auth guard Middleware role guard Middleware module access guard | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 8 | High | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin role & permission system agar sistem login multi-tenant dengan role-based access control
3 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Multi-Tenant Isolation | Tenant model & migration Tenant middleware for data isolation Tenant-aware query scoping Tenant settings API | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin multi-tenant isolation agar sistem login multi-tenant dengan role-based access control
4 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Frontend | Login & Register Pages | Login page UI Register page UI Forgot password flow OTP verification UI Auth context/provider | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-03-26 | 2026-04-02 | 1 | Sebagai pengguna, saya ingin login & register pages agar sistem login multi-tenant dengan role-based access control
5 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Frontend | Auth Guards & Layout | Protected route wrapper Role-based route guard Layout with sidebar (HQ/Branch/Admin) Sidebar config integration User profile dropdown | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin auth guards & layout agar sistem login multi-tenant dengan role-based access control
6 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Mobile | Mobile Auth Flow | Login screen Biometric auth (fingerprint/face) Token storage (secure) Auto-refresh token Push notification token registration | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna mobile, saya ingin mobile auth flow agar sistem login multi-tenant dengan role-based access control
7 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Backend | Onboarding API | POST /api/onboarding/start Business type selection endpoint KYB document upload Tenant provisioning service Default data seeding | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin onboarding api agar wizard onboarding untuk tenant baru dan setup awal bisnis
8 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Backend | Subscription & Package API | Package model & CRUD Subscription lifecycle Module activation per package Trial period management | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin subscription & package api agar wizard onboarding untuk tenant baru dan setup awal bisnis
9 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Frontend | Onboarding Wizard UI | Step 1: Business info Step 2: Business type Step 3: KYB upload Step 4: Branch setup Step 5: Admin user Progress indicator | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin onboarding wizard ui agar wizard onboarding untuk tenant baru dan setup awal bisnis
10 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Mobile | Mobile Onboarding | Onboarding welcome screens Business setup wizard Initial sync | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin mobile onboarding agar wizard onboarding untuk tenant baru dan setup awal bisnis
11 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Backend | Branch CRUD API | GET/POST/PUT/DELETE /api/branches Branch model & migration Branch-module activation Branch user assignment Branch metrics model | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin branch crud api agar manajemen multi-cabang dari hq dengan monitoring performa
12 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Backend | Branch Performance API | Sales aggregation per branch Inventory status per branch Employee count & schedule Comparison analytics | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin branch performance api agar manajemen multi-cabang dari hq dengan monitoring performa
13 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Frontend | Branch List & Detail Pages | Branch list with filters Branch detail page Branch creation form Branch settings page Branch performance dashboard | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin branch list & detail pages agar manajemen multi-cabang dari hq dengan monitoring performa
14 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Frontend | Branch Performance Charts | Revenue comparison chart Branch ranking Branch map view (Leaflet) Real-time metrics cards | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna, saya ingin branch performance charts agar manajemen multi-cabang dari hq dengan monitoring performa
15 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Mobile | Branch Switcher (Mobile) | Branch selector Branch dashboard summary Quick performance view | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin branch switcher (mobile) agar manajemen multi-cabang dari hq dengan monitoring performa
16 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Backend | Settings API | Store settings CRUD Tax & fee configuration Notification settings Module toggle Integration config | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai developer, saya ingin settings api agar pengaturan global, modul, pajak, notifikasi, dan integrasi
17 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Frontend | Settings Pages | Global settings page Module management Tax & fee settings Notification preferences Integration settings | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna, saya ingin settings pages agar pengaturan global, modul, pajak, notifikasi, dan integrasi
18 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Mobile | Mobile Settings | App preferences Notification toggle Printer/device settings | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin mobile settings agar pengaturan global, modul, pajak, notifikasi, dan integrasi
19 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Backend | Product CRUD API | Product model & migration GET/POST/PUT/DELETE /api/products Product variant support Image upload (multer) Barcode generation Bulk import/export CSV | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-09 | 2026-04-16 | 1 | Sebagai developer, saya ingin product crud api agar master data produk, kategori, varian, dan harga
20 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Backend | Category & Pricing API | Category hierarchy CRUD Price tier model Multi-branch pricing logic HPP calculation | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai developer, saya ingin category & pricing api agar master data produk, kategori, varian, dan harga
21 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Frontend | Product Management Pages | Product list grid/list view Product create/edit form Variant builder UI Image upload with crop Barcode scanner Bulk import UI | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna, saya ingin product management pages agar master data produk, kategori, varian, dan harga
22 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Frontend | Category & Pricing Pages | Category tree view Drag-drop reorder Price tier management Branch-specific pricing UI | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 5 | Medium | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna, saya ingin category & pricing pages agar master data produk, kategori, varian, dan harga
23 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Mobile | Mobile Product Catalog | Product list & search Product detail view Barcode scan Quick price check | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 5 | Medium | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna mobile, saya ingin mobile product catalog agar master data produk, kategori, varian, dan harga
24 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | POS Transaction API | POST /api/pos/transactions Transaction model & items Payment processing (cash, card, QRIS, e-wallet) Split payment logic Void & refund Transaction search | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai developer, saya ingin pos transaction api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
25 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | Shift & Cash Management API | Open/close shift Cash drawer tracking Shift handover report Held transaction CRUD Daily sales summary | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai developer, saya ingin shift & cash management api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
26 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | Receipt & Printer API | Receipt template engine Thermal printer config Digital receipt (email/WA) Receipt reprint | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 5 | Medium | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin receipt & printer api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
27 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Frontend | POS Cashier Interface | POS main screen Product grid + categories Cart management Quantity & discount Customer selection Barcode scanner Payment modal Split bill UI Receipt preview & print | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai pengguna, saya ingin pos cashier interface agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
28 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Frontend | Shift & Transaction History | Shift open/close dialogs Cash count form Shift summary Transaction history Transaction detail & reprint Held transactions list | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin shift & transaction history agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
29 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Mobile | Mobile POS | Mobile POS interface Product search & scan Cart management Payment processing Bluetooth printer Offline queue Sync when online | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-23 | 2026-05-07 | 2 | Sebagai pengguna mobile, saya ingin mobile pos agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
30 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Stock & Warehouse API | Stock model per branch/warehouse Stock movement logging GET /api/inventory/stock Stock adjustment Warehouse CRUD Stock transfer | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai developer, saya ingin stock & warehouse api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
31 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Stock Opname API | Stock opname session CRUD Opname item recording Variance calculation Approval workflow Opname reports | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin stock opname api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
32 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Alerts & Reorder API | Low stock threshold Alert generation Reorder point notification Stock expiry tracking Batch/lot tracking | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 5 | Medium | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin alerts & reorder api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
33 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Frontend | Inventory Dashboard & Stock Pages | Inventory dashboard KPIs Stock list with filters Stock detail & history Stock adjustment form Transfer request form Multi-warehouse view | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin inventory dashboard & stock pages agar stok real-time, transfer antar gudang, stock opname, dan peringatan
34 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Frontend | Stock Opname UI | Start opname wizard Item count entry Variance review Approval flow UI Opname history | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin stock opname ui agar stok real-time, transfer antar gudang, stock opname, dan peringatan
35 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Mobile | Mobile Stock Management | Stock check by scan Mobile stock opname Stock transfer request Low stock alert push Stock receive confirmation | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile stock management agar stok real-time, transfer antar gudang, stock opname, dan peringatan
36 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Backend | Purchase Order API | PO model & items PO CRUD PO approval workflow PO status tracking Auto-PO from reorder point | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin purchase order api agar pembelian barang, manajemen pemasok, dan penerimaan barang
37 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Backend | Supplier & Goods Receipt API | Supplier CRUD Goods receipt recording Partial receipt Receipt-to-stock integration Supplier metrics | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 5 | Medium | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin supplier & goods receipt api agar pembelian barang, manajemen pemasok, dan penerimaan barang
38 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Frontend | Purchase Order Pages | PO list & filter PO creation wizard PO approval screen PO detail & timeline Supplier list Goods receipt form | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin purchase order pages agar pembelian barang, manajemen pemasok, dan penerimaan barang
39 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Mobile | Mobile Goods Receipt | Scan PO barcode Item count confirmation Photo proof Receipt signature capture | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 5 | Medium | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile goods receipt agar pembelian barang, manajemen pemasok, dan penerimaan barang
40 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Backend | Customer CRUD API | Customer model & migration CRUD endpoints Customer search & filter Import/export Segmentation logic Corporate customer support | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin customer crud api agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
41 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Frontend | Customer Management Pages | Customer list Customer detail 360 view Add customer wizard Edit form Transaction history Segmentation UI Corporate form | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin customer management pages agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
42 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Mobile | Mobile Customer Lookup | Customer search Quick add customer Customer card view Link to POS transaction | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 3 | Low | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile customer lookup agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
43 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Backend | Loyalty Program API | LoyaltyProgram model Point transaction Tier calculation Reward catalog CRUD Redemption processing Point expiry | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin loyalty program api agar program poin, tier, reward, dan redemption
44 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Frontend | Loyalty Program Pages | Loyalty dashboard Program config Tier management Reward catalog Redemption history Member analytics | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin loyalty program pages agar program poin, tier, reward, dan redemption
45 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Mobile | Mobile Loyalty | Loyalty card view Point balance Available rewards Redeem from mobile Digital membership | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna mobile, saya ingin mobile loyalty agar program poin, tier, reward, dan redemption
46 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Backend | Promo & Voucher API | Promo model & rules Bundle deal logic Voucher generation Voucher validation Promo scheduling Category/product promos | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin promo & voucher api agar sistem promosi, bundle, voucher, dan diskon otomatis
47 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Frontend | Promo & Voucher Pages | Promo list & wizard Bundle builder Voucher generator Promo analytics Promo calendar | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin promo & voucher pages agar sistem promosi, bundle, voucher, dan diskon otomatis
48 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Mobile | Mobile Promo Display | Active promo list Voucher scanner Apply promo in cart Push notification promos | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 3 | Low | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna mobile, saya ingin mobile promo display agar sistem promosi, bundle, voucher, dan diskon otomatis
49 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Core API | CrmContact model CrmCommunication model CrmInteraction tracking CrmDocument management CrmCalendarEvent CRUD Customer 360 aggregation | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin crm core api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
50 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Tickets & Automation API | CrmTicket CRUD SLA policy engine Ticket escalation CrmAutomationRule engine Trigger-based actions CrmFollowUp scheduler | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin crm tickets & automation api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
51 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Forecasting API | CrmForecast model Pipeline value calc Win probability CrmDealScore model Forecast vs actual | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin crm forecasting api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
52 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Frontend | CRM Dashboard & Contact Pages | CRM dashboard pipeline Contact list & 360 Communication timeline Calendar & task integration Document management UI | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin crm dashboard & contact pages agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
53 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Frontend | CRM Tickets & Automation UI | Ticket kanban Ticket detail & comments SLA config Automation rule builder Follow-up scheduler | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin crm tickets & automation ui agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
54 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Mobile | Mobile CRM | Contact list Quick log interaction Ticket view Follow-up reminders | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile crm agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
55 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Backend | Kitchen Order API | KitchenOrder model Order queue management Order status updates KDS integration Order priority logic | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin kitchen order api agar manajemen dapur f&b: pesanan, resep, inventori bahan
56 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Backend | Recipe & Kitchen Inventory API | Recipe CRUD with ingredients Auto-deduct stock Kitchen inventory tracking Waste recording Recipe costing | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin recipe & kitchen inventory api agar manajemen dapur f&b: pesanan, resep, inventori bahan
57 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Frontend | Kitchen Display System (KDS) | KDS board layout Order cards with timers Status update buttons Sound/visual alerts Multi-station view | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin kitchen display system (kds) agar manajemen dapur f&b: pesanan, resep, inventori bahan
58 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Frontend | Recipe & Kitchen Settings | Recipe editor Ingredient mapping Kitchen inventory page Staff assignment Kitchen settings | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin recipe & kitchen settings agar manajemen dapur f&b: pesanan, resep, inventori bahan
59 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Mobile | Mobile KDS | Mobile kitchen display Order status quick update Alert on new orders | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 3 | Low | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile kds agar manajemen dapur f&b: pesanan, resep, inventori bahan
60 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Backend | Table & Session API | Table model CRUD Table session management Table status tracking Merge/split table Table-POS linking | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin table & session api agar manajemen meja restoran dan sistem reservasi
61 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Backend | Reservation API | Reservation CRUD Availability check Confirmation & reminder Walk-in vs reserved Cancellation policy | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin reservation api agar manajemen meja restoran dan sistem reservasi
62 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Frontend | Table Layout & Reservation UI | Drag-drop table layout Real-time table map Table session view Reservation calendar Reservation form Waitlist management | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin table layout & reservation ui agar manajemen meja restoran dan sistem reservasi
63 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Mobile | Mobile Table/Reservation | Table status overview Quick seat assignment Reservation lookup | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 3 | Low | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile table/reservation agar manajemen meja restoran dan sistem reservasi
64 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Backend | Schedule & Shift API | Shift model & templates Schedule CRUD Shift assignment engine Shift handover recording Conflict detection | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin schedule & shift api agar jadwal karyawan, shift, dan handover
65 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Frontend | Schedule & Shift Pages | Schedule calendar (FullCalendar) Shift template builder Drag-drop assignment Shift handover form Schedule export | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin schedule & shift pages agar jadwal karyawan, shift, dan handover
66 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Mobile | Mobile Schedule View | My schedule view Shift swap request Clock in/out Handover checklist | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile schedule view agar jadwal karyawan, shift, dan handover
67 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Employee Database API | Employee model Documents Family data Education & skills Work experience Org structure Job grade system | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin employee database api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
68 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Attendance & Devices API | AttendanceDevice model Device log ingestion Attendance calc Overtime calc Settings per branch Device integration | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin attendance & devices api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
69 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Payroll API | PayrollComponent model Salary structure Payroll run processing Tax PPh21 Payslip generation Bank file export | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 13 | Critical | 2026-05-14 | 2026-05-28 | 2 | Sebagai developer, saya ingin payroll api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
70 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Leave & Performance API | LeaveType & balance Leave request workflow Approval chain PerformanceReview model KPI template 360 feedback | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin leave & performance api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
71 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Recruitment & Training API | Job posting CRUD Candidate tracking Interview scheduling Training program Certification tracking Employee mutation | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin recruitment & training api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
72 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | HRIS Dashboard & Employee Pages | HRIS dashboard Employee list & detail Create/edit wizard Org chart Document mgmt Lifecycle timeline | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin hris dashboard & employee pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
73 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | Attendance & Payroll Pages | Attendance dashboard Daily log Device management Payroll run wizard Payslip viewer Salary structure editor | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin attendance & payroll pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
74 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | Leave, KPI & Recruitment Pages | Leave calendar Leave request form Leave approval KPI dashboard KPI scoring Performance review Recruitment pipeline Training catalog | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin leave, kpi & recruitment pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
75 | Phase 4 - Operations (W6-9) | M16 - HRIS | Mobile | Mobile HRIS (ESS) | My profile Clock in/out GPS Leave request Payslip viewer KPI & goals Training schedule Claim submission Travel request | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna mobile, saya ingin mobile hris (ess) agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
76 | Phase 5 - Finance & Advanced (W8-11) | M17 - Finance Lite | Backend | Finance Lite API | FinanceTransaction model Daily income aggregation Basic expense recording Daily/weekly/monthly summary Export to Excel/PDF | Ringkasan keuangan dasar: transaksi harian dan laporan sederhana | Daily transaction summary; Basic income/expense tracking | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin finance lite api agar ringkasan keuangan dasar: transaksi harian dan laporan sederhana
77 | Phase 5 - Finance & Advanced (W8-11) | M17 - Finance Lite | Frontend | Finance Lite Pages | Transaction list Daily summary dashboard Income/expense chart Export buttons | Ringkasan keuangan dasar: transaksi harian dan laporan sederhana | Daily transaction summary; Basic income/expense tracking | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin finance lite pages agar ringkasan keuangan dasar: transaksi harian dan laporan sederhana
78 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Chart of Accounts & GL API | FinanceAccount model (CoA) Journal entry recording General ledger queries Trial balance Balance sheet Income statement (P&L) | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 13 | Critical | 2026-05-21 | 2026-06-04 | 2 | Sebagai developer, saya ingin chart of accounts & gl api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
79 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Invoice & AP/AR API | Invoice model & items Invoice from POS AR tracking & aging AP tracking & aging Payment recording Invoice email | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin invoice & ap/ar api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
80 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Budget & Cash Flow API | Budget model per dept Budget vs actual Cash flow projection Cash flow report Tax calculation Tax report | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin budget & cash flow api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
81 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Finance Dashboard & GL Pages | Finance dashboard KPIs Chart of Accounts page Journal entry form GL view Trial balance report P&L report Balance sheet report | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai pengguna, saya ingin finance dashboard & gl pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
82 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Invoice & AP/AR Pages | Invoice list & detail Invoice creation AR aging report AP aging report Payment recording Invoice PDF preview | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin invoice & ap/ar pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
83 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Budget & Tax Pages | Budget planning page Budget vs actual chart Cash flow report Tax summary Financial ratio analysis | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 5 | Medium | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin budget & tax pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
84 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Mobile | Mobile Finance | Daily revenue summary Expense quick entry Invoice approval Cash flow overview | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 3 | Low | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile finance agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
85 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Backend | SFA Core API | SfaTeam & territory SfaVisit GPS check-in SfaLead & opportunity pipeline SfaFieldOrder CRUD SfaQuotation CRUD Coverage plan | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin sfa core api agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
86 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Backend | SFA Target & Incentive API | SfaTarget & assignment Achievement tracking Incentive scheme Commission calculation SfaPlafon (credit limit) Approval workflow | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin sfa target & incentive api agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
87 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Frontend | SFA Dashboard & Pages | SFA dashboard Visit map & list Lead pipeline kanban Field order mgmt Quotation builder Territory mgmt Target tracking Incentive view Survey & competitor | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai pengguna, saya ingin sfa dashboard & pages agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
88 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Mobile | Mobile SFA | GPS check-in visits Photo proof upload Quick field order Route plan view Target dashboard Visit history Offline mode + sync | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile sfa agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
89 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Backend | Marketing API | MktCampaign CRUD MktCampaignChannel tracking MktSegment rules engine MktPromotion model MktBudget tracking Campaign analytics | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin marketing api agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
90 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Frontend | Marketing Pages | Marketing dashboard Campaign builder wizard Segment builder Promotion management Budget allocation Campaign analytics | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin marketing pages agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
91 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Mobile | Mobile Marketing | Campaign overview Quick promotion setup Push notification to customers | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 3 | Low | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile marketing agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
92 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Backend | Fleet Core API | FleetVehicle CRUD FleetDriver CRUD GPS location ingestion Geofence model & check Maintenance schedule Fuel transaction recording Inspection & incident models | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin fleet core api agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
93 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Frontend | Fleet Dashboard & Pages | Fleet dashboard Vehicle list & detail Driver list & assignment GPS live map (Leaflet) Geofence editor Maintenance calendar Fuel log & analytics Inspection forms Incident reports Cost analytics | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin fleet dashboard & pages agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
94 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Mobile | Mobile Fleet (Driver App) | Driver check-in/out GPS tracking background Fuel entry form Vehicle inspection checklist Incident report with photos Route navigation | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile fleet (driver app) agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
95 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Backend | TMS API | Shipment CRUD Dispatch & assignment Tracking status Carrier model & scoring Route optimization Rate card management Zone mapping Billing integration SLA monitoring | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin tms api agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
96 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Frontend | TMS Dashboard & Pages | TMS dashboard Shipment list & tracking Dispatch board Carrier management Route planner Rate card editor Zone management SLA dashboard Logistics KPI | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin tms dashboard & pages agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
97 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Mobile | Mobile TMS (Driver) | Delivery task list GPS tracking & proof of delivery Signature capture Photo upload Status updates | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 5 | Medium | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile tms (driver) agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
98 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Backend | Manufacturing API | MfgWorkOrder CRUD MfgBom & BomItem MfgRouting & operations MfgWorkCenter & Machine MfgQcTemplate MfgProductionPlan MfgProductionCost MfgWasteRecord MfgShiftProduction Subcontracting COGM calculation | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai developer, saya ingin manufacturing api agar produksi: work order, bom, routing, qc, oee, waste tracking
99 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Frontend | Manufacturing Pages | Manufacturing dashboard Work order list BOM builder Routing editor Work center mgmt Machine registry QC inspection forms Production planning calendar OEE analytics Cost analysis Waste tracking PLM | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin manufacturing pages agar produksi: work order, bom, routing, qc, oee, waste tracking
100 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Mobile | Mobile Manufacturing | Work order task view QC inspection mobile Production count entry Machine status update Waste recording | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile manufacturing agar produksi: work order, bom, routing, qc, oee, waste tracking
101 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Backend | Asset Management API | Asset CRUD AssetCategory Depreciation (SL/DB/SYD) AssetMovement tracking MaintenanceSchedule AssetWorkOrder AssetLicense AssetTenancy Alert generation | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin asset management api agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
102 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Frontend | Asset Management Pages | Asset dashboard Asset registry Asset detail & history Depreciation report Maintenance calendar Work order mgmt License tracking Movement log Settings | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin asset management pages agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
103 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Mobile | Mobile Asset | Asset scan (barcode/QR) Asset inspection form Maintenance request Asset transfer request | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 3 | Low | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile asset agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
104 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Backend | Project Management API | PjmProject CRUD PjmTask CRUD PjmMilestone model PjmTimesheet recording PjmResource allocation PjmRisk model PjmBudget tracking PjmDocument management | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin project management api agar manajemen proyek: task, milestone, timesheet, risk, budget
105 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Frontend | Project Management Pages | Project dashboard Project list & detail Task kanban board Gantt chart view Milestone timeline Timesheet entry Resource allocation Risk register Budget tracking Document repository | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin project management pages agar manajemen proyek: task, milestone, timesheet, risk, budget
106 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Mobile | Mobile Project | Task list & update Time logging Milestone notifications Document viewer | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile project agar manajemen proyek: task, milestone, timesheet, risk, budget
107 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Backend | E-Procurement API | EprVendor CRUD EprProcurementRequest EprRfq & responses EprTender & bids EprContract lifecycle EprEvaluation scoring Approval workflows Analytics | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin e-procurement api agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
108 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Frontend | E-Procurement Pages | E-Procurement dashboard Vendor registry Procurement request form RFQ builder Tender management Contract management Vendor evaluation Analytics & reports | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin e-procurement pages agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
109 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Mobile | Mobile E-Procurement | Approval from mobile Vendor lookup RFQ review | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile e-procurement agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
110 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Backend | EXIM API | EximShipment CRUD EximCustoms model EximLC (Letter of Credit) EximContainer tracking EximDocument mgmt EximPartner CRUD EximCost recording EximHsCode reference Analytics | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin exim api agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
111 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Frontend | EXIM Pages | EXIM dashboard Shipment list & detail Customs management L/C tracking Container tracking Document mgmt Partner registry Cost analysis HS code search Analytics | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin exim pages agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
112 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Mobile | Mobile EXIM | Shipment status tracker Document viewer Cost entry | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile exim agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
113 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Backend | Report Engine API | Report query builder Sales aggregation Inventory aggregation Finance aggregation HR aggregation Multi-branch consolidated Export Excel/PDF/CSV Scheduled report (cron) | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin report engine api agar pusat laporan konsolidasi untuk semua modul
114 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Frontend | Report Hub & Pages | Report hub dashboard Sales report page Inventory report Finance report Customer report HR report Procurement report Custom data analysis Chart & pivot builder Export & schedule UI | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin report hub & pages agar pusat laporan konsolidasi untuk semua modul
115 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Mobile | Mobile Reports | Key metric dashboard Quick report viewer Share report via mobile | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 3 | Low | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile reports agar pusat laporan konsolidasi untuk semua modul
116 | Phase 6 - Enterprise (W9-13) | M29 - WhatsApp Business Integration | Backend | WhatsApp API Integration | WA Business API connection Message template CRUD Broadcast service Auto-reply webhook Message log & analytics Rate limiting | Integrasi WhatsApp untuk broadcast, notifikasi, dan pesan otomatis | WA API integration; Broadcast messaging; Template messages; Auto-reply | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin whatsapp api integration agar integrasi whatsapp untuk broadcast, notifikasi, dan pesan otomatis
117 | Phase 6 - Enterprise (W9-13) | M29 - WhatsApp Business Integration | Frontend | WhatsApp Management Pages | WA dashboard Template editor Broadcast builder Message analytics Settings & connection | Integrasi WhatsApp untuk broadcast, notifikasi, dan pesan otomatis | WA API integration; Broadcast messaging; Template messages; Auto-reply | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin whatsapp management pages agar integrasi whatsapp untuk broadcast, notifikasi, dan pesan otomatis
118 | Phase 6 - Enterprise (W9-13) | M30 - Marketplace Integration | Backend | Marketplace API Integration | Marketplace adapter pattern Tokopedia API Shopee API Product sync service Order sync service Stock sync service Webhook handlers Error retry queue | Integrasi marketplace: sinkronisasi produk dan pesanan multi-channel | Tokopedia/Shopee/Lazada integration; Product sync; Order sync; Stock sync | 13 | Critical | 2026-06-11 | 2026-06-25 | 2 | Sebagai developer, saya ingin marketplace api integration agar integrasi marketplace: sinkronisasi produk dan pesanan multi-channel
119 | Phase 6 - Enterprise (W9-13) | M30 - Marketplace Integration | Frontend | Marketplace Pages | Marketplace dashboard Channel connection wizard Product mapping UI Order list multi-channel Stock sync status Settings | Integrasi marketplace: sinkronisasi produk dan pesanan multi-channel | Tokopedia/Shopee/Lazada integration; Product sync; Order sync; Stock sync | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin marketplace pages agar integrasi marketplace: sinkronisasi produk dan pesanan multi-channel
120 | Phase 6 - Enterprise (W9-13) | M31 - Website Builder | Backend | Website Builder API | Page model CRUD Component/section storage Theme config Publish/unpublish Custom domain mapping SEO metadata | Pembangun website drag-drop untuk toko online sederhana | Page builder; Component library; Theme system; Publish | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin website builder api agar pembangun website drag-drop untuk toko online sederhana
121 | Phase 6 - Enterprise (W9-13) | M31 - Website Builder | Frontend | Website Builder Editor | Drag-drop page editor Component palette Theme customizer Preview mode Publish flow Page list management | Pembangun website drag-drop untuk toko online sederhana | Page builder; Component library; Theme system; Publish | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin website builder editor agar pembangun website drag-drop untuk toko online sederhana
122 | Phase 6 - Enterprise (W9-13) | M32 - Knowledge Base | Backend | Knowledge Base API | Article model CRUD Category organization Full-text search Article versioning Access control | Basis pengetahuan internal untuk SOP dan dokumentasi | Article CRUD; Category organization; Search; Versioning | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin knowledge base api agar basis pengetahuan internal untuk sop dan dokumentasi
123 | Phase 6 - Enterprise (W9-13) | M32 - Knowledge Base | Frontend | Knowledge Base Pages | Article list & search Article editor (rich text) Category navigation Version history | Basis pengetahuan internal untuk SOP dan dokumentasi | Article CRUD; Category organization; Search; Versioning | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin knowledge base pages agar basis pengetahuan internal untuk sop dan dokumentasi
124 | Phase 6 - Enterprise (W9-13) | M33 - Billing & Subscription (SaaS) | Backend | Billing API | SubscriptionPackage CRUD Subscription lifecycle BillingCycle tracking Invoice auto-generation Payment gateway (Stripe/Midtrans) Webhook payment Usage-based billing Upgrade/downgrade logic | Sistem billing SaaS: paket, subscription, invoice, payment gateway | Package management; Subscription lifecycle; Invoice generation; Payment gateway | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin billing api agar sistem billing saas: paket, subscription, invoice, payment gateway
125 | Phase 6 - Enterprise (W9-13) | M33 - Billing & Subscription (SaaS) | Frontend | Billing Pages | Pricing page Subscription management Invoice list & detail Payment history Upgrade/downgrade flow Usage analytics | Sistem billing SaaS: paket, subscription, invoice, payment gateway | Package management; Subscription lifecycle; Invoice generation; Payment gateway | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin billing pages agar sistem billing saas: paket, subscription, invoice, payment gateway
126 | Phase 6 - Enterprise (W9-13) | M34 - Admin Panel (Super Admin) | Backend | Admin API | Tenant list & management Module activation System user management Audit log queries Business type CRUD System health Backup management | Panel admin untuk mengelola semua tenant, modul, dan sistem | Tenant management; Module management; User management; System logs; Business type config | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin admin api agar panel admin untuk mengelola semua tenant, modul, dan sistem
127 | Phase 6 - Enterprise (W9-13) | M34 - Admin Panel (Super Admin) | Frontend | Admin Panel Pages | Admin dashboard Tenant list & detail Module management User management System log viewer Business type config System settings | Panel admin untuk mengelola semua tenant, modul, dan sistem | Tenant management; Module management; User management; System logs; Business type config | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin admin panel pages agar panel admin untuk mengelola semua tenant, modul, dan sistem
128 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Backend | Notification Service | Notification model WebSocket/SSE real-time Push notification (FCM) Email (Nodemailer) Alert subscription model Alert trigger engine Notification preferences | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin notification service agar sistem notifikasi real-time dan alerting
129 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Frontend | Notification UI | Notification bell & dropdown Notification center page Alert subscription settings Real-time toast | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin notification ui agar sistem notifikasi real-time dan alerting
130 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Mobile | Mobile Notifications | Push notification handler Notification list screen Deep linking Badge count management | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile notifications agar sistem notifikasi real-time dan alerting
131 | Phase 6 - Enterprise (W9-13) | M36 - Audit & Security | Backend | Audit & Security API | AuditLog model Auto audit trail middleware Data encryption at rest Rate limiting & throttling IP whitelist/blacklist Security event monitoring GDPR data export/delete Two-factor authentication Session management API key management | Audit trail lengkap dan keamanan sistem | Audit logging; Data encryption; RBAC enforcement; Security monitoring; GDPR compliance | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin audit & security api agar audit trail lengkap dan keamanan sistem
132 | Phase 6 - Enterprise (W9-13) | M36 - Audit & Security | Frontend | Audit & Security Pages | Audit log viewer Security dashboard User session management API key management Security settings Access report Data export (GDPR) | Audit trail lengkap dan keamanan sistem | Audit logging; Data encryption; RBAC enforcement; Security monitoring; GDPR compliance | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin audit & security pages agar audit trail lengkap dan keamanan sistem

## Backend Tasks
ID | Phase | Module | Platform | Task | Subtasks | Goal | Objectives | Story Points | Priority | Start Date | End Date | Duration (Weeks) | User Story
1 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Auth API - Register/Login/Logout | POST /api/auth/register POST /api/auth/login POST /api/auth/logout JWT token generation & refresh Password hashing (bcrypt) Email verification flow | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 8 | High | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin auth api - register/login/logout agar sistem login multi-tenant dengan role-based access control
2 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Role & Permission System | Role model (super_admin, owner, admin, manager, staff, cashier) Permission matrix CRUD Middleware auth guard Middleware role guard Middleware module access guard | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 8 | High | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin role & permission system agar sistem login multi-tenant dengan role-based access control
3 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Backend | Multi-Tenant Isolation | Tenant model & migration Tenant middleware for data isolation Tenant-aware query scoping Tenant settings API | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-03-26 | 2026-04-02 | 1 | Sebagai developer, saya ingin multi-tenant isolation agar sistem login multi-tenant dengan role-based access control
7 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Backend | Onboarding API | POST /api/onboarding/start Business type selection endpoint KYB document upload Tenant provisioning service Default data seeding | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin onboarding api agar wizard onboarding untuk tenant baru dan setup awal bisnis
8 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Backend | Subscription & Package API | Package model & CRUD Subscription lifecycle Module activation per package Trial period management | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin subscription & package api agar wizard onboarding untuk tenant baru dan setup awal bisnis
11 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Backend | Branch CRUD API | GET/POST/PUT/DELETE /api/branches Branch model & migration Branch-module activation Branch user assignment Branch metrics model | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin branch crud api agar manajemen multi-cabang dari hq dengan monitoring performa
12 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Backend | Branch Performance API | Sales aggregation per branch Inventory status per branch Employee count & schedule Comparison analytics | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai developer, saya ingin branch performance api agar manajemen multi-cabang dari hq dengan monitoring performa
16 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Backend | Settings API | Store settings CRUD Tax & fee configuration Notification settings Module toggle Integration config | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai developer, saya ingin settings api agar pengaturan global, modul, pajak, notifikasi, dan integrasi
19 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Backend | Product CRUD API | Product model & migration GET/POST/PUT/DELETE /api/products Product variant support Image upload (multer) Barcode generation Bulk import/export CSV | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-09 | 2026-04-16 | 1 | Sebagai developer, saya ingin product crud api agar master data produk, kategori, varian, dan harga
20 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Backend | Category & Pricing API | Category hierarchy CRUD Price tier model Multi-branch pricing logic HPP calculation | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai developer, saya ingin category & pricing api agar master data produk, kategori, varian, dan harga
24 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | POS Transaction API | POST /api/pos/transactions Transaction model & items Payment processing (cash, card, QRIS, e-wallet) Split payment logic Void & refund Transaction search | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai developer, saya ingin pos transaction api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
25 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | Shift & Cash Management API | Open/close shift Cash drawer tracking Shift handover report Held transaction CRUD Daily sales summary | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai developer, saya ingin shift & cash management api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
26 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Backend | Receipt & Printer API | Receipt template engine Thermal printer config Digital receipt (email/WA) Receipt reprint | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 5 | Medium | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin receipt & printer api agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
30 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Stock & Warehouse API | Stock model per branch/warehouse Stock movement logging GET /api/inventory/stock Stock adjustment Warehouse CRUD Stock transfer | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai developer, saya ingin stock & warehouse api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
31 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Stock Opname API | Stock opname session CRUD Opname item recording Variance calculation Approval workflow Opname reports | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin stock opname api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
32 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Backend | Alerts & Reorder API | Low stock threshold Alert generation Reorder point notification Stock expiry tracking Batch/lot tracking | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 5 | Medium | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin alerts & reorder api agar stok real-time, transfer antar gudang, stock opname, dan peringatan
36 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Backend | Purchase Order API | PO model & items PO CRUD PO approval workflow PO status tracking Auto-PO from reorder point | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin purchase order api agar pembelian barang, manajemen pemasok, dan penerimaan barang
37 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Backend | Supplier & Goods Receipt API | Supplier CRUD Goods receipt recording Partial receipt Receipt-to-stock integration Supplier metrics | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 5 | Medium | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin supplier & goods receipt api agar pembelian barang, manajemen pemasok, dan penerimaan barang
40 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Backend | Customer CRUD API | Customer model & migration CRUD endpoints Customer search & filter Import/export Segmentation logic Corporate customer support | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai developer, saya ingin customer crud api agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
43 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Backend | Loyalty Program API | LoyaltyProgram model Point transaction Tier calculation Reward catalog CRUD Redemption processing Point expiry | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin loyalty program api agar program poin, tier, reward, dan redemption
46 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Backend | Promo & Voucher API | Promo model & rules Bundle deal logic Voucher generation Voucher validation Promo scheduling Category/product promos | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin promo & voucher api agar sistem promosi, bundle, voucher, dan diskon otomatis
49 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Core API | CrmContact model CrmCommunication model CrmInteraction tracking CrmDocument management CrmCalendarEvent CRUD Customer 360 aggregation | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai developer, saya ingin crm core api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
50 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Tickets & Automation API | CrmTicket CRUD SLA policy engine Ticket escalation CrmAutomationRule engine Trigger-based actions CrmFollowUp scheduler | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin crm tickets & automation api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
51 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Backend | CRM Forecasting API | CrmForecast model Pipeline value calc Win probability CrmDealScore model Forecast vs actual | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin crm forecasting api agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
55 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Backend | Kitchen Order API | KitchenOrder model Order queue management Order status updates KDS integration Order priority logic | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin kitchen order api agar manajemen dapur f&b: pesanan, resep, inventori bahan
56 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Backend | Recipe & Kitchen Inventory API | Recipe CRUD with ingredients Auto-deduct stock Kitchen inventory tracking Waste recording Recipe costing | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin recipe & kitchen inventory api agar manajemen dapur f&b: pesanan, resep, inventori bahan
60 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Backend | Table & Session API | Table model CRUD Table session management Table status tracking Merge/split table Table-POS linking | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai developer, saya ingin table & session api agar manajemen meja restoran dan sistem reservasi
61 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Backend | Reservation API | Reservation CRUD Availability check Confirmation & reminder Walk-in vs reserved Cancellation policy | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin reservation api agar manajemen meja restoran dan sistem reservasi
64 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Backend | Schedule & Shift API | Shift model & templates Schedule CRUD Shift assignment engine Shift handover recording Conflict detection | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin schedule & shift api agar jadwal karyawan, shift, dan handover
67 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Employee Database API | Employee model Documents Family data Education & skills Work experience Org structure Job grade system | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin employee database api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
68 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Attendance & Devices API | AttendanceDevice model Device log ingestion Attendance calc Overtime calc Settings per branch Device integration | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai developer, saya ingin attendance & devices api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
69 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Payroll API | PayrollComponent model Salary structure Payroll run processing Tax PPh21 Payslip generation Bank file export | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 13 | Critical | 2026-05-14 | 2026-05-28 | 2 | Sebagai developer, saya ingin payroll api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
70 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Leave & Performance API | LeaveType & balance Leave request workflow Approval chain PerformanceReview model KPI template 360 feedback | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin leave & performance api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
71 | Phase 4 - Operations (W6-9) | M16 - HRIS | Backend | Recruitment & Training API | Job posting CRUD Candidate tracking Interview scheduling Training program Certification tracking Employee mutation | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin recruitment & training api agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
76 | Phase 5 - Finance & Advanced (W8-11) | M17 - Finance Lite | Backend | Finance Lite API | FinanceTransaction model Daily income aggregation Basic expense recording Daily/weekly/monthly summary Export to Excel/PDF | Ringkasan keuangan dasar: transaksi harian dan laporan sederhana | Daily transaction summary; Basic income/expense tracking | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai developer, saya ingin finance lite api agar ringkasan keuangan dasar: transaksi harian dan laporan sederhana
78 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Chart of Accounts & GL API | FinanceAccount model (CoA) Journal entry recording General ledger queries Trial balance Balance sheet Income statement (P&L) | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 13 | Critical | 2026-05-21 | 2026-06-04 | 2 | Sebagai developer, saya ingin chart of accounts & gl api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
79 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Invoice & AP/AR API | Invoice model & items Invoice from POS AR tracking & aging AP tracking & aging Payment recording Invoice email | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin invoice & ap/ar api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
80 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Backend | Budget & Cash Flow API | Budget model per dept Budget vs actual Cash flow projection Cash flow report Tax calculation Tax report | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin budget & cash flow api agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
85 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Backend | SFA Core API | SfaTeam & territory SfaVisit GPS check-in SfaLead & opportunity pipeline SfaFieldOrder CRUD SfaQuotation CRUD Coverage plan | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin sfa core api agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
86 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Backend | SFA Target & Incentive API | SfaTarget & assignment Achievement tracking Incentive scheme Commission calculation SfaPlafon (credit limit) Approval workflow | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 8 | High | 2026-05-28 | 2026-06-04 | 1 | Sebagai developer, saya ingin sfa target & incentive api agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
89 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Backend | Marketing API | MktCampaign CRUD MktCampaignChannel tracking MktSegment rules engine MktPromotion model MktBudget tracking Campaign analytics | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin marketing api agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
92 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Backend | Fleet Core API | FleetVehicle CRUD FleetDriver CRUD GPS location ingestion Geofence model & check Maintenance schedule Fuel transaction recording Inspection & incident models | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin fleet core api agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
95 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Backend | TMS API | Shipment CRUD Dispatch & assignment Tracking status Carrier model & scoring Route optimization Rate card management Zone mapping Billing integration SLA monitoring | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin tms api agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
98 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Backend | Manufacturing API | MfgWorkOrder CRUD MfgBom & BomItem MfgRouting & operations MfgWorkCenter & Machine MfgQcTemplate MfgProductionPlan MfgProductionCost MfgWasteRecord MfgShiftProduction Subcontracting COGM calculation | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai developer, saya ingin manufacturing api agar produksi: work order, bom, routing, qc, oee, waste tracking
101 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Backend | Asset Management API | Asset CRUD AssetCategory Depreciation (SL/DB/SYD) AssetMovement tracking MaintenanceSchedule AssetWorkOrder AssetLicense AssetTenancy Alert generation | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai developer, saya ingin asset management api agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
104 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Backend | Project Management API | PjmProject CRUD PjmTask CRUD PjmMilestone model PjmTimesheet recording PjmResource allocation PjmRisk model PjmBudget tracking PjmDocument management | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin project management api agar manajemen proyek: task, milestone, timesheet, risk, budget
107 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Backend | E-Procurement API | EprVendor CRUD EprProcurementRequest EprRfq & responses EprTender & bids EprContract lifecycle EprEvaluation scoring Approval workflows Analytics | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin e-procurement api agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
110 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Backend | EXIM API | EximShipment CRUD EximCustoms model EximLC (Letter of Credit) EximContainer tracking EximDocument mgmt EximPartner CRUD EximCost recording EximHsCode reference Analytics | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin exim api agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
113 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Backend | Report Engine API | Report query builder Sales aggregation Inventory aggregation Finance aggregation HR aggregation Multi-branch consolidated Export Excel/PDF/CSV Scheduled report (cron) | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai developer, saya ingin report engine api agar pusat laporan konsolidasi untuk semua modul
116 | Phase 6 - Enterprise (W9-13) | M29 - WhatsApp Business Integration | Backend | WhatsApp API Integration | WA Business API connection Message template CRUD Broadcast service Auto-reply webhook Message log & analytics Rate limiting | Integrasi WhatsApp untuk broadcast, notifikasi, dan pesan otomatis | WA API integration; Broadcast messaging; Template messages; Auto-reply | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai developer, saya ingin whatsapp api integration agar integrasi whatsapp untuk broadcast, notifikasi, dan pesan otomatis
118 | Phase 6 - Enterprise (W9-13) | M30 - Marketplace Integration | Backend | Marketplace API Integration | Marketplace adapter pattern Tokopedia API Shopee API Product sync service Order sync service Stock sync service Webhook handlers Error retry queue | Integrasi marketplace: sinkronisasi produk dan pesanan multi-channel | Tokopedia/Shopee/Lazada integration; Product sync; Order sync; Stock sync | 13 | Critical | 2026-06-11 | 2026-06-25 | 2 | Sebagai developer, saya ingin marketplace api integration agar integrasi marketplace: sinkronisasi produk dan pesanan multi-channel
120 | Phase 6 - Enterprise (W9-13) | M31 - Website Builder | Backend | Website Builder API | Page model CRUD Component/section storage Theme config Publish/unpublish Custom domain mapping SEO metadata | Pembangun website drag-drop untuk toko online sederhana | Page builder; Component library; Theme system; Publish | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin website builder api agar pembangun website drag-drop untuk toko online sederhana
122 | Phase 6 - Enterprise (W9-13) | M32 - Knowledge Base | Backend | Knowledge Base API | Article model CRUD Category organization Full-text search Article versioning Access control | Basis pengetahuan internal untuk SOP dan dokumentasi | Article CRUD; Category organization; Search; Versioning | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin knowledge base api agar basis pengetahuan internal untuk sop dan dokumentasi
124 | Phase 6 - Enterprise (W9-13) | M33 - Billing & Subscription (SaaS) | Backend | Billing API | SubscriptionPackage CRUD Subscription lifecycle BillingCycle tracking Invoice auto-generation Payment gateway (Stripe/Midtrans) Webhook payment Usage-based billing Upgrade/downgrade logic | Sistem billing SaaS: paket, subscription, invoice, payment gateway | Package management; Subscription lifecycle; Invoice generation; Payment gateway | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin billing api agar sistem billing saas: paket, subscription, invoice, payment gateway
126 | Phase 6 - Enterprise (W9-13) | M34 - Admin Panel (Super Admin) | Backend | Admin API | Tenant list & management Module activation System user management Audit log queries Business type CRUD System health Backup management | Panel admin untuk mengelola semua tenant, modul, dan sistem | Tenant management; Module management; User management; System logs; Business type config | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin admin api agar panel admin untuk mengelola semua tenant, modul, dan sistem
128 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Backend | Notification Service | Notification model WebSocket/SSE real-time Push notification (FCM) Email (Nodemailer) Alert subscription model Alert trigger engine Notification preferences | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin notification service agar sistem notifikasi real-time dan alerting
131 | Phase 6 - Enterprise (W9-13) | M36 - Audit & Security | Backend | Audit & Security API | AuditLog model Auto audit trail middleware Data encryption at rest Rate limiting & throttling IP whitelist/blacklist Security event monitoring GDPR data export/delete Two-factor authentication Session management API key management | Audit trail lengkap dan keamanan sistem | Audit logging; Data encryption; RBAC enforcement; Security monitoring; GDPR compliance | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai developer, saya ingin audit & security api agar audit trail lengkap dan keamanan sistem

## Frontend Tasks
ID | Phase | Module | Platform | Task | Subtasks | Goal | Objectives | Story Points | Priority | Start Date | End Date | Duration (Weeks) | User Story
4 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Frontend | Login & Register Pages | Login page UI Register page UI Forgot password flow OTP verification UI Auth context/provider | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-03-26 | 2026-04-02 | 1 | Sebagai pengguna, saya ingin login & register pages agar sistem login multi-tenant dengan role-based access control
5 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Frontend | Auth Guards & Layout | Protected route wrapper Role-based route guard Layout with sidebar (HQ/Branch/Admin) Sidebar config integration User profile dropdown | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin auth guards & layout agar sistem login multi-tenant dengan role-based access control
9 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Frontend | Onboarding Wizard UI | Step 1: Business info Step 2: Business type Step 3: KYB upload Step 4: Branch setup Step 5: Admin user Progress indicator | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin onboarding wizard ui agar wizard onboarding untuk tenant baru dan setup awal bisnis
13 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Frontend | Branch List & Detail Pages | Branch list with filters Branch detail page Branch creation form Branch settings page Branch performance dashboard | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 8 | High | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna, saya ingin branch list & detail pages agar manajemen multi-cabang dari hq dengan monitoring performa
14 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Frontend | Branch Performance Charts | Revenue comparison chart Branch ranking Branch map view (Leaflet) Real-time metrics cards | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna, saya ingin branch performance charts agar manajemen multi-cabang dari hq dengan monitoring performa
17 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Frontend | Settings Pages | Global settings page Module management Tax & fee settings Notification preferences Integration settings | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 5 | Medium | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna, saya ingin settings pages agar pengaturan global, modul, pajak, notifikasi, dan integrasi
21 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Frontend | Product Management Pages | Product list grid/list view Product create/edit form Variant builder UI Image upload with crop Barcode scanner Bulk import UI | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 8 | High | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna, saya ingin product management pages agar master data produk, kategori, varian, dan harga
22 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Frontend | Category & Pricing Pages | Category tree view Drag-drop reorder Price tier management Branch-specific pricing UI | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 5 | Medium | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna, saya ingin category & pricing pages agar master data produk, kategori, varian, dan harga
27 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Frontend | POS Cashier Interface | POS main screen Product grid + categories Cart management Quantity & discount Customer selection Barcode scanner Payment modal Split bill UI Receipt preview & print | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-16 | 2026-04-30 | 2 | Sebagai pengguna, saya ingin pos cashier interface agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
28 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Frontend | Shift & Transaction History | Shift open/close dialogs Cash count form Shift summary Transaction history Transaction detail & reprint Held transactions list | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin shift & transaction history agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
33 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Frontend | Inventory Dashboard & Stock Pages | Inventory dashboard KPIs Stock list with filters Stock detail & history Stock adjustment form Transfer request form Multi-warehouse view | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin inventory dashboard & stock pages agar stok real-time, transfer antar gudang, stock opname, dan peringatan
34 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Frontend | Stock Opname UI | Start opname wizard Item count entry Variance review Approval flow UI Opname history | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-23 | 2026-04-30 | 1 | Sebagai pengguna, saya ingin stock opname ui agar stok real-time, transfer antar gudang, stock opname, dan peringatan
38 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Frontend | Purchase Order Pages | PO list & filter PO creation wizard PO approval screen PO detail & timeline Supplier list Goods receipt form | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin purchase order pages agar pembelian barang, manajemen pemasok, dan penerimaan barang
41 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Frontend | Customer Management Pages | Customer list Customer detail 360 view Add customer wizard Edit form Transaction history Segmentation UI Corporate form | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin customer management pages agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
44 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Frontend | Loyalty Program Pages | Loyalty dashboard Program config Tier management Reward catalog Redemption history Member analytics | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna, saya ingin loyalty program pages agar program poin, tier, reward, dan redemption
47 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Frontend | Promo & Voucher Pages | Promo list & wizard Bundle builder Voucher generator Promo analytics Promo calendar | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin promo & voucher pages agar sistem promosi, bundle, voucher, dan diskon otomatis
52 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Frontend | CRM Dashboard & Contact Pages | CRM dashboard pipeline Contact list & 360 Communication timeline Calendar & task integration Document management UI | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin crm dashboard & contact pages agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
53 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Frontend | CRM Tickets & Automation UI | Ticket kanban Ticket detail & comments SLA config Automation rule builder Follow-up scheduler | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin crm tickets & automation ui agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
57 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Frontend | Kitchen Display System (KDS) | KDS board layout Order cards with timers Status update buttons Sound/visual alerts Multi-station view | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 8 | High | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna, saya ingin kitchen display system (kds) agar manajemen dapur f&b: pesanan, resep, inventori bahan
58 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Frontend | Recipe & Kitchen Settings | Recipe editor Ingredient mapping Kitchen inventory page Staff assignment Kitchen settings | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin recipe & kitchen settings agar manajemen dapur f&b: pesanan, resep, inventori bahan
62 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Frontend | Table Layout & Reservation UI | Drag-drop table layout Real-time table map Table session view Reservation calendar Reservation form Waitlist management | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin table layout & reservation ui agar manajemen meja restoran dan sistem reservasi
65 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Frontend | Schedule & Shift Pages | Schedule calendar (FullCalendar) Shift template builder Drag-drop assignment Shift handover form Schedule export | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin schedule & shift pages agar jadwal karyawan, shift, dan handover
72 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | HRIS Dashboard & Employee Pages | HRIS dashboard Employee list & detail Create/edit wizard Org chart Document mgmt Lifecycle timeline | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna, saya ingin hris dashboard & employee pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
73 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | Attendance & Payroll Pages | Attendance dashboard Daily log Device management Payroll run wizard Payslip viewer Salary structure editor | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin attendance & payroll pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
74 | Phase 4 - Operations (W6-9) | M16 - HRIS | Frontend | Leave, KPI & Recruitment Pages | Leave calendar Leave request form Leave approval KPI dashboard KPI scoring Performance review Recruitment pipeline Training catalog | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin leave, kpi & recruitment pages agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
77 | Phase 5 - Finance & Advanced (W8-11) | M17 - Finance Lite | Frontend | Finance Lite Pages | Transaction list Daily summary dashboard Income/expense chart Export buttons | Ringkasan keuangan dasar: transaksi harian dan laporan sederhana | Daily transaction summary; Basic income/expense tracking | 5 | Medium | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna, saya ingin finance lite pages agar ringkasan keuangan dasar: transaksi harian dan laporan sederhana
81 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Finance Dashboard & GL Pages | Finance dashboard KPIs Chart of Accounts page Journal entry form GL view Trial balance report P&L report Balance sheet report | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai pengguna, saya ingin finance dashboard & gl pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
82 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Invoice & AP/AR Pages | Invoice list & detail Invoice creation AR aging report AP aging report Payment recording Invoice PDF preview | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin invoice & ap/ar pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
83 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Frontend | Budget & Tax Pages | Budget planning page Budget vs actual chart Cash flow report Tax summary Financial ratio analysis | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 5 | Medium | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin budget & tax pages agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
87 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Frontend | SFA Dashboard & Pages | SFA dashboard Visit map & list Lead pipeline kanban Field order mgmt Quotation builder Territory mgmt Target tracking Incentive view Survey & competitor | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-05-28 | 2026-06-11 | 2 | Sebagai pengguna, saya ingin sfa dashboard & pages agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
90 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Frontend | Marketing Pages | Marketing dashboard Campaign builder wizard Segment builder Promotion management Budget allocation Campaign analytics | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 8 | High | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin marketing pages agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
93 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Frontend | Fleet Dashboard & Pages | Fleet dashboard Vehicle list & detail Driver list & assignment GPS live map (Leaflet) Geofence editor Maintenance calendar Fuel log & analytics Inspection forms Incident reports Cost analytics | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin fleet dashboard & pages agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
96 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Frontend | TMS Dashboard & Pages | TMS dashboard Shipment list & tracking Dispatch board Carrier management Route planner Rate card editor Zone management SLA dashboard Logistics KPI | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna, saya ingin tms dashboard & pages agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
99 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Frontend | Manufacturing Pages | Manufacturing dashboard Work order list BOM builder Routing editor Work center mgmt Machine registry QC inspection forms Production planning calendar OEE analytics Cost analysis Waste tracking PLM | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin manufacturing pages agar produksi: work order, bom, routing, qc, oee, waste tracking
102 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Frontend | Asset Management Pages | Asset dashboard Asset registry Asset detail & history Depreciation report Maintenance calendar Work order mgmt License tracking Movement log Settings | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin asset management pages agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
105 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Frontend | Project Management Pages | Project dashboard Project list & detail Task kanban board Gantt chart view Milestone timeline Timesheet entry Resource allocation Risk register Budget tracking Document repository | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin project management pages agar manajemen proyek: task, milestone, timesheet, risk, budget
108 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Frontend | E-Procurement Pages | E-Procurement dashboard Vendor registry Procurement request form RFQ builder Tender management Contract management Vendor evaluation Analytics & reports | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna, saya ingin e-procurement pages agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
111 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Frontend | EXIM Pages | EXIM dashboard Shipment list & detail Customs management L/C tracking Container tracking Document mgmt Partner registry Cost analysis HS code search Analytics | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin exim pages agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
114 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Frontend | Report Hub & Pages | Report hub dashboard Sales report page Inventory report Finance report Customer report HR report Procurement report Custom data analysis Chart & pivot builder Export & schedule UI | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 13 | Critical | 2026-06-04 | 2026-06-18 | 2 | Sebagai pengguna, saya ingin report hub & pages agar pusat laporan konsolidasi untuk semua modul
117 | Phase 6 - Enterprise (W9-13) | M29 - WhatsApp Business Integration | Frontend | WhatsApp Management Pages | WA dashboard Template editor Broadcast builder Message analytics Settings & connection | Integrasi WhatsApp untuk broadcast, notifikasi, dan pesan otomatis | WA API integration; Broadcast messaging; Template messages; Auto-reply | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin whatsapp management pages agar integrasi whatsapp untuk broadcast, notifikasi, dan pesan otomatis
119 | Phase 6 - Enterprise (W9-13) | M30 - Marketplace Integration | Frontend | Marketplace Pages | Marketplace dashboard Channel connection wizard Product mapping UI Order list multi-channel Stock sync status Settings | Integrasi marketplace: sinkronisasi produk dan pesanan multi-channel | Tokopedia/Shopee/Lazada integration; Product sync; Order sync; Stock sync | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin marketplace pages agar integrasi marketplace: sinkronisasi produk dan pesanan multi-channel
121 | Phase 6 - Enterprise (W9-13) | M31 - Website Builder | Frontend | Website Builder Editor | Drag-drop page editor Component palette Theme customizer Preview mode Publish flow Page list management | Pembangun website drag-drop untuk toko online sederhana | Page builder; Component library; Theme system; Publish | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin website builder editor agar pembangun website drag-drop untuk toko online sederhana
123 | Phase 6 - Enterprise (W9-13) | M32 - Knowledge Base | Frontend | Knowledge Base Pages | Article list & search Article editor (rich text) Category navigation Version history | Basis pengetahuan internal untuk SOP dan dokumentasi | Article CRUD; Category organization; Search; Versioning | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin knowledge base pages agar basis pengetahuan internal untuk sop dan dokumentasi
125 | Phase 6 - Enterprise (W9-13) | M33 - Billing & Subscription (SaaS) | Frontend | Billing Pages | Pricing page Subscription management Invoice list & detail Payment history Upgrade/downgrade flow Usage analytics | Sistem billing SaaS: paket, subscription, invoice, payment gateway | Package management; Subscription lifecycle; Invoice generation; Payment gateway | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin billing pages agar sistem billing saas: paket, subscription, invoice, payment gateway
127 | Phase 6 - Enterprise (W9-13) | M34 - Admin Panel (Super Admin) | Frontend | Admin Panel Pages | Admin dashboard Tenant list & detail Module management User management System log viewer Business type config System settings | Panel admin untuk mengelola semua tenant, modul, dan sistem | Tenant management; Module management; User management; System logs; Business type config | 8 | High | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin admin panel pages agar panel admin untuk mengelola semua tenant, modul, dan sistem
129 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Frontend | Notification UI | Notification bell & dropdown Notification center page Alert subscription settings Real-time toast | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin notification ui agar sistem notifikasi real-time dan alerting
132 | Phase 6 - Enterprise (W9-13) | M36 - Audit & Security | Frontend | Audit & Security Pages | Audit log viewer Security dashboard User session management API key management Security settings Access report Data export (GDPR) | Audit trail lengkap dan keamanan sistem | Audit logging; Data encryption; RBAC enforcement; Security monitoring; GDPR compliance | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna, saya ingin audit & security pages agar audit trail lengkap dan keamanan sistem

## Mobile Tasks
ID | Phase | Module | Platform | Task | Subtasks | Goal | Objectives | Story Points | Priority | Start Date | End Date | Duration (Weeks) | User Story
6 | Phase 1 - Foundation (W1-3) | M01 - Authentication & Authorization | Mobile | Mobile Auth Flow | Login screen Biometric auth (fingerprint/face) Token storage (secure) Auto-refresh token Push notification token registration | Sistem login multi-tenant dengan role-based access control | JWT auth flow; Multi-tenant isolation; Role & permission matrix; Session management | 5 | Medium | 2026-04-02 | 2026-04-09 | 1 | Sebagai pengguna mobile, saya ingin mobile auth flow agar sistem login multi-tenant dengan role-based access control
10 | Phase 1 - Foundation (W1-3) | M02 - Onboarding & Tenant Setup | Mobile | Mobile Onboarding | Onboarding welcome screens Business setup wizard Initial sync | Wizard onboarding untuk tenant baru dan setup awal bisnis | KYB application flow; Business type selection; Initial branch & user setup | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin mobile onboarding agar wizard onboarding untuk tenant baru dan setup awal bisnis
15 | Phase 1 - Foundation (W1-3) | M03 - Branch Management | Mobile | Branch Switcher (Mobile) | Branch selector Branch dashboard summary Quick performance view | Manajemen multi-cabang dari HQ dengan monitoring performa | CRUD cabang; Performance dashboard per branch; Branch settings; Real-time metrics | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin branch switcher (mobile) agar manajemen multi-cabang dari hq dengan monitoring performa
18 | Phase 1 - Foundation (W1-3) | M04 - Settings & Configuration | Mobile | Mobile Settings | App preferences Notification toggle Printer/device settings | Pengaturan global, modul, pajak, notifikasi, dan integrasi | Global settings; Module management; Tax configuration; Notification settings | 3 | Low | 2026-04-09 | 2026-04-16 | 1 | Sebagai pengguna mobile, saya ingin mobile settings agar pengaturan global, modul, pajak, notifikasi, dan integrasi
23 | Phase 2 - Core Commerce (W3-6) | M05 - Product & Category Management | Mobile | Mobile Product Catalog | Product list & search Product detail view Barcode scan Quick price check | Master data produk, kategori, varian, dan harga | Product CRUD with variants; Category hierarchy; Price tiers; Barcode support | 5 | Medium | 2026-04-16 | 2026-04-23 | 1 | Sebagai pengguna mobile, saya ingin mobile product catalog agar master data produk, kategori, varian, dan harga
29 | Phase 2 - Core Commerce (W3-6) | M06 - Point of Sale (POS) | Mobile | Mobile POS | Mobile POS interface Product search & scan Cart management Payment processing Bluetooth printer Offline queue Sync when online | Sistem kasir lengkap dengan multi-payment, split bill, dan struk | Full POS flow; Multi-payment; Receipt printing; Held transactions; Shift management | 13 | Critical | 2026-04-23 | 2026-05-07 | 2 | Sebagai pengguna mobile, saya ingin mobile pos agar sistem kasir lengkap dengan multi-payment, split bill, dan struk
35 | Phase 2 - Core Commerce (W3-6) | M07 - Inventory Management | Mobile | Mobile Stock Management | Stock check by scan Mobile stock opname Stock transfer request Low stock alert push Stock receive confirmation | Stok real-time, transfer antar gudang, stock opname, dan peringatan | Real-time stock; Stock movements; Stock opname; Multi-warehouse; Low stock alerts | 8 | High | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile stock management agar stok real-time, transfer antar gudang, stock opname, dan peringatan
39 | Phase 2 - Core Commerce (W3-6) | M08 - Purchase Orders & Suppliers | Mobile | Mobile Goods Receipt | Scan PO barcode Item count confirmation Photo proof Receipt signature capture | Pembelian barang, manajemen pemasok, dan penerimaan barang | PO lifecycle; Supplier management; Goods receipt; PO approval | 5 | Medium | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile goods receipt agar pembelian barang, manajemen pemasok, dan penerimaan barang
42 | Phase 3 - Customer & Engagement (W5-7) | M09 - Customer Management | Mobile | Mobile Customer Lookup | Customer search Quick add customer Customer card view Link to POS transaction | Database pelanggan lengkap dengan segmentasi dan riwayat transaksi | Customer CRUD; Segmentation & tags; Transaction history; Corporate customers | 3 | Low | 2026-04-30 | 2026-05-07 | 1 | Sebagai pengguna mobile, saya ingin mobile customer lookup agar database pelanggan lengkap dengan segmentasi dan riwayat transaksi
45 | Phase 3 - Customer & Engagement (W5-7) | M10 - Loyalty Program | Mobile | Mobile Loyalty | Loyalty card view Point balance Available rewards Redeem from mobile Digital membership | Program poin, tier, reward, dan redemption | Point accumulation; Tier system; Reward catalog; Redemption flow | 5 | Medium | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna mobile, saya ingin mobile loyalty agar program poin, tier, reward, dan redemption
48 | Phase 3 - Customer & Engagement (W5-7) | M11 - Promo & Voucher | Mobile | Mobile Promo Display | Active promo list Voucher scanner Apply promo in cart Push notification promos | Sistem promosi, bundle, voucher, dan diskon otomatis | Promo engine; Bundle deals; Voucher generation; Auto-discount rules | 3 | Low | 2026-05-07 | 2026-05-14 | 1 | Sebagai pengguna mobile, saya ingin mobile promo display agar sistem promosi, bundle, voucher, dan diskon otomatis
54 | Phase 3 - Customer & Engagement (W5-7) | M12 - CRM | Mobile | Mobile CRM | Contact list Quick log interaction Ticket view Follow-up reminders | CRM 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan | Contact management; Communication tracking; Support tickets & SLA; Sales forecasting | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile crm agar crm 360 dengan komunikasi, tiket, otomasi, dan peramalan penjualan
59 | Phase 4 - Operations (W6-9) | M13 - Kitchen Management | Mobile | Mobile KDS | Mobile kitchen display Order status quick update Alert on new orders | Manajemen dapur F&B: pesanan, resep, inventori bahan | Kitchen order display; Recipe management; Kitchen inventory; Staff assignment | 3 | Low | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile kds agar manajemen dapur f&b: pesanan, resep, inventori bahan
63 | Phase 4 - Operations (W6-9) | M14 - Table & Reservation | Mobile | Mobile Table/Reservation | Table status overview Quick seat assignment Reservation lookup | Manajemen meja restoran dan sistem reservasi | Table layout; Table sessions; Reservation booking; Table-POS integration | 3 | Low | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile table/reservation agar manajemen meja restoran dan sistem reservasi
66 | Phase 4 - Operations (W6-9) | M15 - Employee & Schedule | Mobile | Mobile Schedule View | My schedule view Shift swap request Clock in/out Handover checklist | Jadwal karyawan, shift, dan handover | Shift templates; Schedule builder; Shift handover; Attendance basic | 5 | Medium | 2026-05-14 | 2026-05-21 | 1 | Sebagai pengguna mobile, saya ingin mobile schedule view agar jadwal karyawan, shift, dan handover
75 | Phase 4 - Operations (W6-9) | M16 - HRIS | Mobile | Mobile HRIS (ESS) | My profile Clock in/out GPS Leave request Payslip viewer KPI & goals Training schedule Claim submission Travel request | Sistem HR lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen | Employee database; Attendance; Payroll; Leave management; Performance review; Recruitment | 8 | High | 2026-05-21 | 2026-05-28 | 1 | Sebagai pengguna mobile, saya ingin mobile hris (ess) agar sistem hr lengkap: kehadiran, penggajian, cuti, kinerja, rekrutmen
84 | Phase 5 - Finance & Advanced (W8-11) | M18 - Finance Pro (Full Accounting) | Mobile | Mobile Finance | Daily revenue summary Expense quick entry Invoice approval Cash flow overview | Akuntansi lengkap: GL, AP/AR, invoicing, anggaran, arus kas, pajak | Chart of Accounts; General Ledger; AP & AR; Invoicing; Budget; Cash flow; Tax | 3 | Low | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile finance agar akuntansi lengkap: gl, ap/ar, invoicing, anggaran, arus kas, pajak
88 | Phase 5 - Finance & Advanced (W8-11) | M19 - SFA (Sales Force Automation) | Mobile | Mobile SFA | GPS check-in visits Photo proof upload Quick field order Route plan view Target dashboard Visit history Offline mode + sync | Otomasi tenaga penjualan: kunjungan, target, insentif, pipeline | Visit tracking; Target & achievement; Incentive calculation; Field order; Territory management | 13 | Critical | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile sfa agar otomasi tenaga penjualan: kunjungan, target, insentif, pipeline
91 | Phase 5 - Finance & Advanced (W8-11) | M20 - Marketing & Campaigns | Mobile | Mobile Marketing | Campaign overview Quick promotion setup Push notification to customers | Kampanye pemasaran, segmentasi, promosi, dan anggaran marketing | Campaign management; Customer segmentation; Promotion engine; Marketing budget | 3 | Low | 2026-06-04 | 2026-06-11 | 1 | Sebagai pengguna mobile, saya ingin mobile marketing agar kampanye pemasaran, segmentasi, promosi, dan anggaran marketing
94 | Phase 6 - Enterprise (W9-13) | M21 - Fleet Management (FMS) | Mobile | Mobile Fleet (Driver App) | Driver check-in/out GPS tracking background Fuel entry form Vehicle inspection checklist Incident report with photos Route navigation | Manajemen armada kendaraan: tracking, maintenance, BBM, inspeksi | Vehicle registry; Driver management; GPS tracking; Maintenance; Fuel tracking; Geofencing | 8 | High | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile fleet (driver app) agar manajemen armada kendaraan: tracking, maintenance, bbm, inspeksi
97 | Phase 6 - Enterprise (W9-13) | M22 - Transportation Management (TMS) | Mobile | Mobile TMS (Driver) | Delivery task list GPS tracking & proof of delivery Signature capture Photo upload Status updates | Manajemen pengiriman, dispatch, pelacakan, dan carrier management | Shipment management; Dispatch planning; Carrier scorecards; Delivery SLA; Rate cards | 5 | Medium | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile tms (driver) agar manajemen pengiriman, dispatch, pelacakan, dan carrier management
100 | Phase 6 - Enterprise (W9-13) | M23 - Manufacturing | Mobile | Mobile Manufacturing | Work order task view QC inspection mobile Production count entry Machine status update Waste recording | Produksi: work order, BOM, routing, QC, OEE, waste tracking | Work order management; BOM & routing; Quality control; OEE analytics; Production planning | 5 | Medium | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile manufacturing agar produksi: work order, bom, routing, qc, oee, waste tracking
103 | Phase 6 - Enterprise (W9-13) | M24 - Asset Management | Mobile | Mobile Asset | Asset scan (barcode/QR) Asset inspection form Maintenance request Asset transfer request | Pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi | Asset registry; Depreciation; Maintenance work orders; Software licenses; Asset movements | 3 | Low | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile asset agar pengelolaan aset: registry, penyusutan, pemeliharaan, lisensi
106 | Phase 6 - Enterprise (W9-13) | M25 - Project Management | Mobile | Mobile Project | Task list & update Time logging Milestone notifications Document viewer | Manajemen proyek: task, milestone, timesheet, risk, budget | Project CRUD; Task board (Kanban); Milestone tracking; Timesheet; Resource allocation; Risk management | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile project agar manajemen proyek: task, milestone, timesheet, risk, budget
109 | Phase 6 - Enterprise (W9-13) | M26 - E-Procurement | Mobile | Mobile E-Procurement | Approval from mobile Vendor lookup RFQ review | Pengadaan elektronik: vendor, RFQ, tender, kontrak, evaluasi | Vendor management; RFQ process; Tender management; Contract lifecycle; Vendor evaluation | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile e-procurement agar pengadaan elektronik: vendor, rfq, tender, kontrak, evaluasi
112 | Phase 6 - Enterprise (W9-13) | M27 - Export/Import (EXIM) | Mobile | Mobile EXIM | Shipment status tracker Document viewer Cost entry | Manajemen ekspor-impor: pengiriman, kepabeanan, L/C, dokumen | Shipment tracking; Customs management; Letter of Credit; HS code; Cost tracking | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile exim agar manajemen ekspor-impor: pengiriman, kepabeanan, l/c, dokumen
115 | Phase 6 - Enterprise (W9-13) | M28 - Reports & Analytics | Mobile | Mobile Reports | Key metric dashboard Quick report viewer Share report via mobile | Pusat laporan konsolidasi untuk semua modul | Sales reports; Inventory reports; Finance reports; HR reports; Custom report builder | 3 | Low | 2026-06-11 | 2026-06-18 | 1 | Sebagai pengguna mobile, saya ingin mobile reports agar pusat laporan konsolidasi untuk semua modul
130 | Phase 6 - Enterprise (W9-13) | M35 - Notifications & Alerts | Mobile | Mobile Notifications | Push notification handler Notification list screen Deep linking Badge count management | Sistem notifikasi real-time dan alerting | In-app notifications; Push notifications; Email notifications; Alert subscriptions | 3 | Low | 2026-06-18 | 2026-06-25 | 1 | Sebagai pengguna mobile, saya ingin mobile notifications agar sistem notifikasi real-time dan alerting

## Gantt Chart
# | Task | Platform | W1 03-26 | W2 04-02 | W3 04-09 | W4 04-16 | W5 04-23 | W6 04-30 | W7 05-07 | W8 05-14 | W9 05-21 | W10 05-28 | W11 06-04 | W12 06-11 | W13 06-18
1 | Auth API - Register/Login/Logout | Backend | 8
2 | Role & Permission System | Backend | 8
3 | Multi-Tenant Isolation | Backend | 5
4 | Login & Register Pages | Frontend | 5
5 | Auth Guards & Layout | Frontend |  | 5
6 | Mobile Auth Flow | Mobile |  | 5
7 | Onboarding API | Backend |  | 8
8 | Subscription & Package API | Backend |  | 5
9 | Onboarding Wizard UI | Frontend |  | 8
10 | Mobile Onboarding | Mobile |  |  | 3
11 | Branch CRUD API | Backend |  | 8
12 | Branch Performance API | Backend |  | 5
13 | Branch List & Detail Pages | Frontend |  | 8
14 | Branch Performance Charts | Frontend |  |  | 5
15 | Branch Switcher (Mobile) | Mobile |  |  | 3
16 | Settings API | Backend |  |  | 5
17 | Settings Pages | Frontend |  |  | 5
18 | Mobile Settings | Mobile |  |  | 3
19 | Product CRUD API | Backend |  |  | 8
20 | Category & Pricing API | Backend |  |  |  | 8
21 | Product Management Pages | Frontend |  |  |  | 8
22 | Category & Pricing Pages | Frontend |  |  |  | 5
23 | Mobile Product Catalog | Mobile |  |  |  | 5
24 | POS Transaction API | Backend |  |  |  | 13 | 13
25 | Shift & Cash Management API | Backend |  |  |  | 8
26 | Receipt & Printer API | Backend |  |  |  |  | 5
27 | POS Cashier Interface | Frontend |  |  |  | 13 | 13
28 | Shift & Transaction History | Frontend |  |  |  |  | 8
29 | Mobile POS | Mobile |  |  |  |  | 13 | 13
30 | Stock & Warehouse API | Backend |  |  |  | 13 | 13
31 | Stock Opname API | Backend |  |  |  |  | 8
32 | Alerts & Reorder API | Backend |  |  |  |  | 5
33 | Inventory Dashboard & Stock Pages | Frontend |  |  |  |  | 8
34 | Stock Opname UI | Frontend |  |  |  |  | 8
35 | Mobile Stock Management | Mobile | [5 empty] | 8
36 | Purchase Order API | Backend |  |  |  |  | 8
37 | Supplier & Goods Receipt API | Backend | [5 empty] | 5
38 | Purchase Order Pages | Frontend | [5 empty] | 8
39 | Mobile Goods Receipt | Mobile | [5 empty] | 5
40 | Customer CRUD API | Backend |  |  |  |  | 8
41 | Customer Management Pages | Frontend | [5 empty] | 8
42 | Mobile Customer Lookup | Mobile | [5 empty] | 3
43 | Loyalty Program API | Backend | [5 empty] | 8
44 | Loyalty Program Pages | Frontend | [5 empty] | 8
45 | Mobile Loyalty | Mobile | [6 empty] | 5
46 | Promo & Voucher API | Backend | [5 empty] | 8
47 | Promo & Voucher Pages | Frontend | [6 empty] | 8
48 | Mobile Promo Display | Mobile | [6 empty] | 3
49 | CRM Core API | Backend | [5 empty] | 8
50 | CRM Tickets & Automation API | Backend | [6 empty] | 8
51 | CRM Forecasting API | Backend | [6 empty] | 5
52 | CRM Dashboard & Contact Pages | Frontend | [6 empty] | 8
53 | CRM Tickets & Automation UI | Frontend | [6 empty] | 8
54 | Mobile CRM | Mobile | [7 empty] | 5
55 | Kitchen Order API | Backend | [6 empty] | 8
56 | Recipe & Kitchen Inventory API | Backend | [6 empty] | 8
57 | Kitchen Display System (KDS) | Frontend | [6 empty] | 8
58 | Recipe & Kitchen Settings | Frontend | [7 empty] | 5
59 | Mobile KDS | Mobile | [7 empty] | 3
60 | Table & Session API | Backend | [6 empty] | 5
61 | Reservation API | Backend | [7 empty] | 5
62 | Table Layout & Reservation UI | Frontend | [7 empty] | 8
63 | Mobile Table/Reservation | Mobile | [7 empty] | 3
64 | Schedule & Shift API | Backend | [7 empty] | 5
65 | Schedule & Shift Pages | Frontend | [7 empty] | 8
66 | Mobile Schedule View | Mobile | [7 empty] | 5
67 | Employee Database API | Backend | [7 empty] | 8
68 | Attendance & Devices API | Backend | [7 empty] | 8
69 | Payroll API | Backend | [7 empty] | 13 | 13
70 | Leave & Performance API | Backend | [8 empty] | 8
71 | Recruitment & Training API | Backend | [8 empty] | 5
72 | HRIS Dashboard & Employee Pages | Frontend | [7 empty] | 8
73 | Attendance & Payroll Pages | Frontend | [8 empty] | 8
74 | Leave, KPI & Recruitment Pages | Frontend | [8 empty] | 8
75 | Mobile HRIS (ESS) | Mobile | [8 empty] | 8
76 | Finance Lite API | Backend | [8 empty] | 5
77 | Finance Lite Pages | Frontend | [8 empty] | 5
78 | Chart of Accounts & GL API | Backend | [8 empty] | 13 | 13
79 | Invoice & AP/AR API | Backend | [9 empty] | 8
80 | Budget & Cash Flow API | Backend | [9 empty] | 8
81 | Finance Dashboard & GL Pages | Frontend | [9 empty] | 13 | 13
82 | Invoice & AP/AR Pages | Frontend | [10 empty] | 8
83 | Budget & Tax Pages | Frontend | [10 empty] | 5
84 | Mobile Finance | Mobile | [10 empty] | 3
85 | SFA Core API | Backend | [9 empty] | 13 | 13
86 | SFA Target & Incentive API | Backend | [9 empty] | 8
87 | SFA Dashboard & Pages | Frontend | [9 empty] | 13 | 13
88 | Mobile SFA | Mobile | [10 empty] | 13
89 | Marketing API | Backend | [10 empty] | 8
90 | Marketing Pages | Frontend | [10 empty] | 8
91 | Mobile Marketing | Mobile | [10 empty] | 3
92 | Fleet Core API | Backend | [9 empty] | 13 | 13
93 | Fleet Dashboard & Pages | Frontend | [10 empty] | 13 | 13
94 | Mobile Fleet (Driver App) | Mobile | [11 empty] | 8
95 | TMS API | Backend | [10 empty] | 13
96 | TMS Dashboard & Pages | Frontend | [10 empty] | 13
97 | Mobile TMS (Driver) | Mobile | [11 empty] | 5
98 | Manufacturing API | Backend | [10 empty] | 13 | 13
99 | Manufacturing Pages | Frontend | [10 empty] | 13 | 13
100 | Mobile Manufacturing | Mobile | [12 empty] | 5
101 | Asset Management API | Backend | [10 empty] | 8
102 | Asset Management Pages | Frontend | [11 empty] | 8
103 | Mobile Asset | Mobile | [11 empty] | 3
104 | Project Management API | Backend | [11 empty] | 8
105 | Project Management Pages | Frontend | [11 empty] | 8
106 | Mobile Project | Mobile | [12 empty] | 3
107 | E-Procurement API | Backend | [11 empty] | 8
108 | E-Procurement Pages | Frontend | [11 empty] | 8
109 | Mobile E-Procurement | Mobile | [12 empty] | 3
110 | EXIM API | Backend | [11 empty] | 8
111 | EXIM Pages | Frontend | [12 empty] | 8
112 | Mobile EXIM | Mobile | [12 empty] | 3
113 | Report Engine API | Backend | [9 empty] | 13 | 13
114 | Report Hub & Pages | Frontend | [10 empty] | 13 | 13
115 | Mobile Reports | Mobile | [11 empty] | 3
116 | WhatsApp API Integration | Backend | [11 empty] | 8
117 | WhatsApp Management Pages | Frontend | [12 empty] | 5
118 | Marketplace API Integration | Backend | [11 empty] | 13 | 13
119 | Marketplace Pages | Frontend | [12 empty] | 8
120 | Website Builder API | Backend | [12 empty] | 5
121 | Website Builder Editor | Frontend | [12 empty] | 8
122 | Knowledge Base API | Backend | [12 empty] | 3
123 | Knowledge Base Pages | Frontend | [12 empty] | 3
124 | Billing API | Backend | [12 empty] | 8
125 | Billing Pages | Frontend | [12 empty] | 5
126 | Admin API | Backend | [12 empty] | 8
127 | Admin Panel Pages | Frontend | [12 empty] | 8
128 | Notification Service | Backend | [12 empty] | 8
129 | Notification UI | Frontend | [12 empty] | 3
130 | Mobile Notifications | Mobile | [12 empty] | 3
131 | Audit & Security API | Backend | [12 empty] | 8
132 | Audit & Security Pages | Frontend | [12 empty] | 5
| LEGEND: |  | Backend |  | Frontend |  | Mobile

## Summary
PROJECT SUMMARY - 3 BULAN AGRESIF
Metric | Backend | Frontend | Mobile | Total
Task Count | 57 | 47 | 28 | 132
Story Points | 459 | 368 | 135 | 962
Critical Tasks | 10 | 7 | 2 | 19
High Priority Tasks | 32 | 27 | 3 | 62
Module | Tasks | Story Points | Start Week | End Week
M01 - Authentication & Authorization | 6 | 36 | W1 | W2
M02 - Onboarding & Tenant Setup | 4 | 24 | W2 | W3
M03 - Branch Management | 5 | 29 | W2 | W3
M04 - Settings & Configuration | 3 | 13 | W3 | W3
M05 - Product & Category Management | 5 | 34 | W3 | W4
M06 - Point of Sale (POS) | 6 | 60 | W4 | W6
M07 - Inventory Management | 6 | 50 | W4 | W6
M08 - Purchase Orders & Suppliers | 4 | 26 | W5 | W6
M09 - Customer Management | 3 | 19 | W5 | W6
M10 - Loyalty Program | 3 | 21 | W6 | W7
M11 - Promo & Voucher | 3 | 19 | W6 | W7
M12 - CRM | 6 | 42 | W6 | W8
M13 - Kitchen Management | 5 | 32 | W7 | W8
M14 - Table & Reservation | 4 | 21 | W7 | W8
M15 - Employee & Schedule | 3 | 18 | W8 | W8
M16 - HRIS | 9 | 74 | W8 | W9
M17 - Finance Lite | 2 | 10 | W9 | W9
M18 - Finance Pro (Full Accounting) | 7 | 58 | W9 | W11
M19 - SFA (Sales Force Automation) | 4 | 47 | W10 | W11
M20 - Marketing & Campaigns | 3 | 19 | W11 | W11
M21 - Fleet Management (FMS) | 3 | 34 | W10 | W12
M22 - Transportation Management (TMS) | 3 | 31 | W11 | W12
M23 - Manufacturing | 3 | 31 | W11 | W13
M24 - Asset Management | 3 | 19 | W11 | W12
M25 - Project Management | 3 | 19 | W12 | W13
M26 - E-Procurement | 3 | 19 | W12 | W13
M27 - Export/Import (EXIM) | 3 | 19 | W12 | W13
M28 - Reports & Analytics | 3 | 29 | W10 | W12
M29 - WhatsApp Business Integration | 2 | 13 | W12 | W13
M30 - Marketplace Integration | 2 | 21 | W12 | W13
M31 - Website Builder | 2 | 13 | W13 | W13
M32 - Knowledge Base | 2 | 6 | W13 | W13
M33 - Billing & Subscription (SaaS) | 2 | 13 | W13 | W13
M34 - Admin Panel (Super Admin) | 2 | 16 | W13 | W13
M35 - Notifications & Alerts | 3 | 14 | W13 | W13
M36 - Audit & Security | 2 | 13 | W13 | W13
TEAM RECOMMENDATION (3-Month Aggressive)
Role | Count | Skills
Backend Developers | 8 orang | Node.js, Express, Sequelize, PostgreSQL
Frontend Developers | 8 orang | Next.js, React, TypeScript, TailwindCSS
Mobile Developers | 4 orang | React Native, TypeScript
DevOps Engineers | 2 orang | Docker, CI/CD, AWS/GCP, PostgreSQL
QA Lead | 1 orang | Test strategy, automation framework
QA Engineers | 2 orang | Manual & automated testing
Project Manager | 1 orang | Agile/Scrum, stakeholder management
Tech Lead | 1 orang | Architecture, code review, mentoring
UI/UX Designer | 2 orang | Figma, design system
TOTAL | 29 orang

## Sprint Planning
SPRINT PLANNING - 7 SPRINTS (2 Minggu/Sprint)
Sprint | Start Date | End Date | Deliverables | Story Points
Sprint 1 | 2026-03-26 | 2026-04-09 | M01 - Authentication & Authorization, M02 - Onboarding & Tenant Setup, M03 - Branch Management | 78
Sprint 2 | 2026-04-09 | 2026-04-23 | M02 - Onboarding & Tenant Setup, M03 - Branch Management, M04 - Settings & Configuration, M05 - Product & Category Management, M06 - Point of Sale (POS), M07 - Inventory Management | 105
Sprint 3 | 2026-04-23 | 2026-05-07 | M06 - Point of Sale (POS), M07 - Inventory Management, M08 - Purchase Orders & Suppliers, M09 - Customer Management, M10 - Loyalty Program, M11 - Promo & Voucher, M12 - CRM | 140
Sprint 4 | 2026-05-07 | 2026-05-21 | M10 - Loyalty Program, M11 - Promo & Voucher, M12 - CRM, M13 - Kitchen Management, M14 - Table & Reservation, M15 - Employee & Schedule, M16 - HRIS | 158
Sprint 5 | 2026-05-21 | 2026-06-04 | M16 - HRIS, M17 - Finance Lite, M18 - Finance Pro (Full Accounting), M19 - SFA (Sales Force Automation), M21 - Fleet Management (FMS), M28 - Reports & Analytics | 149
Sprint 6 | 2026-06-04 | 2026-06-18 | M18 - Finance Pro (Full Accounting), M19 - SFA (Sales Force Automation), M20 - Marketing & Campaigns, M21 - Fleet Management (FMS), M22 - Transportation Management (TMS), M23 - Manufacturing, M24 - Asset Management, M25 - Project Management, M26 - E-Procurement, M27 - Export/Import (EXIM), M28 - Reports & Analytics, M29 - WhatsApp Business Integration, M30 - Marketplace Integration | 222
Sprint 7 | 2026-06-18 | 2026-06-25 | M23 - Manufacturing, M25 - Project Management, M26 - E-Procurement, M27 - Export/Import (EXIM), M29 - WhatsApp Business Integration, M30 - Marketplace Integration, M31 - Website Builder, M32 - Knowledge Base, M33 - Billing & Subscription (SaaS), M34 - Admin Panel (Super Admin), M35 - Notifications & Alerts, M36 - Audit & Security | 110